OFFICIAL COORDINATION REQUEST FOR 

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 14TDA01 Navlock shoal removal
COORDINATION DATE-  12/19/13
PROJECT-  The Dalles Dam Downstream Lock Shoal Removal
RESPONSE DATE- 12/27/13
Description of the problem:  A shoal has been identified downstream of the lower lock at The Dalles Dam. A contract survey identified an area of concern, showing shoaling above the 14' project. A government survey conducted on 14 November confirmed a small shoal at -10' in the channel (see attached drawing). Grab samples were taken of the material and showed it to be sand. We estimate the quantity at around 1,200 CY. It is our intention to move forward with dredging by contract to remove this shoal. A contract clamshell dredge or possibly drag beam may be used to remove the shoal. 
This shoal is impacting towboat operators who use the locks regularly and cannot use the full channel for navigation. 
Type of outage required: A clamshell dredge would likely remove the shoal in a few hours, no outage would be required. The contractor may be able to work around the operation of the navigation lock schedule to move out of the way of traffic if needed. If the shoal is removed with a drag beam the contractor could work around any traffic in the area, causing no impact. 
Impact on facility operation:  None, we can coordinate the contractor with the facility to ensure that dredging operations do not impact facility operation. 
Dates of impacts/repairs: We are working to secure funding for this project. We would like to complete the action within the in water work window (before 28-Feb), preferably as soon as possible. 
Length of time for repairs:  If done using a clamshell dredge the equipment would be set up no longer than 24 hours. Actual dredging would be accomplished in 3-12 hours depending on the size of the clamshell. Use of a drag beam would require multiple passes over the area with a tug. 
Expected impacts on fish passage:  Due to the work being confined to the navlock channel and being completed during the in-water work window, the impacts on salmonids (upstream or downstream migrants) and lamprey are expected to be minimal. 
[image: image1.emf]
Comments from agencies

Final results
Please email or call with questions or concerns.
Thank you, 

Tammy

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

503-961-5733 
Tammy.m.mackey@usace.army.mil 
