OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15 IHR 012 – Stilling basin hydrographic survey

COORDINATION DATE-  August 7, 2015

PROJECT-  Ice Harbor Dam

RESPONSE DATE-  August 13, 2015 (FPOM meeting)

Description of the problem

A hydrographic survey of the Ice Harbor spillway stilling basin is scheduled for September 9, 2015, as part of Walla Walla District’s Dam Safety Program.  This type of survey requires minimal turbulence in the stilling basin to be successful.  Specifically, spill must not be occurring and turbine units 4, 5, and 6 must not be operating while the survey is taking place.  The survey may start as early as 0730 hours and end as late as 1900 hours, so this time span will be requested for the outages.

Turbine units 3 and 4 will be out of service for annual maintenance from August 31 to September 25.  With units 5 and 6 being out of service for this hydrographic survey, that leaves only units 1 and 2 available for service on September 9.  Therefore, on September 9, unit 1 will remain the first priority unit for operation and unit 2 will be second (see Table IHR-4 below, from the 2015 Fish Passage Plan, and also the proposed modified Table IHR-4 from concurrent MOC 15 IHR 011).

Table IHR-4.  Unit Operating Priority for Ice Harbor Dam.

| Operation | Season | Unit Priority (section 4.1) |
| --- | --- | --- |
| Single Unit Operation w/ NO Switching *Switching must occur prior to returning to normal unit priority below. | Year-Round | 1,2,6,5 |
| Multiple Unit Operation | Fish Passage Season March 1 – November 30 | 1,3,6,4,2,5 |
|  |  | If Unit 1 OOS and switching has not occurred: 2,3,6,4,5 |
|  | Winter Maintenance Period December 1 – February 28 | Any order |

Type of outage required

All spill gates and units 4, 5, and 6.

Impact on facility operation

Spill for fish passage ends at 0000 hours on September 1, so there should be no need to spill on September 9.  Units 1 and 2 have the hydraulic capacity to pass the anticipated low river flows.  There will be no need to close fish ladder entrances that are adjacent to the stilling basin or shut off auxiliary water supply (AWS) pumps to conduct this survey.  If the navigation lock needs to be drained, the survey boat will temporarily stop surveying and move to a safe location.

Dates of impacts/repairs

September 9, 2015.

Length of time for repairs

Requesting 0730 hours to 1900 hours, although the actual time needed may be less.

Expected impacts on fish passage

Tailrace flow patterns with units 1 and 2 operating may be different than if units 1 and 3 were operating, which may affect juvenile fish egress and the approach patterns of adult fish to the dam.  Juvenile fish passage is typically low during this period, while adult steelhead and adult fall Chinook passage usually peaks in September and early October.  The AWS pumps will be operating as normal and unit 1 will remain the first priority unit for adult fish attraction to the south fish ladder entrances, so no negative impact to adult fish attraction to the south fishway is expected.

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Ken Fone

Fishery Biologist

Ice Harbor Dam

509-543-3208

kenneth.r.fone@usace.army.mil