OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15TDA09 transformer delivery/installation

COORDINATION DATE-  8 July 2015

PROJECT-  The Dalles Dam

RESPONSE DATE- 9 July 2015 (FPOM) NLT 20 July 2015

Description of the problem - The Dalles is undergoing installation of new CO2 fire suppression components and wiring on all units CY cabinets and other circuits for all units. To complete this work, units need to be off for several hours for installation as well as several hours for testing.

Type of outage required – Units 1-4 are on a single CY cabinet, requiring about 2 hours outage for installation on 7/22. A second outage of about 4 hours on 7/23 is required for testing.

In addition the fish units require a single outage of about 4 hours to complete. It may not require the additional testing that main units require. This work will be done during night hours during the first week of Aug. Attempts will be made to coincide with the already scheduled ROV grating inspection on 8/4, but may need more time than is required for ROV.

Impact on facility operation – Fish unit and priority main unit outages.

Dates of impacts/repairs – Units 1-4 on 7/22. Fish units on 8/4 or night during first week of Aug.

Length of time for repairs – Total 6 hours for units 1-4. And 4 hours for fish units.

Expected impacts on fish passage –

Upstream migrants – None if coincides with already scheduled ROV work. Minimal if schedule for night fish unit outage.

Downstream migrants – This is during the tail end of the subyearling annual passage. Subyearling passage via sluiceway is ~8% of total passage. Subyearlings do not have as strong attraction to east powerhouse (Unit 1) as spring outmigrants. Operational options are; open unit 5 sluicegates for ~2 days to encompass all work on units 1-4 OR leave sluicegates open on unit 1 for the duration. Opening sluicegates for separate 2 and 4 hour periods are not feasible.

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Bob Cordie

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

503-961-5733

Tammy.m.mackey@usace.army.mil