OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15 LWG 004 Lower Granite Juvenile Fish Collection Channel Upgrade

COORDINATION DATE- 11 March 2015

PROJECT- Lower Granite

DATE OF ACTION – October 2014 – April 2017

RESPONSE DATE – N/A

Description of the problem – Update of Work Progress at Lower Granite Dam.

Construction of the Lower Granite Fish Bypass System upgrade began October, 2014 (Notice to Proceed) and will continue until April, 2017 (Project Completion).  Construction activities in 2015 are anticipated to include the drilling and pouring of piers, mining of the transportation channel (the south non-overflow area) and limited portion of the juvenile collection channel (Units 5 and 6), erection of the primary and secondary dewatering structures and transportation flume.  The Fish Screen Slot Plugs will be completed during 2015 (MOC 15 LWG 001).  The majority of collection channel mining activities will occur in 2016 during the extended Juvenile Bypass System (JBS) outage (August 2016 to March 2017).  The Juvenile Fish Bypass Upgrade has numerous milestones with anticipated end dates (Table 1) for different components of the project.

Piers: (Future information will be provided regarding pier construction and potential impacts)

Mining Transportation Channel: (Text will be provided outlining potential impacts)

Mining Collection Channel: (Text will be provided outlining potential impacts)

Primary Dewatering Structure: (Text will be provided outlining potential impacts)

Secondary Dewatering Structure: (Text will be provided outlining potential impacts)

Transportation Flume: (Text will be provided outlining potential impacts)

Outfall:  (Text will be provided outlining potential impacts)

Table 1. – Lower Granite Juvenile Fish Bypass upgrades milestones.

| Activity | Start Date | End Date | MOC Coordination Ref. |
| --- | --- | --- | --- |
| Granite Phase 1A | October 2014 |  |  |
| Drill and Pour Piers |  |  |  |
| Mobilize to PDS | 27 March | 27 March | 15 LWG 005 |
| Drill pier #22 | 30 March | 31 March | TBD |
| Drill pier #20 | 1 April | 1 April | TBD |
| Pour piers #20 & #22 | 2 April | 2 April | TBD |
| Drill pier #21 | 3 April | 3 April | TBD |
| Mining Transportation Channel |  |  |  |
| Excavation of ??? |  |  |  |
| Fish Screen Slot Plugs |  |  | 15 LWG 001 |
| Mining Collection Channel |  |  |  |
| Extended Outage |  |  | 13 LWG 017 |
| Primary Dewatering |  |  |  |
| Survey PDS |  |  |  |
| Secondary Dewatering |  |  |  |
| Transportation Flume |  |  |  |
| Survey Transport Flume | Add date |  |  |
| Outfall Pipe |  |  |  |

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Scott Fielding

Fishery Biologist

US Army Corps of Engineers

201 North 3rd Avenue

Walla Walla, WA 99362

509-527-7236

Email: scott.d.fielding@usace.army.mil

John C. Bailey

Fishery Biologist

US Army Corps of Engineers

Walla Walla District

Operations Division

201 N. 3rd St

Walla Walla. WA 99362-1876

Phone: (509) 527-7123

Fax:   (509) 527-7823

Email: john.c.bailey@usace.army.mil