OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15 LWG 005 Lower Granite Juvenile Fish Bypass Upgrades - Pier Drilling and Survey Work near the Adult Fish Ladder and Juvenile Transportation Pipe.

COORDINATION DATE- March 11, 2015

PROJECT- Lower Granite

DATE OF ACTION – Between March 30 and April 3, 2015

RESPONSE DATE-   To be discussed at 12 March 2015 FPOM Meeting

Description of the problem

Construction activities associated with the Lower Granite fish bypass system upgrade will require work to be completed within 100’ of the adult ladder and within 20’ of juvenile fish transportation pipes.  The USACE has placed work restrictions (as coordinated with FFDRWG) on JBS Phase 1a constructions activities while working near active adult and juvenile fishways.  The work restriction will require the contractor to work during the hours of 1800 to 0600 when conducting work activities near the fish ladder including the drilling of piers to support the elevated transportation flume.  Sunshade material will be placed in areas in which construction equipment may cause rapid shadowing in the adult ladder.

The contractor is making progress in getting piers drilled and poured for the Juvenile Fish Bypass upgrade during the winter maintenance period.  The contractor currently anticipates drilling two piers within 100’ of the adult ladder during the April timeframe.  Activities associated with the two piers are scheduled to begin 30 March and be completed 3 April.  The excavation of the pier cap associated with pier #1 will require the contractor to excavate with 10.13’ of the 42’ pipe.  This excavation is anticipated to be completed in April.  Additionally, the contractor will be conducting surveys to layout the pier cap for pier #1, the primary dewater structure, and the transportation flume.

Work Restrictions near Adult Ladder and Juvenile Fish Transportation Pipes

The USACE has placed contractual restrictions when working in the vicinity of active adult and juvenile fishways.  The adult fishway work window is from 1 January to 28 February.  The adult fishway restricted work window is from 1 March to 31 December.  The restricted work window requires if activities are to be completed near the adult fishway then the contractor if required to perform activities between the hours of 1800 to 0600.  The USACE has set a work restriction of 10’ from the juvenile fish transportation pipe.

Type of outage required

No outage required

Impact on facility operation

No impacts to facility operations other than coordination of various onsite activities

Dates of impacts/repairs

Survey work anticipated to be completed 11 March and 27 and 30 March

Pier drilling and pouring work near adult ladder anticipated 30 March to 3 April

Length of time for repairs

To be determined; an update on activities will be provided to FPOM at the April meeting.  Schedule of activities related to pier drilling may be delayed slightly due to varying schedule and site conditions requirements.

Expected impacts on fish passage

No expected impacts are anticipated to be associated with the site survey work.  As adult passage through the LGR adult ladder is minimal during nighttime periods, work involving significant sound/vibration, including the drilling and pouring of piers, will be restricted to the hours of 1800 to 0600 in order to limit impacts to fish passage.

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Scott Fielding

Fishery Biologist

US Army Corps of Engineers

201 North 3rd Avenue

Walla Walla, WA 99362

509-527-7236

Email: scott.d.fielding@usace.army.mil

John C. Bailey

Fishery Biologist

US Army Corps of Engineers

Walla Walla District

Operations Division

201 N. 3rd St

Walla Walla. WA 99362-1876

Phone: (509) 527-7123

Fax:   (509) 527-7823

Email: john.c.bailey@usace.army.mil