OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15 LWG 004 Lower Granite Juvenile Fish Collection Channel Upgrade Update 14 May 2015

COORDINATION DATE- 11 March 2015

PROJECT- Lower Granite

DATE OF ACTION – October 2014 – April 2017

RESPONSE DATE – N/A

Description of the problem

Construction of the Lower Granite Fish Bypass System (JBS) upgrade began October, 2014 (Notice to Proceed) and will continue until April, 2017 (Project Completion).  The major components of Phase 1A and Phase 1B include:

- Juvenile Collection Channel widening and orifice enlargement (14”)

- Transportation channel inside dam (South non-overflow section)

- Transportation channel outside dam

- Primary dewatering structure

- Re-use of excess water to augment both the adult fishway and the adult trap

- Fish transport flume (including loop structure)

- Secondary dewatering structure

- New emergency bypass outfall

- New primary bypass outfall (Phase 1b)

- Tie-in to existing Juvenile Fish Facility (JFF)

In 2015, construction activities are anticipated to be conducted under two main construction contracts.  Overall, major construction activities will primarily include the plugging and filling of the unused Fish Screen Slots (FSS), drilling and pouring of transportation channel and flume support piers, mining of the transportation channel through the dam (south non-overflow area) and mining of limited portion of the juvenile collection channel (Units 5 and 6), erection of the primary and secondary dewatering structures and transportation flume.

Construction activities will continue through 2016 and early 2017 in order to complete all project components including mining of the juvenile collection channel, completion of elevation transportation channels and dewatering structures, and final tie-in of new system components into the existing infrastructure (i.e. crossover).  An extended JBS outage has been coordinated through FPOM for 1 August 2016 to 24 March 2017(13 LWG 017) in order to facilitate collection channel mining and final JBS cross-over activities necessary for integration of the new systems into the JBS.

A variety of restrictions are in place to ensure juvenile and adult fish passage systems are adequately maintained during the respective passage seasons.  At the time of the Phase 1a contract award, the Corps provided the Contractor the ability to conduct heavy construction activities during the standard in-water (15 Dec to 28 February) and during a subset of the standard unwatered work windows (JBS – 1 Dec to 24 March; adult ladder 1 Jan to 28 February) as well as one extended unwatered JBS period of 1 August 2016 to 24 March 2017 (13 LWG 017).  Any other Phase 1a heavy construction work not conducted during these periods must be generally completed between the hours of 1800 to 0600, unless coordinated otherwise (e.g. 15 LWG 007).

Furthermore, the 2015 Fish Passage Plan, Section 2.1.1, states that research, non-routine maintenance activities and construction will not be conducted within 100’ of any fishway entrance or exit, within 50’ of any other part of the adult fishway, or directly in, above or adjacent to any fishway, unless coordinated by the Project, Walla Walla District (NWW) Operations and/or Planning or Construction office through FPOM or FFDRWG. As a result of this 2015 FPP requirement, construction activities associated with Phase 1 JBS upgrade efforts will be further coordinated with FPOM and FFDRWG as appropriate and identified in the following table.

Table 1. – Lower Granite Juvenile Fish Bypass upgrades MOC coordination’s.

| Activity | Start Date | End Date | MOC Coordination Ref. |
| --- | --- | --- | --- |
| Granite Phase 1A | October 2014 | April 2017 | 15 LWG 004 |
| Mining Transportation Channel inside Dam |  |  |  |
| Mining inside the dam | 12 May | 30 Sept | 15 LWG 010 |
| Transportation Channel outside dam |  |  |  |
| Drill and pour piers | 27 March | 30 April | 15 LWG 007 |
| Fish Screen Slot Plugs |  |  |  |
| Units 1 ,2 & 3 | 1 Oct 2014 | 25 Mar 2015 | 13 LWG 022 |
| Units 4, 5 & 6 | Jul 2015 | Oct 2015 | TBD |
| Mining Collection Channel |  |  |  |
| Extended Outage (Units 1-4 & Crossover activities) | 1 Aug 2016 | 24 Mar 2017 | 13 LWG 017 |
| Unit 5&6 widening | 15 Dec 2015 | 28 Feb 2016 | TBD |
| Primary Dewatering Structure |  |  |  |
| Drill and pour piers |  | 30 April | 15 LWG 007 |
| Secondary Dewatering Structure |  |  |  |
| Drill and pour piers |  | 30 April | 15 LWG 007 |
| Transportation Flume |  |  |  |
| Drill and pour piers |  | 30 April | 15 LWG 007 |
| Emergency Outfall Pipe (Phase 1a) | 15 Dec 2015 15 Dec 2016 | 28 Feb 2016 28 Feb 2017 | N/A (Standard in-water work window) |
| Primary Outfall Pipe (Phase 1b) | TBD (15 Dec 16) | TBD (28 Feb 17) | Likely Not Applicable (Standard in-water work window anticipated) |

Comments from agencies

Final results

Please email or call with questions or concerns.

Thank you,

Scott Fielding

Fishery Biologist

US Army Corps of Engineers

201 North 3rd Avenue

Walla Walla, WA 99362

509-527-7236

Email: scott.d.fielding@usace.army.mil

David Trachtenbarg

Fishery Biologist

US Army Corps of Engineers

201 North 3rd Avenue

Walla Walla, WA 99362

509-527-7238

Email: david.a.trachtenbarg@usace.army.mil

John C. Bailey

Fishery Biologist

US Army Corps of Engineers

Walla Walla District

Operations Division

201 N. 3rd St

Walla Walla. WA 99362-1876

Phone: (509) 527-7123

Fax:   (509) 527-7823

Email: john.c.bailey@usace.army.mil