OFFICIAL COORDINATION REQUEST

FOR NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 15TDA05 railroad rail replacement

COORDINATION DATE- May 21, 2015

PROJECT- The Dalles Dam

RESPONSE DATE- August 13, 2015

Description of the problem. This request was previously coordinated and addresses one element of the overall crane rail replacement and railroad removal project.  Since that time, the Corps has revised the overall project schedule and decided to construct the project using two separate contracts.  Railroad removal will proceed in 2016 and 2017.  Crane rail replacement will be delayed until 2018 and 2019 and will be addressed in a separate request.  Because of the change in schedule and contracting plan, the Corps would like to coordinate an adjusted schedule for the railroad removal and eliminate the need for multiple mobilizations by the railroad removal contractor.

Type of outage required. None. Derelict railroad rail removal on the Intake and Tailrace Powerhouse decks and on the approach to the intake deck.

- July through Nov 2016, railroad removal on intake deck (including fish units; the units would remain operational throughout);July through Nov 2016 (nighttime work for 2 weeks or less), railroad removal on approach to intake deck over east fish ladder exit (approximate area depicted below);

Dec 2016 through Feb 2017 IWWW, railroad removal on tailrace deck.

Figure 1. Approximate area of railroad removal on approach to intake deck.

Fish coordination issues will be involved with this work

1) Intake deck work will be approximately 10 ft downstream from the downstream edge of the Ice and Trash Sluiceway and would therefore be within 100’ of entrances and 50’ of other areas of the fishways.

2) Work on the approach to the intake deck will occur over or within 50’ of fishways.

Impact on facility operation – There is no direct impact expected to the fishway or fishway operation due to this work.  There will be rail removal within 50’ of the ITS entrances and channel during the intake deck work.  The Corps would require work on the approach to the intake deck (over/near the east fish ladder exit) to be done at night, and would complete this work prior to the start of construction work on the AWS project.

Dates of impacts/repairs – Impacts to the ITS entrances and channel, and east fish ladder exit, are expected to occur from July – November 2016.

Length of time for repairs – July – November 2016 and December 2016 - February 2017. The Corps expects that the work on the approach to the intake deck (over/near the east fish ladder exit) would take no longer than 2 weeks.

Expected impacts on fish passage –

Upstream migrants.  There are no expected impacts to upstream migrants as the work over TDA-E will occur during the winter maintenance period and coincide with the outages planned for the Back-up AWS work.

Minimal or no impacts are expected. Work over the fishway exit will occur the first 2 weeks of Aug which will be after sockeye passage and before fall Chinook passage. Fall steelhead passage are beginning to increase during that time (~1800 daily), but little night passage is expected.

Downstream migrants.  Fish migrating downstream may be impacted by the work over the ITS.  It is expected that once fish enter the ITS they will quickly move through and that the derelict railroad rail removal work will not cause an impact to fish once they are in the channel.  Open gates will be adjusted as rail removal proceeds across the deck.  The open gates will be kept as close to the priority unit as seems reasonable, depending on noise and vibration generated by the rail removal.

Lamprey –There is substantial lamprey passage at night, However, there are no expected impacts to lamprey passage. Studies have shown lamprey are not able to detect vibrations due to lack of swim bladder.

Bull Trout – impacts to Bull Trout are expected to be similar to other upstream migrating salmonids.  Very few Bull Trout have been counted at TDA in the last 10 years.  “WDFW and COE provided a list of anecdotal sightings/captures of bull trout in the mainstem Columbia River.  From 2000 through 2012 there were eleven bull trout reported.  Three were downstream of Bonneville Dam, with two at the mouth of Hamilton Creek (CRM 143) and one in 2005 at the Bonneville Dam Smolt Monitoring Facility (CRM 144).  Upstream of the dam, one bull trout was found at Cascade Locks (CRM 149), two at Drano Lake (CRM 162), two at the mouth of the Klickatat River (CRM 180.5), one in 2002 at the John Day Dam Smolt Monitoring Facility (CRM 215), and one sighting at Dog Creek Falls by a reputable WDFW creel sampler who observed 18-24” cuts or dollies working old redds below the splash pool over the course of two weeks. “

Comments from agencies

NOAA Fisheries - -----Original Message-----
From: Gary Fredricks - NOAA Federal [mailto:gary.fredricks@noaa.gov] 
Sent: Tuesday, May 26, 2015 2:22 PM
To: Mackey, Tammy M NWP
Cc: Trevor Conder - NOAA Federal; Cordie, Robert P NWP; Lorz, Tom; Rerecich, Jonathan G NWP
Subject: [EXTERNAL] Re: FPOM: Official Coordination - TDA MOCs 15TDA04 and 15TDA05

Tammy,  After a quick review I really don't see a serious issue with either 15TDA04 or 15TDA05.  Also, I think the authors did a good job laying out the issues in both.   I agree with Fenton's recommendations for ITS operation in 15TDA05.  I would be more concerned with downstream steelhead passage late in the IWW period than anything else, so we should probably talk about that.  An early start to the N. Ladder outage in 15TDA04 would have minimal impact.  I would like to have a little more detail on the rock cleanup work in 15TDA04.  I'm assuming a periodic use of a jack hammer to remove the "protrusions"??   Perhaps we could talk about the timing of this work a bit (space it out, bunch it up, do it at night, a little attraction spill at the N. Ladder, etc.) but overall I suspect the impact to fish passage would be small in early March.  More on June 2.  Gary

Final results –

FPOM met on 2 June to discuss the crane  and railroad rail work.

- 15TDA05 railroad rail removal – MOC will be modified and has concurrence.

  - Railroad rail removal.  The derelict rails would be removed during the summer while units are available for service. Fredricks asked if there would be any excessive noise.  He recalled the work completed at BON and noted it wasn’t much of an issue.  Webber suggested a chipping hammer may be used but not a jackhammer.  Fredricks asked how noisy and how consistently noisy would the work be.   Fredricks expressed concern about the rail removal during the day.  He suggested moving the ITS gates to a unit not under the rail removal work.  Cordie said it is possible to move the gates to units not under the rail removal work.  After the work has moved beyond the normal open gates, return to the FPP criteria.  Working at night is another option.  Bettin asked if the railroad rail removal was O&M funded.  Turaski said rail removal is part of the larger BPA funded project.  Fredricks recommended clarifying that there are two rail systems in the MOC.  ACTION: Cordie will separate the MOCs into two separate MOCs.  One will address the railroad rail removal, the other will address the crane rail replacement.  FPOM is most concerned about the July/August timeframe for juvenile passage.  Fredricks suggested Cordie come up with a plan for whether gates are moved to an adjacent unit or spaced at least a unit away from the priority unit.

13 August 2015 FPOM - Revised 15TDA05 Railroad rail removal.  Pending.  Fredricks has concerns about the MOC and doing the rail work over the TDA-E exit.  Fredricks would prefer the approach not be done in July; he would prefer November.  Lorz agreed that October or November would be preferred.

Please email or call with questions or concerns. Thank you,

Bob Cordie

TDA Project Fisheries

541-506-7800

Tammy Mackey

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

Tammy.m.mackey@usace.army.mil