# Fish Passage Plan (FPP) Change Request Form

Change Form # & Title:	17AppA001 – Doble Testing Schedule for 2017

Date Submitted:		December 15, 2016

Project:			NWW Projects

Requester Name, Agency:	Corps NWW

Final Action:

FPP SECTION:  Appendix A – Special Project Operations

JUSTIFICATION:  FPOM requested the yearly schedule of Doble testing at Walla Walla District (NWW) projects to be added to Appendix A.  The schedule will be coordinated each year in a change form (one change form for all projects).

PROPOSED CHANGES:

1.4. Doble Testing at NWW Projects.

- 1.4.1. Doble testing of transformers at the NWW projects is required every three years and must be conducted during warm, dry conditions (July-August).  During testing, the transformer and associated units must be out of service (OOS).  Tests are scheduled concurrent with already scheduled unit outages to the extent possible, and timed to avoid or minimize impacts to fish. The schedule for the current year is defined in Table A-1 below. For more information, refer to the FPP project-specific chapters and sections below.

Table A- 1. Schedule for Doble Testing at Corps NWW Projects in 2017.

| Project | Dates | Outage (Transformer, Units) | Notes |
| --- | --- | --- | --- |
| IHR | July 31-August 3 | TW3,4 (Units 3, 4) | Doble Testing |
| LMN | July 24–July 27 |  | Perform work on high voltage disconnects |
| LGS | Aug 7–11 | T1 (Units 1-4) | Possibly Capacitative Coupling Potential Device (CCPD) testing as well |
| MCN | Jul 17-Jul 21 | T1 (Units 1–2) | Doble Testing |
| MCN | Jul 24-Jul 28 | T2(units 3-4) | Doble Testing |

COMMENTS:

RECORD OF FINAL ACTION: