These are the milestones for Dworshak Unit 3 Rehab now underway:

Generator Disassembly Start 19 Sep 2016

Rotor Removed 11 Oct 2016

Winding Removal Complete  29 Oct 2016

Stator Core Removal Complete 05 Nov 2016

Install Stator Core Complete 08 Dec 2016

Rotor Work Complete 24 Jan 2017

Winding Install Complete 11 Mar 2017

Unit Reassembly Complete 05 Apr 2017

U3 RTS 01 May 2017.

Special Field Tests Completion 15 May 2017

Model Validation Testing completion 01 July 2017