# OFFICIAL COORDINATION REQUEST FOR NON-

# ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE – 17 IHR 011 MOC Trolley and Fish Pipe Install Outage

COORDINATION DATE – 27 July 2017

PROJECT- Ice Harbor Dam

RESPONSE DATE – 10 August 2017

Description of the problem: The installation of the new turbine runner in Unit 2 at Ice Harbor Dam is scheduled for completion in late winter of 2017/2018. Biological testing for Unit 2 is scheduled for fall of 2018. Fish are currently being cultured for use in this testing by PNNL. Biological testing of Unit 3 would occur following the Unit 3 install. Additional studies would occur after the installation of Unit 1. Trolley pipes, to be used for study fish releases in the tailrace for these studies were not installed in January and February 2017 because of early high water and multiple turbine outages at Ice Harbor Dam. We request an extension of the work window (November 15, 2017 through February 28, 2018) for installation of the trolley pipes required for this and future testing. This time extension would allow for flexibility to complete all pipe installs in one work window that would save time and money.

Other outage times considered included late summer and early fall. These alternatives are associated with greater negative impacts to fisheries resources and were discarded for that reason.

Type of outage required: Work will be performed during an extended winter work window (November 15, 2017 – February 28, 2018).  The outage will require different combinations of turbines and fish pumps depending on the trolley or fish pipe being installed (See Attachment 1).  Pipe installs on the power house will require the unit for the install and any adjacent units be out of service for the duration of the install.  For example, when unit 2 pipes are installed, units 1 through 3 will need to be out of service. Pipe installs on the fish pumps will require the fish pumps to be out of service as well as units 1 through 3. Due to the complexity of the work and conditions, all installations (dives) will be performed during the day. To the degree possible, work that directly impacts priority units, fish pumps, and fishways will be performed during the normal winter maintenance period.  Outage includes time for project staff to dewater and secure fish pumps and fishways.

Dates of impacts/repairs: November 15, 2017 – February 28, 2018.

Length of time for repairs: Total time of work on site is estimated between 40 to 60 d (See Attachment 1). Actual number of work days will depend on river flows and climate conditions.

Impact on fish facility operation: Short term impacts will include fish pump and fishway outages during pipe installs.

This work may be performed before and/or after the unit 2 commissioning; depending on commissioning schedule. Attachment 1 shows proposed outage needs, but does not yet provide specific dates.  Priority units (1 and 3) will require outages to allow fish pipe and trolley pipe installs. For example, unit 1 will require outages totaling 276 hours to complete all installs.  Dive safety will require all spillbays to be out of operation for all dive times.

# Analysis of potential impacts to fish:

- 10-year average passage during the dates of impact for adults and juveniles for each affected listed species.

On average 2,935 (0.6%) adult salmon and steelhead pass Ice Harbor Dam from November 15 to December 31. Of these, 2,879 are steelhead, 48 are Chinook, and 8 are Coho.  No adult sockeye or lamprey pass during this time period. At least one of the two ladders at the project will be in operation at all times, but priority units and fish pumps may be out of service. The north fish ladder and fish pumps will be operational for fish passage while the south ladder is out of service.

Juvenile fish facilities are not in operation during the proposed outage. Very few juvenile fish are expected to pass the project during this time period.

- Statement about the current year’s run (e.g., higher or lower than 10-year average).

Steelhead forecast for the Snake River to Lower Granite dam is 59,700 for 2017, with B run component estimated to be 5,475. This is below the 10 yr average run of 151,687.

- Estimated exposure to impact for adults and/or juveniles, as appropriate, by species (number or percentage of the 10 yr average that occurs during dates of action).

See number 1 above - To the degree possible, work that directly impacts priority units, fish pumps, and fishways will be performed during the normal winter maintenance period.  Short term delays may occur for a small portion of adult populations as priority units are switched to accommodate dives and fish search for fishways. No anticipated future impacts to fish from proposed actions.

- Type of impact for adults and/or juveniles, as appropriate, by species (increased delay, exposure to predation, exposure to a route of higher injury/mortality rate, exposure to higher TDG, etc.).

Short term delays may occur for a small portion of adult populations as priority units are switched to accommodate dives and fish search for fish ways. No anticipated future impacts to fish from proposed actions.

Final judgement on scale of expected impacts (negligible, minor, significant) on:

  - Downstream migrants: Negligible. Less than 1/10th of a percent of juvenile fish are moving during this time period. Installation would have no direct effect on those that are.

  - Upstream migrants (including Bull Trout): Negligible. Less than 1 percent of adult fish are migrating during this time period and at least one ladder will remain open at all times.

  - Lamprey: Negligible. No adults are passing at this time and about 1/10th of one percent of all juveniles pass during this time. Passage will still be open.

# Comments from agencies Final coordination results After action update

Please email or call with questions or concerns. Thank you,

Charles Chamberlain, Fish Biologist US Army Corps of Engineers

201 North Third Avenue Walla Walla, WA 99362-1876 Phone:  509-527-7298

Email: charles.b.chamberlain@usace.army.mil

Attachment 1

Outage Needs and Schedules for Contract 17-C-0004 HLD Trolley and Fish Release Pipes

| Outages Needed for FY 18 November to February |  |  |  |  |  |  |  |  |  | Trolley Pipes (Future Studies) | Timing | Number of Turbines Available |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | South Fish Pumps | Fishway Entrance | South Fish Ladder | Spillway |  |  |  |
| 36 hrs | 36 hrs |  |  |  |  | 1 pump 36 hrs | SSE1&2 36 hrs | 36 hrs | 36 hrs | Unit 1 | Jan 1 - 31 | 4 |
| 36 hrs | 36 hrs | 36 hrs |  |  |  | 1 pump 36 hrs | SSE 1&2 36 hrs | ? | 36 hrs | Unit 2 | Jan 1 - 31 | 3 |
|  | 36 hrs | 36 hrs | 36 hrs |  |  |  |  |  | 36 hrs | Unit 3 | Nov 15 - Dec 30 | 3 |
|  |  | 36 hrs | 36 hrs | 36 hrs |  |  |  |  | 36 hrs | Unit 4 | Nov 15 - Dec 30 | 2 |
|  |  |  | 36 hrs | 36 hrs | 36 hrs |  |  |  | 36 hrs | Unit 5 | Nov 15 - Dec 30 | 2 |
|  |  |  |  | 36 hrs | 36 hrs |  | NPE 1&2 36 hrs |  | 36 hrs | Unit 6 | Nov 15 - Dec 30 | 3 |
| 4 days | 6 days | 6 days | 6 days | 6 days | 4 days | 4 days | 2 days | 2 days | All | Turbine Trolley Pipe Sub Totals |  |  |

| Outages Needed for FY 18 November to February |  |  |  |  |  |  |  |  |  | Fish Release Pipes (Current Study) | Timing | Number of Turbines Available |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | South Fish Pumps | Fishway Entrance | South Fish Ladder | Spillway |  |  |  |
| 60 hrs | 60 hrs | 60 hrs |  |  |  | 1 Pump 60 hrs | SSE 1&2 60 hrs | ? | 60 hrs | Unit 2 | Jan 1 - 31 | 3 |
|  | 60 hrs | 60 hrs | 60 hrs |  |  |  |  |  | 60 hrs | Unit 3 | Nov 15 - Dec 30 | 3 |
| 3 days | 6 days | 6 days | 3 days | 0 days | 0 days | 3 days | 0 days | 0 days | All | Release Pipe Sub Total |  |  |

| Outages Needed for FY 18 November to February |  |  |  |  |  |  |  |  |  | Fish Pump Trolley Pipes (Future Studies) | Timing | Number of Turbines Available |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unit 1 | Unit 2 | Unit 3 | Unit 4 | Unit 5 | Unit 6 | South Fish Pumps | Fishway Entrance | South Fish Ladder | Spillway |  |  |  |
| 36 hrs | 36 hrs | 36 hrs | ? |  |  | 36 hrs | SSE 1&2 36 hrs | ? | 36 hrs | 1* | Jan 1 - 31 | 2-3 |
| 36 hrs | 36 hrs | 36 hrs | ? |  |  | 36 hrs |  |  | 36 hrs | 2 | Jan 1 - 31 | 2-3 |
| 36 hrs | 36 hrs | 36 hrs | ? |  |  | 36 hrs |  |  | 36 hrs | 3 | Dec 1 - 30 | 2-3 |
| 36 hrs | 36 hrs | 36 hrs | ? |  |  | 36 hrs |  |  | 36 hrs | 4** | Dec 1 - 30 | 2-3 |
| 8 Days | 8 Days | 8 days | 0 days | 0 days | 0 days | 8 days | 0 days | 0 days | All | Fish Pump Trolley Pipe Sub Totals |  |  |
| 15 days | 20 days | 20 days | 9 days | 6 days | 4 days | 15 days | 2 days | 2 days | All | Total Days Needed |  |  |
| *Furthest Upstream ** Furthest Downstream |  |  |  |  |  |  |  |  |  |  |  |  |

Priority Units Used

Possible Outage Needed