## Sheet1
FPOM JAN-MAR Transmission Outages That Have Potential to Limit Generation
ONGOING Continuous Outages 2019- 2020
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
N/A
JANUARY - 2019 (45 day outage planning process completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
John Day PH-John Day 1 500kV Line OOS | 12/5/18 (7:00)- 1/25/19 (17:00) | Continuous | U 1-4 OOS | COE work- To replace disconnect switch on PH line.
McNary: NWPUD Fishway Powerhouse #6 Line relays | 2019-01-04 | 9:00-15:00 | McNary PH Units 13 and 14 and fishway restricted to 0MW . | Relay maintenance and trip checks.
Bonneville PH 1-North Bonneville NO 1 230KV Line | 2019-01-28 | 9:00-12:00 | BONN Units 3 & 4 limited to 0MW. | NERC required annual maintenance
The Dalles PH-Big Eddy 4 230kV Line | 1/28/19 (8:00)-2/5/19 (17:00) | Continuous | TD Units 9-12 OOS | COE work- Clearance for Arc Flash Mitigation
Bonneville PH 1-North Bonneville 2 230kV Line | 2019-01-30 | 9:00-12:00 | BONN Units 5 through 8 OOS | Nerc Required Annual Mainteneance
McNary: Main Bus Section 2 | 2019-01-31 | 7:30-17:00 | McNary PH Units 13 and 14 and fishway restricted to 0MW . | Supporting Transformer and PCB replacement
FEBRUARY - 2019 (Tentative: 45 day outage planning process completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH-Big Eddy 4 230kV Line OOS | 1/28/19 (8:00)-2/5/19 (17:00) | Continuous | TD Units 9-12 OOS. | COE work- Arc Flash Mitigation
Ice Harbor-Franklin 2 115kV Line OOS | 2/4/19 (6:30)-2/16/19 (17:00) | Continuous | Ice Harbor Units 3 & 4 are OOS. | COE work- Disconnect installation
John Day PH-John Day 3 500kV Line OOS | 2/4/2019 (6:00)-2/6/19 (17:00) | Continuous | JD Units 9-12 OOS | COE work- New e-crane
John Day PH-John Day 1 500kV Line OOS | 2/11/2019 (6:00)-2/15/19 (17:00) | Continuous | JD Units 1-4 OOS | COE work- switching powerhouse from temp. to permanent 480V power source.
The Dalles PH-Big Eddy 5 230kV Line OOS | 2/11/2019 (8:00)-2/19/19 (17:00) | Continuous | TD Units 13-16 OOS. | COE work - Arc flash mitigation
John Day PH-John Day 2 500kV Line OOS | 2/19/2019 (8:00)-2/26/19 (14:30) | Continuous | JD Units 5-8 OOS | Rewiring relay and performing trip checks
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (6:30)-3/7/19 (17:00) | Continuous | TD Units 5-8 | Connect T3 CT circuit
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (8:00)-3/7/19 (17:00) | Continuous | TD Units 5-8 | COE work - Arc flash mitigation
MARCH - 2019 (Tentative: 45 day outage planning process NOT completed)
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (6:30)-3/7/19 (17:00) | Continuous | TD Units 5-8 | Connect T3 CT circuit
The Dalles PH-Big Eddy 3 230kV Line OOS | 2/25/2019 (8:00)-3/7/19 (17:00) | Continuous | TD Units 5-8 | COE work - Arc flash mitigation
The Dalles PH-Big Eddy 4 230kV Line OOS | 3/11/2019 (8:00)-3/21/19 (18:00) | Continuous | TD Units 9-12 | COE work - pre work for T5 replacement
The Dalles PH-Big Eddy 6 230kV Line OOS | 3/18/2019 (8:00)-3/26/19 (17:00) | Continuous | TD Units 17-22 | COE work - Arc flash mitigation