OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE – 19BON55 PH2 OWS & Head Cover Pump Installation

COORDINATION DATE – 06 September 2019

PROJECT – Bonneville Lock and Dam

RESPONSE DATE – September FPOM or 20 September.

Description of the problem:

The U.S. Army Corps of Engineers, Portland District proposes to upgrade and modify the oil and water separator (OWS) and head cover pumps at Bonneville Dam, Powerhouse 2 (PH2). These modifications will help to assure compliance with the requirements of a future National Pollutant Discharge Elimination System permit. The work includes the installation of two new oil water separators in the abandoned ice and trash chute at Bonneville Dam Powerhouse 2, installation of piping to the new oil water separators from the head cover pumps for all generating turbines including the fish units on the north end of Bonneville Powerhouse 2, modifications to the existing oil water separator, and incidental related work.

B2 Current Layout

Corner Collector

Corner Collector

New OWS Housing

Type of outage required –Work will be within 50’ of the fish ladder. Unit outages will occur during the winter and a ladder entrance closure will occur this winter for a dive.

Impact on facility operation (FPP deviations) 
Construction of the new downstream OWS system will require coordination of FPP section 2.1.3. Research, non-routine maintenance, fish-related activities, and construction will not be conducted within 100' of any fishway entrance or exit, within 50' of any other part of the adult fishway, or directly in, above, or adjacent to any fishway, unless coordinated with FPOM or FFDRWG by the Project, District Operations and/or Planning or Construction office. Alternate actions will be considered by District and Project biologists in conjunction with the Regional fish agencies on a case-by-case basis.

Additionally, modifications to unit priority will be required for tying main units into the new piping and the installation of a new discharge pipe intermittently during the months of January through March. 

Impact on unit priority
PH2 will remain the priority powerhouse. Bradford Island fishway will be out of service for winter maintenance during the IWWP. During unit outages, the FPP guidelines on using the next available unit will be followed.

Impact on forebay/tailwater operation
The work is not expected to impact forebay or tailwater operations.

Impact on spill
Forced spill could occur during the month of January when dive work is scheduled if units are not available.

Dates of impacts/repairs:

Proposed Work Windows
07 October 2019 through 30 November 2019: Night Operations from the hours of 1700 to 0600. 
01 December 2019 to 29 February 2020: Day/Night Operations, unrestricted work hours. 
01-28 March 2020: Night Operations from the hours of 1730 to 0600.

During the above identified work windows, the Contractor has no restrictions to noise and vibration impacts to fish or fish structures caused by heavy construction or diving. Outside the IWWP in the months of October and November, the Contractor may use heavy equipment but only at night from 5pm to 6am; in the month of March the Contractor may use heavy equipment and dive but only at night from 7:30pm to 6am.

Work activities outside the IWWP identified and the night time durations stated above, within 50' proximity to the ladder structures shall be limited to light construction (hand tools), material movements, electrical conduit installation, lighting installation, mechanical pipe installation, welding, painting, and other activities that will not produce loud noises or vibration loading to the ladder structure.

Proposed Unit outages schedule

Tie in Unit #18-#14 to New OWS Piping, MU18-14 OOS – 26 February through 03 March.

Tie in Unit #11-#13 to New OWS Piping, MU 11-13 OOS – 04 March through 12 March.

Install River Discharge Piping – 01 through 10 January (MU 11-12 OOS, potentially additional units).

Analysis of potential impacts to fish

- 10-year average passage by run during the period of impact for adults and juvenile listed species, as appropriate for the proposed action and time of year.

  - The majority of out-migrating juveniles pass the project during spring and summer spill 10 April through 31 August. The construction of the new downstream OWS system is thought to have minimal effects on juveniles.

- Statement about the current year’s run (e.g., higher or lower than 10-year average).

  - We are currently well below the 10-year average for all species of salmonids.

- Estimated exposure to impact by species and age class (i.e., number or percentage of run exposed to an impact by the action).

*These figures account for daily passage at both Bradford Island and Washington Shore. The proposed work will only occur during nighttime hours, 1700-0600 for October & November and 1730-0600 in March at PH2. Estimated impact will be far less.

| Date | Daily Total Salmonids | 10 YR AVG | % Affected |
| --- | --- | --- | --- |
| 10/7 | 4470 | 1720079 | 0.260% |
| 10/8 | 4942 | 1720079 | 0.287% |
| 10/9 | 4863 | 1720079 | 0.283% |
| 10/10 | 4187 | 1720079 | 0.243% |
| 10/11 | 4262 | 1720079 | 0.248% |
| 10/12 | 3231 | 1720079 | 0.188% |
| 10/13 | 3001 | 1720079 | 0.174% |
| 10/14 | 3057 | 1720079 | 0.178% |
| 10/15 | 2507 | 1720079 | 0.146% |
| 10/16 | 2773 | 1720079 | 0.161% |
| 10/17 | 2307 | 1720079 | 0.134% |
| 10/18 | 2736 | 1720079 | 0.159% |
| 10/19 | 2003 | 1720079 | 0.116% |
| 10/20 | 1751 | 1720079 | 0.102% |
| 10/21 | 1604 | 1720079 | 0.093% |
| 10/22 | 1903 | 1720079 | 0.111% |
| 10/23 | 1734 | 1720079 | 0.101% |
| 10/24 | 1379 | 1720079 | 0.080% |
| 10/25 | 1392 | 1720079 | 0.081% |
| 10/26 | 1142 | 1720079 | 0.066% |
| 10/27 | 1283 | 1720079 | 0.075% |
| 10/28 | 890 | 1720079 | 0.052% |
| 10/29 | 991 | 1720079 | 0.058% |
| 10/30 | 874 | 1720079 | 0.051% |
| 10/31 | 908 | 1720079 | 0.053% |
| 11/1 | 952 | 1720079 | 0.055% |
| 11/2 | 726 | 1720079 | 0.042% |
| 11/3 | 753 | 1720079 | 0.044% |
| 11/4 | 588 | 1720079 | 0.034% |
| 11/5 | 565 | 1720079 | 0.033% |
| 11/6 | 520 | 1720079 | 0.030% |
| 11/7 | 440 | 1720079 | 0.026% |
| 11/8 | 364 | 1720079 | 0.021% |
| 11/9 | 285 | 1720079 | 0.017% |
| 11/10 | 287 | 1720079 | 0.017% |
| 11/11 | 298 | 1720079 | 0.017% |
| 11/12 | 222 | 1720079 | 0.013% |
| 11/13 | 202 | 1720079 | 0.012% |
| 11/14 | 194 | 1720079 | 0.011% |
| 11/15 | 138 | 1720079 | 0.008% |
| 11/16 | 123 | 1720079 | 0.007% |
| 11/17 | 113 | 1720079 | 0.007% |
| 11/18 | 137 | 1720079 | 0.008% |
| 11/19 | 114 | 1720079 | 0.007% |
| 11/20 | 125 | 1720079 | 0.007% |
| 11/21 | 96 | 1720079 | 0.006% |
| 11/22 | 114 | 1720079 | 0.007% |
| 11/23 | 103 | 1720079 | 0.006% |
| 11/24 | 115 | 1720079 | 0.007% |
| 11/25 | 94 | 1720079 | 0.005% |
| 11/26 | 97 | 1720079 | 0.006% |
| 11/27 | 69 | 1720079 | 0.004% |
| 11/28 | 60 | 1720079 | 0.003% |
| 11/29 | 71 | 1720079 | 0.004% |
| 11/30 | 51 | 1720079 | 0.003% |
| 3/1 | 48 | 1720079 | 0.003% |
| 3/2 | 37 | 1720079 | 0.002% |
| 3/3 | 46 | 1720079 | 0.003% |
| 3/4 | 49 | 1720079 | 0.003% |
| 3/5 | 47 | 1720079 | 0.003% |
| 3/6 | 54 | 1720079 | 0.003% |
| 3/7 | 45 | 1720079 | 0.003% |
| 3/8 | 34 | 1720079 | 0.002% |
| 3/9 | 49 | 1720079 | 0.003% |
| 3/10 | 76 | 1720079 | 0.004% |
| 3/11 | 67 | 1720079 | 0.004% |
| 3/12 | 69 | 1720079 | 0.004% |
| 3/13 | 62 | 1720079 | 0.004% |
| 3/14 | 80 | 1720079 | 0.005% |
| 3/15 | 96 | 1720079 | 0.006% |
| 3/16 | 111 | 1720079 | 0.006% |
| 3/17 | 88 | 1720079 | 0.005% |
| 3/18 | 86 | 1720079 | 0.005% |
| 3/19 | 87 | 1720079 | 0.005% |
| 3/20 | 57 | 1720079 | 0.003% |
| 3/21 | 85 | 1720079 | 0.005% |
| 3/22 | 79 | 1720079 | 0.005% |
| 3/23 | 78 | 1720079 | 0.005% |
| 3/24 | 89 | 1720079 | 0.005% |
| 3/25 | 88 | 1720079 | 0.005% |
| 3/26 | 96 | 1720079 | 0.006% |
| 3/27 | 107 | 1720079 | 0.006% |
| 3/28 | 123 | 1720079 | 0.007% |

- Type of impact by species and age class (increased delay, exposure to predation, exposure to a route of higher injury/mortality rate, exposure to higher TDG, etc.).

  - The proposed work that occurs outside the IWW period will be at night; minimal impacts are anticipated. For work during the months of December, January, and February, PH2 will be the priority powerhouse as the Bradford Island fishway will be out of service for winter maintenance this year 2019/20.

Summary statement - expected impacts on:

Downstream migrants

The construction of the new downstream OWS system will occur outside the spring and summer spill season when the majority of out-migrating juvenile passage occurs. Impacts are thought to be minimal.

Upstream migrants (including Bull Trout)

The construction of the new downstream OWS system will occur during nighttime hours outside the IWW period. Minimal upstream passage occurs during the IWW period, months of December through February. Impacts due to changes in unit priority (PH2 unit outages required for tie in to new OWS piping and installation of discharge piping) could have impacts if PH1 units are forced to run out of priority or spill is forced.

Lamprey

All construction activities are occurring outside the majority of lamprey migration. Impacts to lamprey are thought to be minimal.

Comments from agencies

Final coordination results

After Action update (After action statement stating what the effect of the action was on listed species. This statement could simply state that the MOC analysis was correct and the action went as expected, or it could explain how the actual action changed the expected effect (e.g., you didn’t need to close that AWS valve after all, so there was no impact of the action).  List any actual mortality noted as a result of the action)

Please email or call with questions or concerns.

Thank you,

Erin

Erin Kovalchuk

NWP Operations Division Fishery Section

Columbia River Coordination Biologist

Erin.H.Kovalchuk@usace.army.mil

Ben Hausmann, Supervisory Fish Biologist

Chief of Fisheries

U.S. Army Corps of Engineers

Bonneville Lock & Dam

Ben.J.Hausmann@usace.army.mil