## Sheet1
FPOM March-May 2020 Transmission Outages That Have Potential to Limit Generation
ONGOING Continuous Outages 2019- 2020
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
MARCH - 2020 (45 day outage planning process completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
1361490 | BIG EDDY: PCB B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 3/9/20 (6:30) - 6/4/20 (17:00) | Continuous | The Dalles - Units 1, 2 and Fish Units 1, 2 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 1 FOR GSU 1 REPLACEMENT
1345162 | JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING MOD 4156 & PCB 4155 | 2020-03-26 | 8:00-16:00 | John Day - Units 5 - 8 | USACE Work - RECONNECT REMOVED BUS ON LINE SIDE AND PCB SIDE OF MOD 4156
APRIL - 2020 (45 day outage planning process completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
1361490 | BIG EDDY: PCB B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 3/9/20 (6:30) - 6/4/20 (17:00) | Continuous | The Dalles - Units 1, 2 and Fish Units on line 3 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 1 FOR GSU 1 REPLACEMENT
1368016 | THE DALLES PH-BIG EDDY NO 2 115KV LINE | 2020-04-01 | 8:00 - 11:30 | The Dalles - Units 3,4 | USACE Work - BLACK START TESTING MU4 AND L2
1360578 | JOHN DAY PH-JOHN DAY NO 3 500KV LINE INCLUDING PCB 4164 | 2020-04-14 | 8:00-16:00 | John Day - Units 9-12 | REMOVE BUS BETWEEN MOD 4165 AND THE JDPH 3 LINE IN PREPARATION FOR REPLACING MOD 4165
MAY - 2020 (45 day outage planning process NOT completed)
DART ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
1361490 | BIG EDDY: PCB B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 3/9/20 (6:30) - 6/4/20 (17:00) | Continuous | The Dalles - Units 1, 2 and Fish Units on line 3 | USACE Work - UN-GROUNDED TERMINAL CLEARANCE ON THE DALLES POWERHOUSE LINE 1 FOR GSU 1 REPLACEMENT
1352352 | MCNARY: PCB A-420 LINE RELAYS INCLUDING MCNARY PH-MCNARY NO 3&4 230KV LINE | 5/4/2020 (8:30) - 5/5/2020 (14:00) | Continuous | McNary - Units 5-8
1352356 | MCNARY: PCB A-434 LINE RELAYS INCLUDING MCNARY PH-MCNARY NO 5 230KV LINE | 5/6/2020 (8:30) - 5/7/2020 (14:00) | Continuous | McNary - Units 9-12
1354636 | MCNARY: PCB A-408 LINE RELAYS (FORCE OUT: MCNARY PH-MCNARY NO 2 230KV LINE) | 5/11/20 (8:00) - 5/12/20 (15:00) | Continuous | McNary - Units 3 and 4