## FPOM Nov-Dec
FPOM NOV-DEC 2020 Transmission Outages That Have Potential to Limit Generation
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
CASCADE LOCKS-HOOD RIVER SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE | 3/16/20 (8:00) - 11/15/20 (17:00) | Continuous | Bonneville 115kV generation
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING PCB 4137 AND PCB 4140 | 10/26/20 (8:00) - 1/5/21 (16:00) | Continuous | Impacted Generation to Units 1-4 | Surge arrestors and general grid modifications
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING PCB 4137 AND PCB 4140 | 10/5/2020 (8:00) -1/5/2020 (16:00) | Continuous | Units 1 - 4 | MOD replacement, addition of new metering CTs, replace ROD gaps with arrestors, raise line CVTs.
THE DALLES PH-BIG EDDY NO 1 115KV LINE | 10/26/20 (6:30) - 2/28/21 (17:00) | Continuous | Units 1 - 2 | Replacement of T1 generator step-up transformer
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 12/14/20 (8:00) - 12/14/20 (17:30) | 8:00 - 1730 | Units 1 - 4 | Routine relay maintenance.
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 12/15/20 (8:00) - 12/15/20 (17:30) | 8:00 - 1730 | Units 1 - 4 | Routine relay maintenance.
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 12/16/20 (8:00) - 12/16/20 (17:30) | 8:00 - 1730 | Units 1 - 4 | Routine relay maintenance.