## FPOM Aug-Oct
FPOM Transmission Outages That Have Potential to Limit Generation AUG-OCT 2021
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH - Big Eddy #5 230kV | 8/2/21 (06:30 - 07:00) | Daily | The Dalles units 13 - 16 | Relay testing
Lower Granite Powerhouse Line #1 | 8/9/21 - 8/13/21 | Daily (06:00 - 18:00) | Lower Granite units 1 - 6 | Transformer testing at the powerhouse
Bonneville Powerhouse 115kV South Main Bus | 8/9/21 (08:00) - 8/27/21 (12:00) | Continuous | A 40MW minimum generation level at the Bonneville 115kV might be needed if the North Bonneville shunt capacitors are not available. | Disconnect maintenance
ACTON: B-1177 TERMINAL OF THE BONNEVILLE PH-ACTON SECTION OF THE BONNEVILLE PH- HOOD RIVER NO 1 115KV LINE | 8/9/21 (09:00) - 8/28/21 (12:00) | Continuous | A 40MW minimum generation level at the Bonneville 115kV might be needed if the North Bonneville shunt capacitors are not available. | Disconnect maintenance
JOHN DAY PH-JOHN DAY NO 2 500KV LINE | 8/17/21 (09:00) - 9/12/21 (16:00) | Continuous | John Day units 5 - 8 | Re-conductor a portion of the powerhouse line
LOWER GRANITE: 4771/4773 TERMINAL OF THE LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 2021-08-17 | Daily (16:00 - 19:00) | Lower Granite units 1 - 6 | Return powerhouse transformer #2 to service
MCNARY PH-MCNARY NO 5 230KV LINE INCLUDING MCNARY: PCB A-434 | 8/23/21 (07:30) - 10/1/21 (16:00) | Continuous | McNary units 9 - 12 | Install new lightning arrestors and metering CTs
LIBBY: A-1590 TERMINAL OF THE LIBBY PH-LIBBY NO 1 230KV LINE | 8/23/2021 (06:30) - 9/9/2021 (16:30) | Continuous | Libby units 1-2
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
MCNARY PH-MCNARY NO 5 230KV LINE INCLUDING MCNARY: PCB A-434 | 8/23/21 (07:30) - 10/1/21 (16:00) | Continuous | McNary units 9 - 12 | Install new lightning arrestors and metering CTs
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 9/1/21 (08:00) - 11/4/21 (15:00) | Continuous | John Day Units 13-16
CHIEF JOSEPH: A-576 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH NO 1 230KV LINE | 9/13/2021 (05:00) - 9/23/21 (17:30) | Continuous | Chief Joseph Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 9/20/2021 (08:00) - 10/1/21 (16:00) | Continuous | Bonneville Units 5-8
LIBBY: A-1590 TERMINAL OF THE LIBBY PH-LIBBY NO 1 230KV LINE | 8/23/2021 (06:30) - 9/9/2021 (16:30) | Continuous | Libby units 1-2
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
MCNARY PH-MCNARY NO 5 230KV LINE INCLUDING MCNARY: PCB A-434 | 8/23/2021 - 10/1/2021 | Continuous | McNary Units 9-12
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 9/1/2021 - 11/4/2021 | Continuous | John Day Units 13-16
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCB'S 4176 & 4173 | 9/14/2021 - 10/17/2021 | Continuous | John Day Units 13-16
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 9/20/2021 - 10/1/2021 | Continuous | Bonneville Units 5-8
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE INCLUDING CHIEF JOSEPH: PCB'S 4730 AND 4598 | 9/27/2021 - 10/7/2021 | Continuous | Chief Joseph Units 21 - 27
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 9/27/2021 - 10/1/2021 | Continuous | Bonneville Units 5-8
DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 10/4/2021 - 11/12/2021 | Continuous | Dworshak Units 1-3
MCNARY PH-MCNARY 3&4 NO 4 230KV LINE INCLUDING MCNARY: PCB A-420 | 10/4/2021 - 11/9/2021 | Continuous | McNary Units 5-8
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/4/2021 - 10/22/2021 | Continuous | Bonneville Units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/2021 - 12/12/2021 | Continuous | John Day Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 10/25/2021 - 11/5/2021 | Continuous | Bonneville Units 3-4