## FPOM DEC-FEB 22
FPOM DEC 21 -FEB 22 Transmission Outages That Have Potential to Limit Generation
DEC
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/2021 - 12/12/2021 | Continuous | John Day units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 11/8/2021 - 12/8/2021 | Continuous | Bonneville units 3-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/4/2021 - 12/31/2021 | Continuous | Bonneville units 5-8
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/8/2021- 12/23/2021 | Continuous | Bonneville units 11 -14
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/27/2021 - 1/28/2022 | Continuous | Bonneville units 11 -14
MCNARY PH-MCNARY NO 2 230KV LINE INCLUDING MCNARY: PCB A-408 | 11/15/2021 - 12/22/2021 | Continuous | Mcnary units 3-4
BIG EDDY: 230/115KV TRANSFORMER 1 INCLUDING PCBS A-802, B-1060 AND L-1468 | 2021-12-09 | 09:00-15:30 | Potential Impact to the Dalles Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 2021-12-02 | 09:00 - 12:00 | Bonneville units 3-4
CONKELLEY: PCB A-1284 (area restriction) | 2021-12-27 | 07:00-15:00 | Hungry Horse Min 100MW, Hungry Horse + Libby Max 600MW, Libby Max 453 MW
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 2021-12-08 | 07:00-08:00 | Little Goose units 1-6
Ice Harbor - Franklin #2 115kV | 2021-12-01 | 0900 - 1800 | Ice Harbor units 3-4
JAN
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE | 1/31/2022 - 2/11/2022 | Continuous | BONNEVILLE Units 15- 18
LANCASTER-NOXON NO 1 230KV LINE INCLUDING LANCASTER: PCB A-1184, PCB A-1186 | 2022-01-13 | 0800-1400 | Possible Impacts to Western Montana Hydro
FRANKLIN: PCB B-608 INCLUDING ICE HARBOR-FRANKLIN NO 3 115KV LINE | 1/18/22-2/4/22 | Continuous | Ice Harbor Units 5-6
MCNARY PH-MCNARY NO 6 115KV LINE | 1/3/2022-2/18/2022 | Continuous | McNary Units 13-14
MCNARY PH-MCNARY NO 6 115KV LINE | 2022-01-03 | 0700-1600 | McNary Units 13-14
JOHN DAY: 4156/4157 TERMINAL OF JOHN DAY PH-JOHN DAY NO 2 500KV LINE | 1/24/2022 - 1/27/2022 | Continuous | John Day Units 5-8
FEB
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE | 2/14/2022-03/11/2022 | Continuous | Bonneville Units 15-18
CHIEF JOSEPH: 230KV MAIN BUS SECTION 1 INCLUDING PCB A-588, PCB A-584, PCB A-575 | 2022-02-14 | 0600-1700 | Chief Jospeh Units 1-8
FRANKLIN: ICE HARBOR-FRANKLIN NO 1 115KV LINE INCLUDING 115KV AUX BUS AND PCB B-1528 | 2/07/2022-2/25/2021 | Continuous | Ice Harbor Units 1-2
FRANKLIN: PCB B-612 AND ICE HARBOR-FRANKLIN NO 2 115KV LINE AND FRANKLIN 115KV AUX BUS | 2/28/2022-3/11/2022 | Continuous | Ice Harbor Units 0, 3, and 4
JOHN DAY PH-JOHN DAY NO 1 500KV LINE | 2/26/2022-2/28/2022 | Continuous | John Day Units 1-4
MCNARY: 115KV MAIN BUS SECTION 2 INCLUDING PCB B-990 | 2021-02-18 | 0700-1200 | McNary Units 13-14
MCNARY PH-MCNARY NO 6 115KV LINE INCLUDING MCNARY 115KV AUX BUS & PCB B-990 | 2021-02-18 | 1200-1600 | McNary Units 13-14
HUNGRY HORSE PH: PCB 2382, PCB 2182 | 2/28/2022-6/24/2022 | Continuous | Hungry Horse Units 1-2