## FPOM Jan-Mar2021
FPOM Transmission outages that have potential to limit generation Jan-Mar 2021
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
N/A
Jan
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BIG EDDY: B-1692 TERMINAL OF THE DALLES PH-BIG EDDY NO 1 115KV LINE | 10/26/2020 (6:30) - 2/28/2021 (5:00) | Continuous | Units 1 - 2 | Replace Generator Step-Up Transformer T1 at The Dalles
Feb
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 2/16/21 (9:00) - 2/16/20 (17:30) | 9:00 - 1730 | Units 1 - 4 | Routine relay maintenance.
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 2/17/21 (9:00) - 2/17/21 (17:30) | 9:00 - 1730 | Units 1 - 4 | Routine relay maintenance.
BIG EDDY: 115KV MAIN BUS SECTION 1 & 2 BUS DIFFERENTIAL RELAYS (forces out The Dalles Powerhouse Lines #1 and #2) | 2/18/21 (9:00) - 2/18/21 (17:30) | 9:00 - 1730 | Units 1 - 4 | Routine relay maintenance.
THE DALLES: PCB B-1110 (BIG EDDY-THE DALLES 1, HOOD RIVER- THE DALLES 115kV LINES) | 2021-02-25 | 8:00 - 15:00 | The Dalles Units 1 - 4 | Breaker Failure Relay Maintenance and Trip Checks
March
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 1/18/2021(8:00) - 3/26/2021(15:00) | Continuous | Units 5 - 8
LOWER MONUMENTAL-MCNARY NO 1 500KV LINE INCLUDING SACAJAWEA TAP | 3/01/21(7:30)-03/04/2021(15:00) | Continuous | INSULATOR REPLACEMENTS IN THE 28 TO THE 60 MILE
THE DALLES PH-BIG EDDY NO 2 115KV LINE | 3/17/2021 (6:30) - 3/17/2021 (11:30) | Daily | Units 3 - 4
THE DALLES PH-BIG EDDY NO 3 230KV LINE | 3/17/2021 (12:00) - 3/17/2021 (17:00) | Daily | Units 5 - 8
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 3/29/2021 (8:00) - 6/04/2021 (15:00) | Continous | Units 13-16
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 3/29/2021 (8:00) - 6/4/2021 (15:00) | Continuous | Units 5 - 8 | GridMod Upgrades
Placeholders for outages that have moved outside of the time window.
sb submitted 1/20/21