## FPOM JUN-AUG
FPOM Transmission Outages That Have Potential to Limit Generation JUNE-AUGUST 2021
JUNE
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY: PCB 4155, PCB 4158 AND JOHN DAY PH-JOHN DAY NO 2 500KV LINE | 03/15/2021 (11:00) - 06/10/2021 (16:00) | Continuous | Units 5 - 8
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 06/01/2021 (5:00) - 06/01/2021 (5:29) | Daily | Units 5 - 8
JOHN DAY PH-JOHN DAY NO 3 500KV LINE INCLUDING JOHN DAY: PCBS 4164 & 4167 | 06/11/2021 (9:00) - 08/15/2021 (16:00) | Continuous | Units 9 - 12
JULY
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE POWERHOUSE 1 - NORTH CAMAS AND ALCOA LINE, MAIN BUS (NORTH), AND AUX BUS OUTAGE. | 7/12/21 (0700) - 7/30/21 (12:00) | Continuous | A 40MW minimum generation level at the Bonneville 115kV might be needed if the North Bonneville shunt capacitors are not available.
MCNARY PH-MCNARY NO 1 230KV LINE INCLUDING MCNARY: PCB A-404 | 7/12/21 (0700) - 8/20/21 (1600) | Continuous | McNary units 1 & 2 | Replace line relays, install new CTs and surge arrestors
The Dalles PH - Big Eddy #2 115kV | 7/29/21 (16:30 - 17:00) | Daily | The Dalles units 3 -4 | Relay Testing
NORTH BONNEVILLE: PCB A-6 TERMINAL OF THE BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 7/21/21 (07:00) - 8/5/21 (13:00) | Continuous | Bonneville units 5 - 8 | Work at the powerhouse
LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 7/29/21 - 8/13/21 | Daily (05:30 - 16:30) | Lower Monumental units 1 - 6 | Transformer testing
AUGUST
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
The Dalles PH - Big Eddy #5 230kV | 8/2/21 (06:30 - 07:00) | Daily | The Dalles units 13 - 16 | Relay testing
Lower Granite Powerhouse Line #1 | 8/9/21 - 8/13/21 | Daily (06:00 - 18:00) | Lower Granite units 1 - 6 | Transformer testing at the powerhouse
CUT OUT DIFFERENTIAL PORTION OF LCB RELAY ON POWERHOUSE LINE NO. 3, BOTH TERMINALS. TRANSFER TRIP PORTION TO REMAIN IN SERVICE. | June 1st | June 1st | Is it the line that is going out or the breaker?
DETROIT PH-DETROIT NO 2 230KV LINE | 09/13/21(7:00)-09/24/2021(17:00) | Continuous | DETROIT UNITS 1,2 AND BIGCLIFF 3
Bonneville Powerhouse 115kV South Main Bus | 8/9/21 (08:00) - 8/27/21 (12:00) | Continuous | A 40MW minimum generation level at the Bonneville 115kV might be needed if the North Bonneville shunt capacitors are not available. | Disconnect maintenance
ACTON: B-1177 TERMINAL OF THE BONNEVILLE PH-ACTON SECTION OF THE BONNEVILLE PH- HOOD RIVER NO 1 115KV LINE | 8/9/21 (09:00) - 8/28/21 (12:00) | Continuous | A 40MW minimum generation level at the Bonneville 115kV might be needed if the North Bonneville shunt capacitors are not available. | Disconnect maintenance
JOHN DAY PH-JOHN DAY NO 2 500KV LINE | 8/17/21 (09:00) - 9/12/21 (16:00) | Continuous | John Day units 5 - 8 | Re-conductor a portion of the powerhouse line
LOWER GRANITE: 4771/4773 TERMINAL OF THE LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 2021-08-17 | Daily (16:00 - 19:00) | Lower Granite units 1 - 6 | Return powerhouse transformer #2 to service
MCNARY PH-MCNARY NO 5 230KV LINE INCLUDING MCNARY: PCB A-434 | 8/23/21 (07:30) - 10/1/21 (16:00) | Continuous | McNary units 9 - 12 | Install new lightning arrestors and metering CTs