## FPOM MAR-MAY 2021
FPOM March -May 2021 Transmission Outages That Have Potential to Limit Generation
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
N/A
March
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
CHIEF JOSEPH PH-CHIEF JOSEPH NO 4 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-602 | 3/1/2021(7:30) - 3/05/2021(19:00) | Continuous | Units 13- 16
CHIEF JOSEPH PH-CHIEF JOSEPH NO 1 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-576 | 3/08/21(7:30)-03/19/2021(19:00) | Continuous | Units 1-4
THE DALLES PH-BIG EDDY NO 2 115KV LINE | 3/17/2021 (6:30) - 3/17/2021 (11:30) | Daily | Units 3 - 4
THE DALLES PH-BIG EDDY NO 3 230KV LINE | 3/17/2021 (12:00) - 3/17/2021 (17:00) | Daily | Units 5 - 8
CHIEF JOSEPH PH-CHIEF JOSEPH NO 2 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-580 | 3/22/2021 (7:30) - 4/02/2021 (19:00) | Continuous | Units 5 - 8
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 03/15/2021 (8:00) - 06/04/2021 (15:00) | Continuous | Units 5 - 8
April
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
CHIEF JOSEPH PH-CHIEF JOSEPH NO 2 230KV LINE INCLUDING CHIEF JOSEPH: PCB A-580 | 3/22/2021 (7:30) - 4/02/2021 (19:00) | Continuous | Units 5 - 8
CHIEF JOSEPH: A-580 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH NO 2 230KV LINE | 4/12/21(5:00)-4/22/2021(17:30) | Continuous
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 3/15/2021(9:00) - 6/4/2021(15:00) | Continuous | Units 5 - 8
CHIEF JOSEPH PH-CHIEF JOSEPH NO 5 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4588, PCB 4724 | 4/5/2021 (8:30) - 5/21/2021 (18:00) | Continuous | Units 17 - 20 | Black Start Testing
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 03/15/2021 (8:00) - 06/04/2021 (15:00) | Continuous | Units 5 - 8
May
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 2 500KV LINE INCLUDING JOHN DAY: PCBS 4155 & 4158 | 03/15/2021 (8:00) - 06/04/2021 (15:00) | Continuous | Units 5 - 8
CHIEF JOSEPH PH-CHIEF JOSEPH NO 5 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4588, PCB 4724 | 4/5/2021 (7:00) - 5/21/2021 (18:00) | Continuous | Units 17 - 20 | Black Start Testing
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 05/31/2021 (6:30) - 06/31/2021 (7:00) | Daily | Units 5-8