## FPOM
FPOM NOV-JAN Transmission Outages That Have Potential to Limit Generation
2021-11-01
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 9/1/21(8:00 AM) - 11/4/21( 3:00) | Continuous | John Day Units 13-16
DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 10/4/21(7:00:00 AM) - 11/12/21(4:00:00 PM) | Continuous | Dworshak Units 2-3
MCNARY PH-MCNARY 3&4 NO 4 230KV LINE INCLUDING MCNARY: PCB A-420 | 10/4/21(7:30:00 AM) - 11/12/21(4:00:00 PM) | Continuous | McNary Units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/21(8:00:00 AM) - 12/12/21( 4:00:00 PM) | Continuous | John Day Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 10/25/21( 8:00:00 AM) - 11/5/21(12:00:00 PM) | Continuous | Bonneville units 3-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 11/8/21( 8:00:00 AM) - 12/7/21(12:00:00 PM) | Continuous | Bonneville units 3-4
MCNARY PH-MCNARY NO 2 230KV LINE INCLUDING MCNARY: PCB A-408 | 11/15/21(7:30:00 AM) - 12/22/21(4:00:00 PM) | Continuous | Mcnary units 3-4
2021-12-01
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/4/2021 - 12/31/2021 | Continuous | Bonneville units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/2021(8:00:00 AM) - 12/12/2021(4:00:00 PM) | Continuous | John Day units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 11/8/2021( 8:00:00 AM) - 12/7/2021(12:00:00 PM) | Continuous | Bonneville units 3-4
MCNARY PH-MCNARY NO 2 230KV LINE INCLUDING MCNARY: PCB A-408 | 11/15/2021(7:30:00 AM) - 12/22/2021(4:00:00 PM) | Continuous | Mcnary units 3-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 2021-12-02 | 09:00 - 12:00 | Bonneville units 3-4
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/8/21(8:00:00 AM) - 12/23/21(8:00:00 AM) | Continuous | Bonneville units 11 - 14
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/27/21(8:00:00 AM) - 1/28/22(5:00:00 PM) | Continuous | Bonneville units 15 - 18
Ice Harbor LINE #2 115kv | 2021-12-01 | 0900-1800 | Ice Harbor units 3-4
2022-01-01
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/27/21(8:00:00 AM) - 1/28/22(5:00:00 PM) | Continuous | Bonneville units 11-14
MCNARY PH-MCNARY NO 6 115KV LINE INCLUDING MCNARY 115KV AUX BUS & PCB B-990 | 1/3/2022(1:30:00 PM) - 1/3/22(6:00:00 PM) | Continuous | MCNARY Units 11-14
FRANKLIN: ICE HARBOR-FRANKLIN NO 1 115KV LINE INCLUDING 115KV AUX BUS AND PCB B-1528 | 1/31/22 (7:00:00 AM)- 2/18/22(3:30:00 PM) | Continuous | Ice Harbor units 1-2
BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE | 1/31/22(8:00:00 AM) - 2/11/22(5:00:00 PM) | Continuous | BONNEVILLE Units 15- 18
BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE | 1/31/22 (8:00:00 AM)- 2/04/22(5:00:00 PM) | Continuous | BONNEVILLE Units 15- 18