## FPOM OCT-DEC 2021
FPOM Transmission Outages That Have Potential to Limit Generation OCT-DEC 2021
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 9/1/2021 - 11/4/2021 | Continuous | John Day Units 13-16
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCB'S 4176 & 4173 | 9/14/2021 - 10/17/2021 | Continuous | John Day Units 13-16
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 9/20/2021 - 10/1/2021 | Continuous | Bonneville Units 5-8
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE INCLUDING CHIEF JOSEPH: PCB'S 4730 AND 4598 | 9/27/2021 - 10/7/2021 | Continuous | Chief Joseph Units 21 - 27
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 9/27/2021 - 10/1/2021 | Continuous | Bonneville Units 5-8
DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 10/4/2021 - 11/12/2021 | Continuous | Dworshak Units 2-3
MCNARY PH-MCNARY 3&4 NO 4 230KV LINE INCLUDING MCNARY: PCB A-420 | 10/4/2021 - 11/9/2021 | Continuous | McNary Units 5-8
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/4/2021 - 10/22/2021 | Continuous | Bonneville Units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/2021 - 12/12/2021 | Continuous | John Day Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 10/25/2021 - 11/5/2021 | Continuous | Bonneville Units 3-4
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
JOHN DAY PH-JOHN DAY NO 4 500KV LINE INCLUDING JOHN DAY: PCBS 4176 & 4173 | 9/1/21 - 11/4/21 | Continuous | John Day Units 13-16
DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 10/4/21 - 11/12/21 | Continuous | Dworshak Units 2-3
MCNARY PH-MCNARY 3&4 NO 4 230KV LINE INCLUDING MCNARY: PCB A-420 | 10/4/21 - 11/12/21 | Continuous | McNary Units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/21 - 12/12/21 | Continuous | John Day Units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 10/25/21 - 11/5/21 | Continuous | Bonneville units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 11/8/21 - 12/7/21 | Continuous | Bonneville units 1-4
MCNARY PH-MCNARY NO 2 230KV LINE INCLUDING MCNARY: PCB A-408 | 11/15/21 - 12/22/21 | Continuous | Mcnary units 3-4
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/4/2021 - 12/31/2021 | Continuous | Bonneville units 5-8
JOHN DAY PH-JOHN DAY NO 1 500KV LINE INCLUDING JOHN DAY PCB 4137 | 10/19/2021 - 12/12/2021 | Continuous | John Day units 1-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 11/8/2021 - 12/7/2021 | Continuous | Bonneville units 1-4
MCNARY PH-MCNARY NO 2 230KV LINE INCLUDING MCNARY: PCB A-408 | 11/15/2021 - 12/22/2021 | Continuous | Mcnary units 3-4
BONNEVILLE PH 1-NORTH BONNEVILLE NO 1 230KV LINE | 2021-12-02 | 09:00 - 12:00 | Bonneville units 1-4
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/8/21 - 12/23/21 | Continuous | Bonneville units 15 - 18
BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 12/27/21 - 1/28/22 | Continuous | Bonneville units 15 - 18
created 10/13/2021sb