## FPOM April-June 2022
FPOM outages April-June 2022 Transmission outages that have potential to limit generation
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
HUNGRY HORSE PH: PCB 2382, PCB 2182 | 2/28/22-6/24/2022 | Continuous | Hungry Horse Units 1-2
FRANKLIN: 115KV EAST MAIN BUS INCLUDING PCB B-615, PCB B-618, PCB B-620, PCB B-622, PCB B-1524, PCB B-1526, PCB B-1528, PCB B-1541 AND PCB B-2112. | 4/4/22-4/18/22 | Continous | Ice Harbor Units 1-2
FRANKLIN: PCB B-608 INCLUDING ICE HARBOR-FRANKLIN NO 3 115KV LINE | 4/18/22-5/6/22 | Continous | Ice Harbor Units 5-6
MCNARY PH-MCNARY 3&4 NO 3 230KV LINE | 4/11/22-4/14/22 | Continous | Mcnary Units 5-8
MCNARY: PCB A-420 OF THE MCNARY PH-MCNARY NO 3&4 230KV LINE | 2022-04-14 | 1630-1700 | Mcnary Units 5-8
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 2022-04-19 | 0600-1800 | Lower Granite Units 1-6 | Unit 5 & 6 will be the only units available between the 19th and 22 nd
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 2022-04-22 | 1500-1800 | Lower Granite Units 1-6
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE INCLUDING CORPS OF ENGINEERS 500/13.8KV TRANSFORMER T1 | 4/18/22-4/22/22 | Continous | Little Goose Units 1-6 | May need to be extended if wind picks up. Unit 5&6 will be O/S until jumpers are removed later in the year.
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 2022-05-30 | 0700-0730 | The Dalles Units 5-8
Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
MCNARY: PCB A-420 OF MCNARY PH-MCNARY NO 3&4 230KV LINE | 2022-06-27 | 0630-0700 | Mcnary Units 5-8
MCC - BONNEVILLE PH 2-NORTH BONNEVILLE NO 3 230KV LINE | 6/27/22-7/15/22 | Continous | Bonneville Units 11-14 | emergency repair of the disconnect switches
BIG EDDY: PCB A-842 OF THE DALLES PH-BIG EDDY NO 6 230KV , THE DALLES PH-BIG EDDY NO 6 230KV LINE | 2022-06-13 | 0630-0700 | The Dalles Units 17-22
updated 4/13/2022 sb