## FPOM Aug-Oct
FPOM Aug-Oct Transmission Outages That Have Potential to Limit Generation
August - 2022 (60 day outage planning process completed)
ITOA ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
22-02600 | -USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | 7/25/2022- 10/28/2022 | 0630-1500 | Hungary Horse Unit 3-4
22-02186 | LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 8/22/22-9/22/22 | Continous | Libby Units 1-2
22-04702 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 2022-08-22 | 0700-0900 | Lower Monumental Units 1-6
22-08685 | NORTH BONNEVILLE: A-11 TERMINAL OF THE BONNEVILLE PH-NORTH BONNEVILLE NO 4 230KV LINE | 8/29/22-9/15/22 | Continous | Bonneville Units 15-18
22-01866 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | 2022-08-10 | 0600-1800 | Lower Granite Units 1-6 | Doble test
22-01867 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | 2022-08-11 | 0600-1800 | Lower Granite Units 1-6 | Doble test
22-01868 | LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE (UNGROUNDED) | 2022-08-12 | 0600-1800 | Lower Granite Units 1-6 | Doble test
22-04985 | BONNEVILLE PH 2-NORTH BONNEVILLE 3 230KV LINE RELAYS | 7/25/2022 - 8/11/2022 | 0800-1700 | Bonneville Units 11-14
22-11650 | LITTLE GOOSE: 4349/4351 TERMINAL OF , LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 08/10/2022 - 08/11/2022 | 1700-0900 | Little Goose Units 1-6 | Roof replacement
22-11651 | LITTLE GOOSE: 4349/4351 TERMINAL OF , LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 08/11/2022 - 08/12/2022 | 1700-0900 | Little Goose Units 1-6 | Roof replacement
22-11652 | LITTLE GOOSE: 4349/4351 TERMINAL OF , LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 08/12/2022 - 08/13/2022 | 1700-0900 | Little Goose Units 1-6 | Roof replacement
22-11653 | LITTLE GOOSE: 4349/4351 TERMINAL OF , LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 08/13/2022 - 08/14/2022 | 1700-0900 | Little Goose Units 1-6 | Roof replacement
22-11556 | BIG EDDY: PCB A-836 OF THE DALLES PH-BIG EDDY NO 5 230KV LINE | 2022-08-15 | 0630-0700 | The Dalles 13-16
22-11558 | BIG EDDY: PCB A-836 OF THE THE DALLES PH-BIG EDDY NO 5 230KV LINE | 2022-08-25 | 1200-1230 | The Dalles 13-16
September - 2022 (60 day outage planning process completed)
ITOA ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
22-02194 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 2022-09-19 | 0700-0900 | Lower Monumental Units 1-6
22-02437 | DWORSHAK: 4657/4658 TERMINAL OF DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 9/21/22 - 9/29/22 | Continous | Dworshak Units 2-3 | Doble test
22-08665 | NORTH BONNEVILLE: PCB A-6 OF THE BONNEVILLE PH-NORTH BONNEVILLE #2 230KV LINE | 2022-09-01 | 0900-1300 | Bonneville Units 5-8
22-02408 | JOHN DAY: 4174/4175 TERMINAL OF JOHN DAY PH-JOHN DAY NO 4 500KV LINE | 9/5/22 - 9/15/22 | Continous | John Day Units 13-16
22-10552 | Columbia Falls - Flathead #1 230kV Line Including Flathead: PCB A-221 and 230kV Aux Bus | 2022-09-08 | 0630-1500 | Libby Max Gen 300MW, Hungry Horse Max Gen 100MW
22-01210 | CHIEF JOSEPH: 4731/4734 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE | 9/6/22 - 9/22/22 | Continous | Chief Joseph Units 21-27
Octuber 2022 (60 outage planning process not completed)
ITOA ID | Equipment Outage | Date(s) | Hours | Impacted Generation | Notes
22-04703 | LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 2022-10-14 | 1500-1700 | Lower Monumental Units 1-6
22-08018 | LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOMO PCB 4316 | 10/31/2022 - 11/04/2022 | Continous | Lower Monumental Units 1-6 | Grid Mod
sb/8/10/22