## Slide 1: Detailed Schedule
Tasks | Timing
Letter to Cooperators | Completed
Research and add pelicans to EA | This ongoing in the process of EA development
Revise gull analysis in EA | This ongoing in the process of EA development
Revise EA for direct, indirect etc.. | Completed
Begin Cooperating Agency Meetings | Begin 26 September 2022 – ongoing weekly
Cooperating Agency Review and Input | Completed
Complete draft EA | Complete by 16 December 2022
Review of EA | 16 December 2022 to 13 January 2023
Revise and advertise EA to Public | 20 January 2023 for 30 days
Address Comments and Final EA | 20 February to 15 March 2023
Apply for Depredation Permit | 16 March 2023
Complete and sign FONSI | 1 April 2023
Implementation | 15 April 2023
We are here