## FPOM Nov-Jan
FPOM outages that have potential to limit generation Oct22-Jan23
November
Equipment Outage | Start | End | Impacted Generation | Notes
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING PCBs 4348 & 4350 | 11/07/2022 09:00 | 11/11/2022 15:00 | Little Goose 1-6
BIG EDDY: 115KV MAIN BUS SECTIONS 1 AND 2 | 11/08/2022 07:00 | 11/10/2022 18:00 | The Dalles 1-4
LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE 1 500KV LINE | 11/29/2022 06:00 | 12/23/2022 18:00 | Lower Granite 1-6 | Gasket replacement T1C, Units 5&6 available during non work hours
BIG EDDY: PCB B-1692 RELAYS | 11/08/2022 08:00 | 11/09/2022 15:00 | The Dalles 1-2
BIG EDDY: PCB B-1050 RELAYS | 11/09/2022 08:00 | 11/09/2022 15:00 | The Dalles 3-4
MCNARY: 230KV MAIN BUS SECTION 2 | 11/09/2022 07:00 | 11/09/2022 15:00 | McNary 5-8
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE, INCLUDING LOWER GRANITE PCB'S 4770 & 4772 | 11/14/2022 08:00 | 11/18/2022 16:00 | Lower Granite 1-6
BIG EDDY: PCB A-824 RELAYS | 11/15/2022 08:00 | 11/15/2022 15:30 | The Dalles Units 9-12
BIG EDDY: PCB A-836 RELAYS | 11/16/2022 08:00 | 11/16/2022 15:30 | The Dalles Units 13-16
BIG EDDY: PCB A-812 RELAYS | 11/14/2022 08:00 | 11/14/2022 15:30 | The Dalles Units 5-8
BIG EDDY: PCB A-842 RELAYS | 11/17/2022 08:00 | 11/17/2022 15:30 | The Dalles Units 17-22
CHIEF JOSEPH-SNOHOMISH NO 3 345KV LINE, (UNGROUNDED) | 11/14/2022 07:00 | 11/15/2022 15:00 | Chief Joseph 230kV Units Combined Generation Limited to 950MW | Gen Con Required per DSO 340 when overlapping with Chief-Joseph-Snohomish No 4 line ITOA - 22-16641
CHIEF JOSEPH PH-CHIEF JOSEPH NO 5 500KV LINE, INCLUDING CHIEF JOSEPH: PCB 4588, PCB 4724 | 11/29/2022 10:00 | 11/29/2022 13:00 | Chief Joseph 17-20
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 11/21/2022 11:30 | 11/21/2022 17:00 | The Dalles 5-8
December
Equipment Outage | Start | End | Impacted Generation | Notes
THE DALLES PH-BIG EDDY NO 6 230KV LINE | 12/12/2022 06:30 | 12/12/2022 07:00 | The Dalles 17-22
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE, INCLUDING CHIEF JOSEPH: PCB 4598, PCB 4730 | 12/01/2022 10:00 | 12/01/2022 13:00 | Chief Joseph 21-27
JOHN DAY: 4138/4139 TERMINAL OF JOHN DAY PH-JOHN DAY NO 1 500KV LINE | 12/05/2022 07:00 | 12/22/2022 17:00 | John Day 1-4
THE DALLES PH: 230/13.2KV BANK 11 | 12/12/2022 06:30 | 12/28/2023 17:00 | The Dalles 21-22
January
Equipment Outage | Start | End | Impacted Generation | Notes
LITTLE GOOSE: 4349/4351 TERMINAL OF, LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 01/21/2023 08:00 | 01/28/2023 17:00 | Little Goose 1-6 | Jumper removal, Units 5 & 6 will once again be accessible.
LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOWER MONUMENTAL PCB 4316 AND 500KV WEST BUS | 01/03/2023 08:30 | 01/07/2023 15:00 | Lower Monumental 1-6
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE, INCLUDING LOWER GRANITE PCB'S 4770 & 4772 | 01/09/2023 08:00 | 01/20/2023 16:00 | Lower Granite 1-6
THE DALLES PH-BIG EDDY NO 6 230KV LINE | 01/17/2023 06:30 | 01/17/2023 07:00 | Big Eddy 17-22
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING LITTLE GOOSE PCBs 4348 & 4350 | 01/21/2023 09:00 | 01/28/2023 15:00 | Little Goose 1-6 | Grid Mod
LOWER MONUMENTAL 500KV WEST BUS INCLUDING LOWER MONUMENTAL PH #1 500KV LINE STUB BUS AND MOD 4343 | 01/30/2023 08:30 | 02/03/2023 15:00 | Lower Monumental 1-6 | Grid Mod