Fish Passage Operation and Maintenance (FPOM) Team DRAFT meeting Agenda

13 October 2022, 09:00-2:00

Meeting will be held via WebEx and Call-in

Conference line: 1-844-800-2712 	Access: 199 076 9084

WebEx meeting:

https://usace1.webex.com/usace1/j.php?MTID=mfd2225aec54960151ed1beffdc99906a

Access Code: 199 076 9084	Password: fy21FPOM**

Documents may be found at: http://pweb.crohms.org/tmt/documents/FPOM/2010/

- Approval of August Minutes: (Mackey)

- Action Items

  - NWW

    - [July 22] LWG adult CH fallback (Bellerud/Swieca) ACTION: Bellerud will provide an update.

  - NWP

    - [June 22] NWP/NWW Critical Fish Passage O&M needs. ACTION: (Mackey/Cordie) will provide an update.

  - Completed Action Items or to be discussed later in the agenda

    - [September 22] 22BON089 MOC Spillway B-Branch erosion and attraction follow outage. 22BON089 MOC and 22BON094 MFR. STATUS: ROV inspection completed 26 September and follow on Hydroservey completed 30 September. Derugin will update.

    - [July 22] Lethal Removal – STATUS: Schmidt has provided an update for the avian task group; A review is planned for 30 January 2023.

    - 21 LWG 08 MOC Trash Rake Crane Replacement (May 2022). STATUS: Postponed.

    - 22 IHR 07 MOC Fish Release Pipe Install Outage and Unit 3 Turbine. STATUS: Postponed.

- Updates

  - NWW Updates

    - Upcoming maintenance/construction/research activities (previously coordinated MOC/MFRs).

      - 22 LWG 08 MOC BPA Outage 500 kV line - scheduled 14–18 November,

      - 22 LWG 04 MOC T1T2 Gasket Repair - T1A scheduled for 28 November,

      - 22 LGS 08 MOC BPA Outage 500 kV line - scheduled 7–11 November,

      - 20 LGS 16 MOC Powerhouse Roof Repair – outage in December to reconnect bus link is moved to January to accommodate another BPA outage,

      - 22 LMN 06 MOC BPA Outage 500 kV line – scheduled Oct 31–4 Nov,

      - 22 LMN 09 MOC T-2 Rehabilitation – Extended to 12 December, units 5 and 6 are out,

      - 22LGS10 MOC WECC NERC testing – Completed Sept 6,

      - McNary crane status - Bay 6 update -

  - NWP Updates

    - Upcoming maintenance/construction/research activities (previously coordinated MOC/MFRs).

      - 21BON001 MOC Navigation Lock 1 (old navlock) Bridge Replacement scheduled for CY 2023. (Trachtenbarg) update -

      - 22BON089 MOC and 22BON094 MFR Spillway B-Branch Erosion and Attraction Follow outage, (Derugin), Update -

      - 19TDA04 MOC – East side powerhouse, Update -

      - 18JDA02 MOC Trash rack replacement – Is fabrication completed? Update -

      - 20JDA04 MOC STS crane replacement, has design phase been completed? Update -

      - 22JDA07 MOC Block Study - concluded 17 August, Results being reviewed, Update-

    - BON ITS end gate.

    - BON ITS PIT tag detector.

    - TDA AWS debris management, (McDonald) Update -

    - TDA trunnion pin/ spillbay 10. Update -

    - TDA N Ladder Rockfall P#449517 - $60k submitted for FY25 budget. Two options for dewatering: 1. shorten the East dewater to add more to North or 2. Overlap the dewatering’s, would require FPOM approval. Update -

    - JDA north pump #4. - OOS for the entire year, Funding needed for O&M next summer, Update -

    - JDA spill bay 10, Still in manual operation, Update -

    - JDA SFL Temperatures, Collected till the end of September, Update -

  - NWS updates.

  - Research/FFDRWG.

    - NWP FFDRWG.

    - NWW FFDRWG.

    - SRWG.

    - 2022 Research and Access requests:

  - RCC update.

Table 1. NOAA Northwest River Forecast Center inflow forecast.

| Project | Previous Day () Average Outflow (kcfs) | 5 Day () Forecasted Inflow (kcfs) | 10 Day () Forecasted Inflow (kcfs) | Forecasted Inflow Low/High (kcfs) |
| --- | --- | --- | --- | --- |
| LWG |  |  |  |  |
| MCN |  |  |  |  |
| BON |  |  |  |  |

    - Fall spill operations.

  - Fish Count Program update (Peery, Wertheimer).

  - Pinniped update

    - Bonneville Dam -

    - Willamette Falls -

  - Lamprey update

    - BON LPS -

    - TDA -

    - JDA -

    - NWW -

    - Lamprey Accords Work Group (Macdonald) -

  - BPA update. -

  - NWP/NWW Critical Fish Passage O&M needs. -

  - Avian updates (10:30)

    - NWW -

    - JDA -

    - TDA –

    - BON -

    - Estuary -

    - NEPA -

- Coordination/Notification forms (need concurrence/discussion)

  - NWW

    - 22LWG11 MFR Change in Exit Temp Pump Operations -

  - NWP

    - 22BON088 MFR AFF Valve 15 four Chinook mort’s -

    - 22BON089 MOC Spillway B-Branch attraction flow -

    - 22BON090 MFR AFF Valve 15 Salmonid mort -

    - 22BON091 MFR AFF Picket Leads left down -

    - 22BON092 MFR WA Shore Serpentine Chinook mort -

    - 22BON093 MFR AFF Brail Pond salmonid mort -

    - 22BON094 MFR AFF Valve 15 Salmonid mort -

    - 22JDA12 MFR Spillbays 1-4 OOS for routine inspection -

    - 22JDA13 MFR STS camera train lubricant leak –

    - 22JDA14 MOC Spillbay 2 outage for bridge inspection –

    - 22JDA15 MFR Crane oil leak -

    - 22TDA13 MFR Spearfish Park salmonid mort’s –

    - 22TDA14 MOC The Dalles Hydro-survey and Bonneville forebay Ops -

- Fish Passage Plan

  - The 2022 FPP went into effect March 1 and is available online at: pweb.crohms.org/tmt/documents/fpp/2022/

    - PENDING Change Forms:

    - NEW Change Forms:

- Task Group Updates.

  - Task Group Kelt Trigger (Wertheimer and Lorz). Documents / FPOM / 2013 / FPOM Task Groups (crohms.org)

  - Task Group Hazing NEPA (CRC and Schmidt). Documents / FPOM Avian Task Group (crohms.org).

  - Avian Task Force (ATF). (Cordie). Documents / FPOM Avian Task Group (crohms.org)