## FPOM
FPOM Oct-Dec Transmission Outages That Have Potential to Limit Generation
Equipment Outage | Start | End | Impacted Generation | Notes
-USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | 07/25/2022 06:30 | 10/28/2022 15:00 | Hungary Horse 3-4
CHIEF JOSEPH PH-CHIEF JOSEPH NO 5 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4588, PCB 4724 | 10/18/2022 12:00 | 10/18/2022 15:00 | Chief Joseph 17-20
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE INCLUDING CHIEF JOSEPH: PCB 4598, PCB 4730 | 10/20/2022 12:00 | 10/20/2022 15:00 | Chief Joseph 21-27
ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE FRANKLIN COUNTY PUD FB103 DISCONNECT | 10/28/2022 08:00 | 11/04/2022 15:00 | Ice Harbor 3-4
LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOMO PCB 4316 | 10/31/2022 08:30 | 11/04/2022 15:30 | Lower Monumental Units 1-6
NORTH BONNEVILLE: PCB A-6 OF THE, BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/27/2022 08:00 | 10/27/2022 13:00 | Bonneville units 5-8
Equipment Outage | Start | End | Impacted Generation | Notes
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING PCBs 4348 & 4350 | 11/07/2022 09:00 | 11/11/2022 15:00 | Little Goose 1-6
CHIEF JOSEPH PH-CHIEF JOSEPH NO 1 230KV LINE, INCLUDING CHIEF JOSEPH: PCB A-576, PCB A-584 | 11/01/2022 12:00 | 11/01/2022 15:00 | Chief Joseph 1-4
CHIEF JOSEPH PH-CHIEF JOSEPH NO 2 230KV LINE, INCLUDING CHIEF JOSEPH: PCB A-580, PCB A-584 | 11/03/2022 12:00 | 11/03/2022 15:00 | Chief Joseph 5-8
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 11/07/2022 06:30 | 11/07/2022 07:00 | The Dalles 5-8
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 11/17/2022 16:30 | 11/17/2022 17:00 | The Dalles 5-8
BIG EDDY: 115KV MAIN BUS SECTIONS 1 AND 2 | 11/08/2022 07:00 | 11/10/2022 18:00 | The Dalles 1-4
LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE 1 500KV LINE | 11/28/2022 06:00 | 12/23/2022 18:00 | Lower Granite 1-6
BIG EDDY: PCB B-1692 RELAYS | 11/08/2022 10:00 | 11/08/2022 15:00 | The Dalles 1-2
BIG EDDY: PCB B-1050 RELAYS | 11/09/2022 08:00 | 11/09/2022 15:00 | The Dalles 3-4
BIG EDDY: PCB A-836 OF, THE DALLES PH-BIG EDDY NO 5 230KV LINE | 11/16/2022 16:00 | 11/16/2022 16:30 | The Dalles 13-16
BIG EDDY: PCB A-824 OF, THE DALLES PH-BIG EDDY NO 4 230KV LINE | 11/17/2022 06:30 | 11/17/2022 07:00 | The Dalles 9-12
BIG EDDY: PCB A-824 OF, THE DALLES PH-BIG EDDY NO 4 230KV LINE | 11/21/2022 16:00 | 11/21/2022 16:30 | The Dalles 9-12
LOWER GRANITE: PCB 4770, INCLUDING MOD 4771 | 11/18/2022 16:00 | 01/09/2023 08:00 | Lower Granite 1-6
MCNARY: 230KV MAIN BUS SECTION 2 | 11/09/2022 07:00 | 11/09/2022 15:00 | McNary 5-8
FRANKLIN: 115KV WEST MAIN BUS | 11/10/2022 08:00 | 11/10/2022 15:00 | Ice Harbor 3-4
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE, INCLUDING LOWER GRANITE PCB'S 4770 & 4772 | 11/14/2022 08:00 | 11/18/2022 16:00 | Lower Granite 1-6
LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 11/18/2022 15:00 | 11/18/2022 17:00 | Lower Monumental 1-6
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 11/21/2022 11:30 | 11/21/2022 17:00 | The Dalles 5-8
Equipment Outage | Start | End | Impacted Generation | Notes
LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 12/05/2022 07:00 | 12/05/2022 17:00 | Lower Monumental 1-6
THE DALLES PH-BIG EDDY NO 6 230KV LINE | 12/12/2022 06:30 | 12/12/2022 07:00 | The Dalles 17-22
JOHN DAY: 4138/4139 TERMINAL OF JOHN DAY PH-JOHN DAY NO 1 500KV LINE | 12/12/2022 07:00 | 12/22/2022 17:00 | John Day 1-4
LITTLE GOOSE: 4349/4351 TERMINAL OF, LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 12/12/2022 08:00 | 12/16/2022 17:00 | Little Goose 1-6 | This may move to January