## FPOM Sept-Nov
FPOM Sep-Nov Transmission Outages That Have Potential to Limit Generation
September
Equipment Outage | Start | End | Impacted Generation | Notes
-USBR- HUNGRY HORSE PH: PCB 2382, PCB 2282 | 07/25/2022 06:30 | 10/28/2022 15:00 | Hungary Horse 3-4
LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 08/22/2022 04:30 | 09/22/2022 15:00 | Libby 1-2
NORTH BONNEVILLE: A-11 TERMINAL OF THE BONNEVILLE PH-NORTH BONNEVILLE NO 4 230KV LINE | 08/29/2022 08:00 | 09/15/2022 16:00 | Bonneville 15-18
DWORSHAK: 4657/4658 TERMINAL OF DWORSHAK PH-DWORSHAK NO 1 500KV LINE | 09/21/2022 06:30 | 09/29/2022 17:00 | Dworshak 2-3 | Doble testing
JOHN DAY: 4174/4175 TERMINAL OF JOHN DAY PH-JOHN DAY NO 4 500KV LINE | 09/06/2022 07:00 | 09/22/2022 17:00 | John Day 13-16
CHIEF JOSEPH: 4731/4734 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE | 09/06/2022 03:00 | 09/30/2022 17:30 | Chief Joseph 21-27
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE, INCLUDING PCB'S 4598 & 4730 | 09/06/2022 03:00 | 09/30/2022 17:30 | Chief Joseph 21-27
MCNARY: PCB A-420 OF THE MCNARY PH-MCNARY NO 3&4 230KV LINE | 09/15/2022 16:30 | 09/15/2022 17:00 | McNary 5-8
MCNARY: PCB A-434 OF THE PH-MCNARY NO 5 230KV LINE | 09/12/2022 06:30 | 09/12/2022 07:00 | McNary 9-12
MCNARY: PCB A-434 OF THE PH-MCNARY NO 5 230KV LINE | 09/22/2022 16:30 | 09/22/2022 17:00 | McNary 9-12
October
Equipment Outage | Start | End | Impacted Generation | Notes
ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE FRANKLIN COUNTY PUD FB103 DISCONNECT | 10/28/2022 08:00 | 11/04/2022 15:00 | Ice Harbor 3-4
LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE INCLUDING: LOMO PCB 4316 | 10/31/2022 08:30 | 11/04/2022 15:30 | Lower Monumental Units 1-6
NORTH BONNEVILLE: PCB A-6 OF THE, BONNEVILLE PH 1-NORTH BONNEVILLE NO 2 230KV LINE | 10/27/2022 08:00 | 10/27/2022 13:00 | Bonneville units 5-8
THE DALLES PH-BIG EDDY NO 6 230KV LINE | 10/31/2022 06:30 | 10/31/2022 07:00 | The Dalles 17-22
November
Equipment Outage | Start | End | Impacted Generation | Notes
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING PCBs 4348 & 4350 | 11/07/2022 09:00 | 11/11/2022 15:00 | Little Goose 1-6
MCNARY: 230KV MAIN BUS SECTION 2 | 11/09/2022 07:00 | 11/09/2022 15:00 | McNary 5-8
FRANKLIN: 115KV WEST MAIN BUS | 11/10/2022 08:00 | 11/10/2022 15:00 | Ice Harbor 3-4
LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE, INCLUDING LOWER GRANITE PCB'S 4770 & 4772 | 11/14/2022 08:00 | 11/18/2022 16:00 | Lower Granite 1-6
BIG EDDY: PCB A-836 OF, THE DALLES PH-BIG EDDY NO 5 230KV LINE | 11/14/2022 16:30 | 11/14/2022 17:00 | The Dalles 13-16
LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 11/18/2022 15:00 | 11/18/2022 17:00 | Lower Monumental 1-6
BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | 11/21/2022 11:30 | 11/21/2022 17:00 | The Dalles 5-8
LITTLE GOOSE: 4349/4351 TERMINAL OF LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 11/28/2022 05:00 | 12/02/2022 17:00 | Little Goose 1-6
sb 9/8/22