## FPOM April - June
FPOM April-June Transmission Outages That Have Potential to Limit Generation
April 2023
Equipment Outage | Start | End | Impacted Generation | Notes
-USBR- HUNGRY HORSE: PCB'S 2182 AND 2382 | 03/13/2023 06:00 | 2023-04-27 16:00 | Hungry Horse 1-2
BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | 04/17/2023 06:30 | 04/17/2023 07:00 | The Dalles 3-4
BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | 04/27/2023 12:00 | 04/27/2023 12:30 | The Dalles 3-4
LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | 04/24/2023 21:00 | 04/25/2023 01:30 | Hungry Horse 100 MW Min, Libby 453 MW Max
LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE INCLUDING THE A-274 LINE SECTIONALIZING DISCONNECT | 04/25/2023 01:30 | 04/27/2023 21:00 | Hungry Horse 100 MW Min, Libby 453 MW Max
LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | 04/27/2023 21:00 | 04/28/2023 01:30 | Hungry Horse 100 MW Min, Libby 453 MW Max
CHIEF JOSEPH: A-602 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 4 230KV LINE | 04/03/2023 05:00 | 04/21/2023 17:00 | Chief Joseph 13-16
ICE HARBOR-FRANKLIN NO 2 115KV LINE INCLUDING THE SACAJAWEA TAP | 04/14/2023 08:00 | 04/14/2023 15:00 | Ice Harbor 1-2
ICE HARBOR-FRANKLIN NO 1 115KV LINE | 04/14/2023 08:00 | 04/14/2023 15:00 | Ice Harbor 3-4 | Replace aircraft warning marker balls.
CHIEF JOSEPH PH-CHIEF JOSEPH 1 230KV LINE | 04/25/2023 03:00 | 04/26/2023 17:00 | Chief Joseph 1-4
May 2023
Equipment Outage | Start | End | Impacted Generation | Notes
BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 05/08/2023 06:30 | 05/08/2023 07:00 | The Dalles 9-12
-COE- DWORSHAK: 115/13.8KV BANK TW1 | 05/15/2023 07:00 | 05/18/2023 17:00 | Dworshak 1
BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 05/18/2023 12:00 | 05/18/2023 12:30 | The Dalles 9-12
MCNARY PH-MCNARY NO 3&4 230KV LINE | 05/22/2023 06:30 | 05/22/2023 07:00 | McNary 5-8
THE DALLES PH-BIG EDDY NO 5 230KV LINE | 05/22/2023 06:30 | 05/22/2023 07:00 | The Dalles 13-16
2023-06-01
Equipment Outage | Start | End | Impacted Generation | Notes
THE DALLES PH-BIG EDDY NO 5 230KV LINE | 06/01/2023 12:00 | 06/01/2023 12:30 | The Dalles 13-16
HUNGRY HORSE-COLUMBIA FALLS NO 1 230KV LINE | 06/20/2023 07:00 | 06/29/2023 16:00 | Libby + Hungry Horse Total Gen 600 MW Max
HUNGRY HORSE-COLUMBIA FALLS NO 1 230KV LINE | 06/26/2023 06:00 | 06/30/2023 15:00 | Libby + Hungry Horse Total Gen 600 MW Max
MCNARY PH-MCNARY NO 3&4 230KV LINE | 06/30/2023 16:30 | 06/30/2023 17:00 | McNary 13-16
sb 4/12/23