## Slide 1: Detailed Schedule
Tasks | Timing
Letter to Cooperators | Completed
Research and add pelicans to EA | Completed
Revise gull analysis in EA | Completed
Revise EA to comply with new NEPA Regs | Completed
Cooperating Agency Meetings (USFWS & APHIS) | Started September 2022 – ongoing as needed
Cooperating Agency Input | Ongoing as needed
Complete draft of draft EA | Completed
Cooperating Agency Review of draft EA | Completed
Incorporate Comments to draft EA | Completed
Revise draft EA to a Public version | Completed
District Quality Control Review | Completed
Release draft EA to Public for 30 days | March 31, 2023 – April 30, 2023
Complete Final EA and sign FONSI | May 20, 2023
Apply for Depredation Permit | May 20, 2023
Juvenile Fish Outmigration | 15 April 2023 to 31 July 2023
APHIS Hazing Implementation | 15 April 2023 to 31 July 2023 (already permitted)
APHIS Implementation of Lethal Reinforcement | Pending APHIS FONSI with 30 day Public Notification and USFWS FONSI and issuance of Depredation Permit
We are here
Notes: Red indicates change in schedule from that planned. APHIS was able to hire additional staff for implementation but will have to develop safety plan with staff and Projects.