## FPOM Aug-Oct
FPOM August-October Transmission Outages That Have Potential to Limit Generation
August - 2023 (60 day outage planning process not completed)
ITOA ID | Equipment Outage | Start | End | Impacted Generation | Notes
23-01163 | CHIEF JOSEPH: 500/230KV TRANSFORMER 3, INCLUDING PCB A-604 | 08/07/2023 08:00 | 2023-09-10 17:00 | CHIEF JOSEPH 230kV UNITS 900 MW
23-04354 | LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 08/14/2023 04:30 | 2023-08-31 15:00 | Libby 3-5
CHIEF JOSEPH 230kV UNITS 950 MW
September - 2023 (60 day outage planning process not completed)
ITOA ID | Equipment Outage | Start | End | Impacted Generation | Notes
23-00264 | JOHN DAY: 4165/4166 TERMINAL OF JOHN DAY PH-JOHN DAY 3 500KV LINE | 2023-08-21 07:00 | 2023-09-14 17:00 | John Day 9-12
23-01365 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | 09/14/2023 12:00 | 09/14/2023 12:30 | UNITS 5,8
23-01363 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | 09/04/2023 06:30 | 09/04/2023 07:00 | UNITS 5,8
23-03174 | HASKILL-TRUMBULL CREEK SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | 2023-09-18 04:15 | 2023-10-02 22:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
23-03589 | Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line Including Haskill Tap | 2023-09-18 03:45 | 2023-09-18 04:14 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
October - 2023 (60 day outage planning process not completed)
ITOA ID | Equipment Outage | Start | End | Impacted Generation | Notes
23-00317 | CHIEF JOSEPH: 4725/4726 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 5 500KV LINE | 09/11/2023 05:00 | 10/05/2023 17:00 | Chief Joshph 17- 20
23-01201 | LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 10/05/2023 07:00 | 10/05/2023 21:00 | Lower Monumental 1-6
23-04186 | NOXON-LIBBY NO 1 230KV LINE | 09/25/2023 07:00 | 10/06/2023 15:00 | restrict Libby Generation to 400MW Maximum and 65MW Minimum.
23-03734 | Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line including Haskill Tap | 2023-10-02 06:00 | 2023-10-02 07:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
23-08507 | NORTH BONNEVILLE: EAST M/B INCLUDING PCB'S A-11, A-17, A-10, A-16, A-8, A-14 AND A-9 | 10/12/2023/ 07:30 | 2023-10-12 16:30 | North Bonneville 11-18

## Sheet1
FPOM August-October Transmission Outages That Have Potential to Limit Generation
August
Equipment Outage | Start | End | Impacted Generation | Notes
LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 08/14/2023 04:30 | 2023-08-31 15:00 | Libby 3-5
CHIEF JOSEPH 230kV UNITS 950 MW
September
Equipment Outage | Start | End | Impacted Generation | Notes
JOHN DAY: 4165/4166 TERMINAL OF JOHN DAY PH-JOHN DAY 3 500KV LINE | 2023-08-21 07:00 | 2023-09-14 17:00 | John Day 9-12
THE DALLES PH-BIG EDDY NO 3 230KV LINE | 09/14/2023 12:00 | 09/14/2023 12:30 | UNITS 5,8
THE DALLES PH-BIG EDDY NO 3 230KV LINE | 09/04/2023 06:30 | 09/04/2023 07:00 | UNITS 5,8
October
Equipment Outage | Start | End | Impacted Generation | Notes
CHIEF JOSEPH: 4725/4726 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 5 500KV LINE | 09/11/2023 05:00 | 10/05/2023 17:00 | Chief Joshph 17- 20
LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 10/05/2023 07:00 | 10/05/2023 21:00 | Lower Monumental 1-6
Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line including Haskill Tap | 2023-10-02 06:00 | 2023-10-02 07:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
NORTH BONNEVILLE: EAST M/B INCLUDING PCB'S A-11, A-17, A-10, A-16, A-8, A-14 AND A-9 | 10/12/2023/ 07:30 | 2023-10-12 16:30 | North Bonneville 11-18