## FPOM Dec-Feb24
FPOM December-February Transmission Outages That Have Potential to Limit Generation
2023-12-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 12/05/2023 06:00 | 2023-12-22 18:00 | Lower Granite 1-6 | Daily Outages from 0600 to 1800, T1 gasket replacement
| LITTLE GOOSE: LITTLE GOOSE PH 1 500KV LINE LOR'S, INCLUDING PCB'S 4350 & 4348 | 12/04/2023 09:00 | 12/07/2023 15:00 | Little Goose 1-6
2024-01-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| ICE HARBOR-FRANKLIN NO 1 115KV LINE | 01/08/2024 07:00 | 01/10/2024 17:00 | Ice Harbor 1-2
| THE DALLES PH-BIG EDDY NO 3 230KV LINE | 01/08/2024 07:00 | 01/08/2024 07:30 | The Dalles 5-8
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 01/09/2024 06:00 | 02/08/2024 18:00 | Lower Granite 1-6
| ICE HARBOR-FRANKLIN NO 1 115KV LINE | 01/15/2024 07:00 | 01/18/2024 17:00 | Ice Harbor 1-2
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 2 115KV LINE TRANSFER TRIP CKT 7103 | 01/17/2024 08:00 | 01/17/2024 14:00 | The Dalles 3-4
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 3 230KV LINE TRANSFER TRIP CKT 7106 | 01/18/2024 08:00 | 01/18/2024 14:00 | The Dalles 5-8
| LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE | 01/22/2024 08:00 | 01/22/2024 12:00 | Lower Monumental 1-6
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 6 230KV LINE TRANSFER TRIP CKT 7109 | 01/22/2024 08:00 | 01/22/2024 14:00 | The Dalles 17-22
| THE DALLES PH-BIG EDDY NO 6 230KV LINE | 01/29/2024 07:00 | 01/29/2024 07:30 | The Dalles 17-22
2024-02-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| THE DALLES PH-BIG EDDY NO 6 230KV LINE | 02/08/2024 12:00 | 02/08/2024 12:30 | The Dalles 17-22
| BIG EDDY: 230KV MAIN BUS SECTION 1 MAIN BUS DIFFERENTIAL RELAY | 02/12/2024 08:00 | 02/14/2024 16:00 | The Dalles 5-8
| LOWER MONUMENTAL: 4318 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE | 02/15/2024 08:00 | 02/15/2024 17:00 | Lower Monumental 1-6
| MCNARY PH-MCNARY NO 1 230KV LINE INCLUDING PCB A-404 AND BUSTIE PCB A-412 | 02/20/2024 07:00 | 02/20/2024 16:00 | Mcnary 1-2
| MCNARY: 230KV MAIN BUS SECTION 3 INCLUDING PCB'S A-440, A-436, A-434, A-432 AND A-431 | 02/21/2024 07:00 | 02/23/2024 17:00 | Mcnary 9-12
| MCNARY PH-MCNARY NO 2 230KV LINE INLCUING PCB A-408 AND BUSTIE PCB A-412 | 02/21/2024 07:00 | 02/21/2024 16:00 | Mcnary 3-4
| MCNARY PH-MCNARY 3&4 NO 4 230KV LINE INCLUDING PCB A-420 | 02/23/2024 08:00 | 02/23/2024 15:00 | Mcnary 5-8
| MCNARY: 230KV MAIN BUS SECTION 3 | 02/27/2024 07:30 | 03/15/2024 17:00 | Mcnary 9-12