## FPOM Feb-March 2023
FPOM Feb-April Transmission Outages That Have Potential to Limit Generation
FEB
Equipment Outage | Start | End | Impacted Generation | Notes
LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE, INCLUDING LITTLE GOOSE PCBs 4348 & 4350 | 02/13/2023 08:00 | 02/21/2023 15:00 | Little Goose 1-6
LITTLE GOOSE: 4349/4351 TERMINAL OF, LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 02/13/2023 08:00 | 02/21/2023 17:00 | Little Goose 1-6
THE DALLES PH-BIG EDDY NO 6 230KV LINE | 02/16/2023 12:00 | 02/16/2023 12:30 | The Dalles 17-22
MCNARY PH-MCNARY NO 1 230KV LINE | 02/28/2023 10:00 | 02/28/2023 14:00 | McNary 1-2
LOWER MONUMENTAL 500KV WEST BUS INCLUDING LOWER MONUMENTAL PH #1 500KV LINE STUB BUS AND MOD 4343 | 02/06/2023 08:30 | 02/10/2023 15:00 | Lower Monumental 1-6
MAR
Equipment Outage | Start | End | Impacted Generation | Notes
THE DALLES PH-BIG EDDY NO 5 230KV LINE | 03/27/2023 06:30 | 03/27/2023 07:00 | The Dallas 13-16
CHIEF JOSEPH PH-CHIEF JOSEPH NO 6 500KV LINE, INCLUDING CHIEF JOSEPH: PCB 4598, PCB 4730 | 03/07/2023 10:00 | 03/07/2023 13:00 | Chief Joseph 21-27
-USBR- HUNGRY HORSE: PCB'S 2182 AND 2382 | 03/13/2023 06:00 | 2023-04-27 16:00 | Hungry Horse 1-2
APR
Equipment Outage | Start | End | Impacted Generation | Notes
BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 04/03/2023 06:30 | 04/03/2023 07:00 | The Dalles 9-12
BIG EDDY: PCB A-824 OF THE DALLES PH-BIG EDDY NO 4 230KV LINE | 04/13/2023 16:30 | 04/13/2023 17:00 | The Dalles 9-12
BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | 04/17/2023 06:30 | 04/17/2023 07:00 | The Dalles 3-4
BIG EDDY: PCB B-1050 OF THE DALLES PH-BIG EDDY NO 2 115KV LINE | 04/27/2023 14:00 | 04/27/2023 15:00 | The Dalles 3-4
LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | 04/24/2023 21:00 | 04/25/2023 01:30 | Hungry Horse 100 MW Min, Libby 453 MW Max
LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE INCLUDING THE A-274 LINE SECTIONALIZING DISCONNECT | 04/25/2023 07:00 | 04/27/2023 14:00 | Hungry Horse 100 MW Min, Libby 453 MW Max
LIBBY-TRUMBULL CREEK SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE INCLUDING HASKILL TAP | 04/27/2023 21:00 | 04/28/2023 01:30 | Hungry Horse 100 MW Min, Libby 453 MW Max