OFFICIAL COORDINATION REQUEST FOR

NON-ROUTINE OPERATIONS AND MAINTENANCE

COORDINATION TITLE- 23BON024 MOC Old Navlock dredge placement

COORDINATION DATE- 	31 May 2023

PROJECT- Bonneville Lock and Dam

RESPONSE DATE- 	14 Jun 2023

Description of the problem - The Corps is proposing to install new concrete stoplogs across the upstream entrance of Bonneville Dam NavLock 1 (NL1), and into the existing stoplog slots. NL1 has been inactive since the 1990s,and the stoplogs will be used to dewater NL1 so inspections / maintenance can occur. The new stoplogs will be installed via barge and no mods to existing staging areas or access routes will be needed. Prior to installation, dredging is required of approximately 1600 CYs of accumulated sediment at the NL1 upstream sill to allow for watertight placement of the new stoplogs. The dredged material is proposed for in water disposal downstream of the dam via barge in the active flow areas at Columbia River flow lane RM 144. Comprehensive sediment testing has been accomplished and material has been approved as suitable for in water disposal by ODEQ and USEPA reps via the Portland Sediment Evaluation Team (PSET) process on 22 Feb 2023.  Proponent requests dredging and in water deposition of ~1600 CYs (PSET tested suitable for in water placement) sediment for Bon Navigation Lock 1 inspections and maintenance.

Figure 1-1 Bon Dam Project area with NL1 Upstream Bulkhead slot (site of dredge action) at far right

Type of outage required- None

Impact on facility operation- None, no impacts to Bonneville Dam or Fish Passage Operations, NL1 is currently not in use.

Dates of impacts/repairs- Work planned for Bonneville dam In Water Work Windows, Jan 14-31, 2024.

Length of time for repairs- 1-2 weeks total for mobilization, dredging of NL1 concrete sill/apron (~1600 CYs), and downriver transport and placement (Columbia River flowlane RM 144).

Analysis of potential impacts to fish-

This work is scheduled to occur during the normal winter maintenance period.  There should be minimal impacts to ESA listed fish.

Summary statement –

Expected impacts on any fish species are minimal (from dredging action at Bonneville NL1 as well as in water deposition of sediment in Columbia River Flowlane at RM 144), due to work being conducted within Bonneville Dam in water work window (Nov-Feb) and historically documented reduced fish passage on Columbia River at Bonneville during that time. In addition, current BON Ops plan for IWW 2023/2024 is for a complete shutdown of fish passages for scheduled maintenance during the 2023/2024 IWW window, further reducing any expected impacts to listed species.  However, some minor species impacts are expected during actual dredge operations as Larval/Juvenile Lamprey, expected to inhabit the BON NL1 concrete apron sediment acumulation, and their habitat will be disrupted (and subsequenty relocated), while sediments are removed via dredge suction device or mechanical clamshell dredge. Dredging contractor will be provided with Best Mgmt Practices (BMPs) designed specifically to minimize impacts to lampreys during dredging actions (ref: Ref: (1)).

The proposed action (maintenance dredging at BON NL1 upstream concrete apron)  is in line with O&M activities as found “not likely to jeopardize” protected anadromous fish spp. and “will not destroy or adversely modify designated critical habitat for the same species” per 2020 NMFS Biological Opinion for Continued Operation and Maintenance of the Columbia River System, Sections 1.3.1.5 (Operations for Navigation) and 1.3.1.7 (System Maintenance).  In addition, a minimal Environmental Remediation benefit is expected to be realized from retention of the sediment material in the Columbia River flowlane as the natural channel flow transports the sediment as nourishing materials for downstream wetland replenishment in place of deposits that naturally erode away due to wave action, wind, etc.

Expected impacts

Downstream migrants: Juvenile salmonid minor impacts only expected due to historic salmonid run periods are outside proposed work window (BON IWW Dec-Feb).

Upstream migrants (including Bull Trout): Adult passage, including bull trout, minor impacts only expected due to historic salmonid run periods are outside proposed work window (BON IWW Dec-Feb).

Lamprey: Juvenile/larval lamprey currently existing in the nav lock concrete apron sediment accumulation may be disturbed/collected/injured/killed via the limited dredging action (either through direct dredging impacts, being crushed under sediment in the barge, or by predation after return to the river). Dredging contractor to be provided Best Mgmt Practices (BMPs) designed specifically to minimize impacts to lampreys during dredging actions (ref: Ref: (1)).

Ref: (1) Pacific Lamprey Cons; Monitoring and Minimizing Effects of Dredging on Lampreys, Living Document, Original Version 1.0, March 2021, Lamprey Technical Workgroup

Comments from agencies:

USFWS – comments in the document in track changes.  Responses also in the document.

Yakama Nation - From: Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >

Sent: Saturday, June 3, 2023 6:26 AM

To: Mackey, Tammy M CIV USARMY CENWP (USA) <Tammy.M.Mackey@usace.army.mil <mailto:Tammy.M.Mackey@usace.army.mil> >

Subject: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old navlock dredge placement

Hi Tammy,

What specifically are the "management practices" that are mentioned below?

Lamprey: Juvenile/larval lamprey may be disturbed/collected/injured via limited

dredging action. Contractor to be advised to mitigate impacts via management practices

I have heard quite a few (hundreds of juvenile lamprey) have been found here in the past and would be important to make a concerted effort to both rescue them as well as document them (subsample some for life stage [larva vs. juveniles], genetics, etc. to find out where the source of these lamprey(s) are).

~Warm Regards~

Ralph Lampman

COLUMBIA RIVER| Honor. Protect. Restore

Yakama Nation FRMP, Pacific Lamprey Project

lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov>

509-388-3871

-----Original Message-----
From: Ralph Lampman <lamr@yakamafish-nsn.gov> 
Sent: Monday, June 12, 2023 5:06 PM
To: Moncrief, James B (Barry) CIV USARMY CENWP (USA) <James.B.Moncrief@usace.army.mil>
Subject: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old NavLock dredge and placement

👍👍

Awesome

~Warm Regards~

Ralph T. Lampman

Lamprey Research Biologist

Yakama Nation FRMP

Pacific Lamprey Project

On Mon, Jun 12, 2023, 2:10 PM Moncrief, James B (Barry) CIV USARMY CENWP (USA) <James.B.Moncrief@usace.army.mil <mailto:James.B.Moncrief@usace.army.mil> > wrote:

Ralph,

Thank you for the excellent guidance documents on lamprey protection during dredging and in water operations.

I’ll forward this info to our dredge team for their guidance as well as my own. Very helpful!

Barry

James B. Moncrief (Barry)

U.S. Army Corps of Engineers, Portland District

Environmental Resource Specialist

Environmental Resources Branch

Phone:  503-808-5101

Email: james.b.moncrief@usace.army.mil <mailto:james.b.moncrief@usace.army.mil>

From: Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >

Sent: Friday, June 9, 2023 8:04 AM

To: Moncrief, James B (Barry) CIV USARMY CENWP (USA) <James.B.Moncrief@usace.army.mil <mailto:James.B.Moncrief@usace.army.mil> >

Subject: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old NavLock dredge and placement

Hi Barry,

The link below is the latest guideline from PL Conservation Initiative Lamprey Technical Work Group on this topic (dredging):

Monitoring and Minimizing Effects of Dredging on Lampreys

https://www.pacificlamprey.org/wp-content/uploads/2022/02/Dredging_-and_Lampreys_03.19.21.pdf

The link below provides more specifics on how to handle lamprey once you encounter them:

Best Management Guidelines for Native Lampreys During In-water Work

https://www.pacificlamprey.org/wp-content/uploads/2022/10/BMGs-for-Native-Lampres-During-In-Water-Work-Final-Updated-2022-2.pdf

If there are any questions, happy to help.

Appreciate your help on this.

~Warm Regards~

Ralph Lampman

COLUMBIA RIVER| Honor. Protect. Restore

Yakama Nation FRMP, Pacific Lamprey Project

lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov>

509-388-3871

USACE/BPA –

From: Mcclain, Nathan A CIV USARMY CENWP (USA) <Nathan.A.McClain@usace.army.mil <mailto:Nathan.A.McClain@usace.army.mil> >

Sent: Thursday, June 8, 2023 12:17 PM

To: Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >; Mackey, Tammy M CIV USARMY CENWP (USA) <Tammy.M.Mackey@usace.army.mil <mailto:Tammy.M.Mackey@usace.army.mil> >

Subject: [EXTERNAL] RE: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old navlock dredge placement

Ralph,

To clarify the dredging will take place in front of the old nav lock. They need to clean up sediment that has settled into the bulkhead slot, upstream of the gate, so the bulkhead can be put in place.

I’ve been told it has [HASN’T been used or dredged since the 1990’s. No lamprey work has been done in that area. The only area dredged at Bonn that has been surveyed for lamprey is the Bradford Island adult ladder exit. Ben] been used (or dredge) since the 1990’s. So I do not know of any work that indicates 100’s of juveniles there but wouldn’t be surprised if there are some. If you have different information please let me know.

More importantly I will try to find out what management practices will be implemented to protect lamprey.

Nathan

From: Macdonald, Jacob B CIV USARMY CENWP (USA) <Jacob.Macdonald@usace.army.mil <mailto:Jacob.Macdonald@usace.army.mil> >

Sent: Thursday, June 8, 2023 3:34 PM

To: Hausmann,Benjamin J (BPA) - EWP-4 <bjhausmann@bpa.gov <mailto:bjhausmann@bpa.gov> >; Mcclain, Nathan A CIV USARMY CENWP (USA) <Nathan.A.McClain@usace.army.mil <mailto:Nathan.A.McClain@usace.army.mil> >; Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >; Mackey, Tammy M CIV USARMY CENWP (USA) <Tammy.M.Mackey@usace.army.mil <mailto:Tammy.M.Mackey@usace.army.mil> >

Subject: RE: [EXTERNAL] RE: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old navlock dredge placement

I think Ralph may be remembering reports of substantial numbers of juvenile lamprey we’ve observed in the chamber of the new nav lock during annual dewatering.  If we see them inside the active nav lock, it’s a pretty safe bet there’s juvenile lamprey in the sediment in and around the old nav lock too.

How are we doing this dredging? With a suction hose or a clamshell?  Is there an opportunity anywhere in the handling process for an interested researcher to sift through the dredge material looking for lamprey?

From: Mcclain, Nathan A CIV USARMY CENWP (USA) <Nathan.A.McClain@usace.army.mil <mailto:Nathan.A.McClain@usace.army.mil> >

Sent: Thursday, June 8, 2023 3:38 PM

To: Macdonald, Jacob B CIV USARMY CENWP (USA) <Jacob.Macdonald@usace.army.mil <mailto:Jacob.Macdonald@usace.army.mil> >; Hausmann,Benjamin J (BPA) - EWP-4 <bjhausmann@bpa.gov <mailto:bjhausmann@bpa.gov> >; Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >; Mackey, Tammy M CIV USARMY CENWP (USA) <Tammy.M.Mackey@usace.army.mil <mailto:Tammy.M.Mackey@usace.army.mil> >

Cc: Moncrief, James B (Barry) CIV USARMY CENWP (USA) <James.B.Moncrief@usace.army.mil <mailto:James.B.Moncrief@usace.army.mil> >

Subject: RE: [EXTERNAL] RE: [URL Verdict: Neutral][Non-DoD Source] Re: FPOM: Official Coordination - 23BON24 MOC Old navlock dredge placement

Barry, do you have any insight on the proposed dredging method? Also see Jake question below [above]:

From: Moncrief, James B (Barry) CIV USARMY CENWP (USA) <James.B.Moncrief@usace.army.mil <mailto:James.B.Moncrief@usace.army.mil> >

Sent: Thursday, June 8, 2023 4:18 PM

To: Mcclain, Nathan A CIV USARMY CENWP (USA) <Nathan.A.McClain@usace.army.mil <mailto:Nathan.A.McClain@usace.army.mil> >; Macdonald, Jacob B CIV USARMY CENWP (USA) <Jacob.Macdonald@usace.army.mil <mailto:Jacob.Macdonald@usace.army.mil> >; Hausmann,Benjamin J (BPA) - EWP-4 <bjhausmann@bpa.gov <mailto:bjhausmann@bpa.gov> >; Ralph Lampman <lamr@yakamafish-nsn.gov <mailto:lamr@yakamafish-nsn.gov> >; Mackey, Tammy M CIV USARMY CENWP (USA) <Tammy.M.Mackey@usace.army.mil <mailto:Tammy.M.Mackey@usace.army.mil> >; Griffith, David W CIV USARMY CENWP (USA) <David.W.Griffith@usace.army.mil <mailto:David.W.Griffith@usace.army.mil> >

Subject: Re: FPOM: Official Coordination - 23BON24 MOC Old NavLock dredge and placement

From Dredging Contracts Team Lead (Terry Geroux):

“I would anticipate that we’d see a combo of mechanical and hydraulic, with the bulk of the material being dredged mechanically”

We figure at least some suction dredging to clear out Nav Lock stoplogs channels so new stoplogs will fit…

Dredging team is also looking for:  “Can your ESA person offer up any sort of restrictions or BMPs that would have to be followed to minimize lamprey injury? It’s not something that we encounter typically.”

So to me this looks like they would (possibly) be receptive to ride along fish guy, but would have to ask. I think this would be very beneficial from overall species protection standpoint as well.

And if you have any specific lamprey precautions for the team, pls pass them along, cheers.

Barry

James B. Moncrief (Barry)

U.S. Army Corps of Engineers, Portland District

Environmental Resource Specialist

Environmental Resources Branch

Phone:  503-808-5101

Email: james.b.moncrief@usace.army.mil <mailto:james.b.moncrief@usace.army.mil>

Final coordination results:

Please email or call with questions or concerns.

Thank you,

Tammy Mackey

Columbia River Coordinator

503-808-4318

Tammy.m.mackey@usace.army.mil

J Barry Moncrief, Portland District Env Resource Specialist

Env Resources Branch

Phone:  503-808-5101

Email: james.b.moncrief@usace.army.mil

David Griffith

Endangered Species Act Coordinator

USACE Portland District

(503) 808-4773

Email: David.W.Griffith@usace.army.mil