## FPOM
FPOM June-August Transmission Outages That Have Potential to Limit Generation
JUNE
Equipment Outage | Start | End | Impacted Generation | Notes
HUNGRY HORSE-COLUMBIA FALLS NO 1 230KV LINE | 06/20/2023 07:00 | 06/29/2023 16:00 | Libby + Hungry Horse Total Gen 600 MW Max
HUNGRY HORSE-COLUMBIA FALLS NO 1 230KV LINE | 06/26/2023 06:00 | 06/30/2023 15:00 | Libby + Hungry Horse Total Gen 600 MW Max
TRUMBULL CREEK-CONKELLEY SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | 06/20/2023 07:00 | 06/22/2023 16:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
LIBBY-HASKILL SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | 06/26/2023 03:00 | 06/29/2023 15:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
JULY
Equipment Outage | Start | End | Impacted Generation | Notes
NORTH BONNEVILLE: EAST M/B INCLUDING PCB'S A-11, A-17, A-10, A-16, A-8, A-14 AND A-9 | 7/25/2023/ 11:00 | 2023-07-25 20:00 | North Bonneville 11-18
HASKILL-TRUMBULL CREEK SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | 07/10/2023 04:15 | 07/28/2023 22:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line including Haskill Tap | 07/28/2023 22:01 | 07/28/2023 22:30 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line Including Haskill Tap | 07/10/2023 03:45 | 07/10/2023 04:14 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
MCNARY: 115KV MAIN BUS SECTION 2 | 07/28/2023 07:00 | 07/28/2023 16:00 | MCNARY UNITS 13 & 14
MCNARY PH-MCNARY NO 1 230KV LINE | 07/10/2023 06:30 | 07/10/2023 07:00 | Mcnary 1-2
CONKELLEY: 230KV EAST AUX BUS INCLUDING PCBS A-1210, A-1282, 230KV REACTIVE BUS 1 AND 230/13.8KV XFMR 4 | 07/24/2023 08:00 | 07/25/2023 15:00 | Libby + Hungry Horse total generation to 600MW
August
Equipment Outage | Start | End | Impacted Generation | Notes
TRUMBLE CREEK-CONKELLEY SECTION OF THE LIBBY-CONKELLEY #1 230KV LINE | 07/31/2023 07:00 | 08/18/2023 14:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
LITTLE GOOSE: 4349/4351 TERMINAL OF LITTLE GOOSE PH-LITTLE GOOSE NO 1 500KV LINE | 07/31/2023 05:00 | 2023-07-31 17:00 | Little Goose 1-6
LITTLE GOOSE | 2023-07-31 07:00 | 8/12/2023 1700 | Litte Goose 1-4
LITTLE GOOSE | 2323-08-12 07:00 | 8/12/2023 1700 | Little Goose 1-6
LOWER MONUMENTAL: 4317/4343 TERMINAL OF LOWER MONUMENTAL PH-LOWER MONUMENTAL 1 500KV LINE | 2023-07-24 05:30 | 08/03/2023 15:00 | Lower Monumental 1-6
LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 08/14/2023 04:30 | 09/01/2023 15:00 | Libby 3-5
sb 6/8/23