## FPOM Nov 23 - Jan 24
FPOM November-January Transmission Outages That Have Potential to Limit Generation
2023-11-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| MCNARY PH-MCNARY NO 6 115KV LINE | 11/09/2023 16:30 | 11/09/2023 17:00 | Mcnary units 13-14
| THE DALLES PH-BIG EDDY NO 1 115KV LINE INCLUDING BIG EDDY PCB B-1692 AND 115KV A/B | 11/13/2023 08:00 | 11/19/2023 18:00 | The Dalles units 1-2
2023-12-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| THE DALLES PH-BIG EDDY NO 2 115KV LINE INCLUDING BIG EDDY PCB B-1050 AND 115KV A/B | 11/27/2023 08:00 | 12/03/2023 18:00 | The DALLES units 3-4
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 11/28/2023 06:00 | 12/22/2023 18:00 | Mcnary units 9-12
2024-01-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 2 115KV LINE TRANSFER TRIP CKT 7103 | 01/17/2024 08:00 | 01/17/2024 14:00 | The Dalles Units 3-4
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 3 230KV LINE TRANSFER TRIP CKT 7106 | 01/18/2024 08:00 | 01/18/2024 14:00 | The Dalles Units 5-8
| BIG EDDY: THE DALLES PH-BIG EDDY NO. 6 230KV LINE TRANSFER TRIP CKT 7109 | 01/22/2024 08:00 | 01/22/2024 14:00 | The Dalles Units 17-22
| THE DALLES PH-BIG EDDY NO 3 230KV LINE | 01/08/2024 07:00 | 01/08/2024 07:30 | THE DALLES PH 5-8
| THE DALLES PH-BIG EDDY NO 3 230KV LINE | 01/18/2024 12:00 | 01/18/2024 12:30 | The DALLES PH Units 5-8
| THE DALLES PH-BIG EDDY NO 6 230KV LINE | 01/29/2024 07:00 | 01/29/2024 07:30 | THE DALLES PH Units 17-22
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 01/09/2024 06:00 | 02/08/2024 18:00 | LOWER GRANITE Units 1-6
sb 11/9