## FPOM Aug-Oct
FPOM October-Deceber 2023 Transmission Outages That Have Potential to Limit Generation
October
| Equipment Outage | Start | End | Impacted Generation | Notes
| CHIEF JOSEPH: 4725/4726 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 5 500KV LINE | 09/11/2023 05:00 | 10/05/2023 17:00 | Chief Joseph 17- 20
| LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 10/05/2023 07:00 | 10/05/2023 21:00 | Lower Monumental 1-6
| NORTH BONNEVILLE: EAST M/B INCLUDING PCB'S A-11, A-17, A-10, A-16, A-8, A-14 AND A-9 | 10/12/2023/ 07:30 | 2023-10-12 16:30 | North Bonneville 11-18
November
| Equipment Outage | Start | End | Impacted Generation | Notes
| BIG EDDY: 115KV MAIN BUS SECTIONS 2 AND 3 INCLUDING PCB B-1054, PCB B-1050 AND PCB B-1048 | 10/30/2023 08:00 | 11/05/2023 18:00 | The Dalles units 17-22
| THE DALLES PH-BIG EDDY NO 1 115KV LINE INCLUDING BIG EDDY PCB B-1692 AND 115KV A/B | 11/13/2023 08:00 | 11/19/2023 18:00 | The Dalles units 1-2
December
| Equipment Outage | Start | End | Impacted Generation | Notes
| THE DALLES PH-BIG EDDY NO 2 115KV LINE INCLUDING BIG EDDY PCB B-1050 AND 115KV A/B | 11/27/2023 08:00 | 12/03/2023 18:00 | The Dalles units 3-4
| MCNARY: 230KV MAIN BUS SECTION 3 | 12/04/2023 07:00 | 12/08/2023 16:00 | McNary units 9-12
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 11/28/2023 06:00 | 12/22/2023 18:00 | Lower Granite Units 1-6
sb 10/5/23