## FPOM Sept -Nov 2023
FPOM September-November Transmission Outages That Have Potential to Limit Generation
2023-09-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| JOHN DAY: 4165/4166 TERMINAL OF JOHN DAY PH-JOHN DAY 3 500KV LINE | 2023-08-21 07:00 | 2023-09-14 17:00 | John Day 9-12
| HASKILL-TRUMBULL CREEK SECTION OF LIBBY-CONKELLEY NO 1 230KV LINE | 2023-09-18 04:15 | 2023-10-02 22:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
| Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line Including Haskill Tap | 2023-09-18 03:45 | 2023-09-18 04:14 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
2023-10-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| LOWER MONUMENTAL PH-LOWER MONUMENTAL NO 1 500KV LINE | 10/05/2023 07:00 | 10/05/2023 21:00 | Lower Monumental 1-6
| BON Big Eddy-TDA 115 kv line outage | 2023-10-11 08:00 |  | may change unit priority | one 115 kv unit will need to run if NBON capacitor bank is not available.
| Libby-Trumbull Creek Section of the Libby-Conkelley No 1 230kV Line including Haskill Tap | 2023-10-02 06:00 | 2023-10-02 07:00 | Hungry Horse generation to 100 MW Minimum Libby generation to 453 MW Maximum.
| NORTH BONNEVILLE: EAST M/B INCLUDING PCB'S A-11, A-17, A-10, A-16, A-8, A-14 AND A-9 | 10/12/2023/ 07:30 | 2023-10-12 16:30 | North Bonneville 11-18
| LIBBY: A-1587 TERMINAL OF THE LIBBY PH-LIBBY NO 2 230KV LINE | 08/14/2023 04:30 | 2023-10-05 15:00 | Libby 3-5
2023-11-01
| Equipment Outage | Start | End | Impacted Generation | Notes
| BIG EDDY: 230KV MAIN BUS SECTION 1 MAIN BUS DIFFERENTIAL RELAY | 11/06/2023 08:00 | 11/08/2023 16:00 | the dallas units 5-8
| MCNARY PH-MCNARY NO 6 115KV LINE | 11/09/2023 16:30 | 11/09/2023 17:00 | Macnary PH 13-14
| LOWER GRANITE: 4771/4773 TERMINAL OF LOWER GRANITE PH-LOWER GRANITE NO 1 500KV LINE | 11/28/2023 06:00 | 12/22/2023 18:00 | GRANITE PH 1-6
| BIG EDDY: 115KV MAIN BUS SECTIONS 2 AND 3 INCLUDING PCB B-1054, PCB B-1050 AND PCB B-1048 | 10/30/2023 08:00 | 11/05/2023 18:00 | the dallas units 17-22
| THE DALLES PH-BIG EDDY NO 1 115KV LINE INCLUDING BIG EDDY PCB B-1692 AND 115KV A/B | 11/13/2023 08:00 | 11/19/2023 18:00 | THE DALLES PH 1-2
| THE DALLES PH-BIG EDDY NO 2 115KV LINE INCLUDING BIG EDDY PCB B-1050 AND 115KV A/B | 11/27/2023 08:00 | 12/03/2023 18:00 | THE DALLES PH 3-4
sb 9/14/23