Update for Natalie Richards- 6/7/2012
CRFM

118738 Lamprey Program

Turned over Research to Mike Langeslay 
373409-BONN WA Shores-Gravity Flow-
Ktrs refused to bid coating( working through issue. Bids due June 6, 2012 COB then they will go to the Technical Evaluation Board for review.
118618-Adult Salmon and Steelhead Studies
Kelt work obligated to PNNL
138171-John Day North Fish Ladder 
Entrance 

Slayden- 2nd season to address ¾” gratings, sluice and stove pipe weirs and possible entrance undermining work- Sean/Dave to discuss with FFDRWG. 
Olsson-6 Pumps, Power Controls and Housing- Pumps #2-#4 are up and running ladder in criteria.  Ktr working on #1, #5 lower bearing issue. #6 awaiting results from #1 and #5
353174-TDA PIT Alternatives Study Report- Team working on 90% Alternative Report. Sean/Marie-USACE wants to assure coordination with BPA on antennas so that all meet in a construction project for FY14.
393762-Fall Creek Fish Facility- A/E (URS) SOW Request for Proposal due back Mid- June.  With negotiations, anticipate contract Late June.  David Leonhardt will work through Doodle pool for a July all agency site visit.
O&M
331067-Bradford Emergency Repair- All work completed
354296-Bradford Island Reliability – Working on 90% Risk Matrix report
2406 Program
373284- JDA PH Monolith Drainage issues – Team working on 30% DDR
