## Prioritization
LPS Project Prioritization Table
Tasks | Mean BON Benefit | MIN BON Benefit | MAX BON Benefit | Construction IWW Period | Comments | Actions
MANDATORY (MOVING FORWARD)
Mandatory mods to existing systems | 0% | 0% | 0% | 2016-17, 2017-18 | Any new systems or modifications to existing structures should include capability of installing additional segments. | PDT: Proceed with 60% DDR design work. Ensure that new proposed (below) LPS segments could be added at a later date, should additional funding and need be identified.
BON WA Shore - Extensive LFS entrained air fix | TBD | TBD | TBD | 2016-17 | Based on early season collection #s, has good potential benefit. Consider mandatory, based on initial investment and potential future extension? Collects smaller fish than are collected in the ladder traps. | PDT: Move forward with LFS entrained air fix.
HIGH PRIORITY TASKS (MOVING FORWARD)
BON WA Shore - New ramp u/s of UMT junction | 0.89% | 0.12% | 2.31% | 2016-17 | Group agreed that this location has greatest potential to benefit overall BON passage by guiding fish away from serpentine weirs, though actual performance here is untested. Potentially more risk relative to salmonids (in ladder), but not likely an issue. Keefer (UI): May be good to use video or DIDSON to evaluate lamprey behavior in this area. Moser (NOAA): Experimental refuge box use in this area suggests good potential. Should look at results. | PDT: Proceed with 60% DDR design work. Develop initial design that has ramps on both north and south walls, for further review by FFDRWG (need NOAA approval).
BON Bradford - New ramp d/s of count station | 0.54% | 0.02% | 1.69% | 2017-18 | Group agreed that this location, like WA Shore, has high potential for guiding lamprey away from problematic serpentine weirs. | PDT: Proceed with 60% DDR design work. Develop initial design that has ramps on both north and south walls, for further review by FFDRWG (need NOAA approval).
JDA North - New entrance ramp (south) | NA | NA | NA | 2017-18 | Tackley: Given relatively low cost and potential to collect additional fish to existing trap/haul LPS, this seems like a good option. | Tackley: Consult with Corps-Tribal workgroup regarding program priorities. PDT: Pending Corps-Tribal workgroup prioritization, move forward with 60% DDR design work. Should include monitoring capability (i-beam for camera?).
JDA North - Extend LPS to 180-degree bend | NA | NA | NA | 2017-18 | Caudill: Alternatively, should consider running vertically to elevated section immediately above current LPS trap box location. Shorter distance, but would require access staircase, more rest boxes. Tackley: This is something we've discussed on previous site visits and it is worth exploring the costs/benefits. | Tackley: Consult with Corps-Tribal workgroup regarding program priorities. PDT: Pending Corps-Tribal lamprey workgroup priorization, move forward with 60% DDR design work. Consider alternative design approach that delivers lamprey to elevated section of ladder. Will include capability to do trap-and-haul.
DO NOT PURSUE FURTHER DESIGN (BEYOND 60% DDR) IN FY15-FY18
BON Cascades - New entrance ramp (south) | 0.1% | -0.13% | 0.49% | 2016-17 | Estimated cost seemed high to group. High cost of adding additional ramp due to new pump requirements, upsizing certain components upstream, etc? | Tackley: Consult with Corps-Tribal workgroup regarding program priorities. PDT: Pending Corps-Tribal workgroup prioritization, move forward with 60% DDR design work. Should include monitoring capability (i-beam for camera?).
BON Bradford - New LPS from transition pool or entrance | 0.19% | -0.1% | 0.79% | 2017-18 | Need to determine whether to install Cascades Island-style LPS or LPS that follows fishway. Group discussed risks/benefits of Cascades Island-style LPS. Relatively easy forebay area for routing. Known quantity, based on Cascades Island (though entrance is different). Separate system spreads risk but results in another LPS counting system. Easier access for O&M. | Tackley: Consult with Corps-Tribal workgroup regarding program priorities. PDT: Complete 60% DDR and suspend further design.
BON WA Shore - Extend LFS and add new transition pool ramp | 0.03% | -0.88% | 1.01% | 2016-17 | This system has good potential, but may be too risky and costly to pursue at this time, given uncertainties about performance of the LFS, potential performance of transition pool LPS, O&M workload, and program uncertainties after 2018. | Tackley: Consult with Corps-Tribal workgroup on decision to suspend design work for now. PDT: Shelve design work. Consider resuming design efforts after FY17 so this design is ready for future use/evaluation.
BON WA Shore - New ramp u/s of picket leads | 0.89% | 0.12% | 2.31% | 2016-17 | May be functionally redundant w/ ramp u/s of UMT junction; Estimated benefits should be adjusted downward if a new ramp is just downstream. Already pretty good collection efficiency of MUWS Channel LPS. | PDT: Suspend design indefinitely; only pursue in future as alternative to a ramp downstream of picket leads.
BON Bradford - New ramp u/s of picket leads | 0.54% | 0.02% | 1.69% | 2017-18 | May be functionally redundant w/ ramp d/s of count station. Estimated benefits should be adjusted downward if a new ramp is just downstream. Already pretty good collection efficiency of MUWS Channel LPS. | PDT: Suspend design indefinitely; only pursue in future as alternative to a ramp downstream of picket leads.
BON Cascades - New MUWS Channel LPS | 0.71% | 0.23% | 1.25% | 2016-17 | Corps concerned about increased O&M due to having separate system (pumps, counting, etc). May be higher risk of fallback, but limited evaluation suggests not. Diminished benefits if a new LPS ramp is installed just upstream of WA Shore UMT junction. Mary Moser (NOAA) noted that directing fish to WA Shore rather than installing a new LPS here carries the "all eggs in one basket" risk. | PDT: Temporarily suspend design work. Consider completing design after FY17 so Corps has option to install this otherwise high-potential system in the future. If any components of existing WA Shore or Bradford Island MUWS Channel LPSs are removed, store for future use at this location.
JDA North - Further extend LPS to forebay | NA | NA | NA | 2017-18 | Tackley: This seems difficult to justify, based on distance, cost, and relatively good passage in ladder. | PDT: Plan on extending to 180-degree bend only, but retain options for (1) using the LPS as trap/haul structure; (2) extending the structure to the ladder exit area.
NEW LPS LOCATIONS DISCUSSED
BON WA Shore - New LPS (trap/haul) between SUE and SDE | 0.12% | 0.45% | 0.89% | 2016-17 (RME, pending prioritization and review) | Caudill: Corps should consider Installing a JDA North-style LPS immediately upstream of BON WA Shore SDE or SUE entrances, given the extremely poor passage efficiency of this area (including collection channel). High potential to improve overall number of lamprey successfully collected into fishways. Routing to ladder/forebay would be complicated given the location; would have to be trap/haul. Tackley: Corps considered this location early in scoping, but given schedule and the trap/haul dynamic, didn't find this appropriate at this time. Would be good location for experimental LPS, perhaps designed and installed by U of I or NOAA. Update: Tackley determined that a location upstream of SUE is not feasible. Upstream of SDE is feasible, but would require design/install of a rest box access point (ladder and platform) in addition to LPS. | Tackley: Discuss this option with BON Project, FFDRWG, and Corps-Tribal workgroup as location for experimental LPS. If this is a priority experimental LPS task, integrate with SRWG research summary/1-pager and fund researchers to design, build, evaluate. Update: Added this task to SRWG 1-pager for FY16 (design and fabrication), but further internal and external discussion required.
BON Bradford Island and BON WA Shore - "Wetted wall" concept for diverting lamprey from serpentine weirs to MUWS Channel LPSs | TBD | TBD | TBD | 2015-16 and 2016-17 (RME) | Group discussed potential use of experimental "wetted wall" (waterfall) to guide lamprey from serpentine weir section to MUWS channel LPSs. This could further reduce number of lamprey encountering turn-around location in serpentine weirs. Tackley: Testing this structure at Bradford Island was included in FY16 AFEP research summary (1-pager), but depends on budget and priorities. | Tackley: Already integrated this into LPS development and adult lamprey passage research summaries/1-pagers for SRWG consideration. Tackley will discuss priorities, evaluation, etc with BON Project, Corps-Tribal workgroup, and researchers. Current schedule is to install at Bradford Island during 2015-16 IWW period; evaluate in 2016. Budget constraints may affect this plan.
JDA South - New LPS (trap/haul) upstream of SE1 entrance (between entrance and transition pool) | TBD | TBD | TBD | 2017-18 (RME, pending prioritization and review) | Caudill: Corps should consider Installing a JDA North-style LPS in JDA South Ladder, somewhere between entrance and transition pool. Tackley: Corps considered this location early in scoping, but given schedule and the trap/haul dynamic, didn't find this appropriate at this time. Would be good location for experimental LPS, perhaps designed and installed by U of I or NOAA. | Tackley: Discuss this option with JDA Project, FFDRWG, and Corps-Tribal workgroup as location for experimental LPS. If this is a priority experimental LPS task, integrate with SRWG research summary/1-pager and fund researchers to design, build, evaluate. Update: Added this task to program plans (RME) for outyear planning purposes, but further internal and external discussion required.

## Passage Benefits Modeling
[11 empty] | B-Branch (Alternative C: site 8 or 9 with one LPS collector) | [8 empty] | WA-shore Junction pool (Alternative A: site 2 with one collector) | [8 empty] | WA-shore UMT Junction (Alternative A: site 3 with one collector) | [8 empty] | Bradford below count station (Alternative B: site 5) | [8 empty] | Cascades Island Exit (Alternative E: site 11) | [8 empty] | Cascades Island Entrance (Alternative F: site 10)
LPS passage efficiency | LPS collection efficiency | Site 2: WA Shore JP | Site 3: WA Shore u/s of UMT Junction | Sites 8 or 9: Bradford B-Branch TP or Entr. | Site 5: Bradford d/s of Count Station | Site 11: Casc. Island MUWS Channel | Site 10: Casc. Island Entr. (South) | Site X: Near WA Shore SDE | Site Y: Near WA Shore SUE | LPS Collection efficiency: | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High |  | BON PH2 SDE | [8 empty] | BON PH2 S corner of collection channel near SUE
[10 empty] | LPS Passage efficiency: | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High
P:low | C:low | -0.1471% | 0.1174% | -0.01672% | 0.02207% | 0.3196% | -0.02123% | 0.1197% | 0.2968% | Total number of lamprey that entered any BON fishway | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | Total number of lamprey that entered any BON fishway | Low | Low | Low | Med | Med | Med | High | High | High | Low | Low | Low | Med | Med | Med | High | High | High
P:med | C:low | 0.01023% | 0.4435% | 0.05759% | 0.1797% | 0.4717% | 0.03055% | 0.1342% | 0.335% | [56 empty] | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High | Low | Med | High
P:high | C:low | 0.1675% | 0.7696% | 0.1319% | 0.3373% | 0.6239% | 0.08233% | 0.1487% | 0.3732% | Baseline: dam passage efficiency (all routes)1 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | Baseline: dam passage efficiency (all routes)1 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
P:low | C:med | -0.4413% | 0.2348% | -0.05016% | 0.0662% | 0.4793% | -0.06369% | 0.3591% | 0.8903% | Baseline: dam passage (n) all routes | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | Baseline: dam passage (n) all routes
P:med | C:med | 0.03068% | 0.887% | 0.1728% | 0.539% | 0.7076% | 0.09165% | 0.4027% | 1.005% | [56 empty] | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506 | 0.506
P:high | C:med | 0.5026% | 1.539% | 0.3957% | 1.012% | 0.9359% | 0.247% | 0.4462% | 1.12% | Baseline: Proportion of lamprey detected at proposed site2 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.188 | 0.398 | 0.398 | 0.398 | 0.398 | 0.398 | 0.398 | 0.398 | 0.398 | 0.398 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.319 | 0.319 | 0.319 | 0.319 | 0.319 | 0.319 | 0.319 | 0.319 | 0.319 | 0.077 | 0.077 | 0.077 | 0.077 | 0.077 | 0.077 | 0.077 | 0.077 | 0.077 | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | 0.131 | Baseline: Proportion of lamprey detected at proposed site2 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600 | 50600
P:low | C:high | -0.8825% | 0.3522% | -0.1003% | 0.1103% | 0.6391% | -0.1274% | 0.7182% | 1.781% | Baseline: proportion of lamprey detected at proposed site that eventually passed the dam2 | 0.445 | 0.445 | 0.445 | 0.445 | 0.445 | 0.445 | 0.445 | 0.445 | 0.445 | 0.587 | 0.587 | 0.587 | 0.587 | 0.587 | 0.587 | 0.587 | 0.587 | 0.587 | 0.782 | 0.782 | 0.782 | 0.782 | 0.782 | 0.782 | 0.782 | 0.782 | 0.782 | 0.793 | 0.793 | 0.793 | 0.793 | 0.793 | 0.793 | 0.793 | 0.793 | 0.793 | 0.695 | 0.695 | 0.695 | 0.695 | 0.695 | 0.695 | 0.695 | 0.695 | 0.695 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | 0.482 | Baseline: proportion of lamprey detected at proposed site that eventually passed the dam2
P:med | C:high | 0.06135% | 1.33% | 0.3455% | 0.8984% | 0.9435% | 0.1833% | 0.8053% | 2.01% | Baseline: Number of lamprey expected near proposed site | 18800 | 18800 | 18800 | 18800 | 18800 | 18800 | 18800 | 18800 | 18800 | 39800 | 39800 | 39800 | 39800 | 39800 | 39800 | 39800 | 39800 | 39800 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | 31900 | 31900 | 31900 | 31900 | 31900 | 31900 | 31900 | 31900 | 31900 | 7700 | 7700 | 7700 | 7700 | 7700 | 7700 | 7700 | 7700 | 7700 | 13100 | 13100 | 13100 | 13100 | 13100 | 13100 | 13100 | 13100 | 13100 | Baseline: Number of lamprey expected near proposed site | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.147 | 0.387 | 0.387 | 0.387 | 0.387 | 0.387 | 0.387 | 0.387 | 0.387 | 0.387 | Lots of fish at the south corner, but LPS siting probably a challenge
P:high | C:high | 1.005% | 2.309% | 0.7914% | 1.686% | 1.248% | 0.494% | 0.8925% | 2.239% | Baseline: Number of lamprey expected to pass dam of those detected at proposed site (no LPS) | 8366 | 8366 | 8366 | 8366 | 8366 | 8366 | 8366 | 8366 | 8366 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 23362.6 | 25806 | 25806 | 25806 | 25806 | 25806 | 25806 | 25806 | 25806 | 25806 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 25296.7 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 5351.5 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | 6314.2 | Baseline: Number of lamprey expected to pass dam of those detected at proposed site (no LPS) | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.412 | 0.412 | 0.412 | 0.412 | 0.412 | 0.412 | 0.412 | 0.412 | 0.412 | Fish detected at either SDE or SUE do relatively poorly (0.39-0.41 versus 0.51 dam-wide)
| Mean | 0.03408% | 0.887% | 0.192% | 0.539% | 0.7076% | 0.1018% | 0.4474% | 1.117% | [56 empty] | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 14700 | 38700 | 38700 | 38700 | 38700 | 38700 | 38700 | 38700 | 38700 | 38700
| Max | 1.005% | 2.309% | 0.7914% | 1.686% | 1.248% | 0.494% | 0.8925% | 2.239% | Estimated collection efficiency of new LPS at proposed site | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.05 | 0.05 | 0.05 | 0.15 | 0.15 | 0.15 | 0.25 | 0.25 | 0.25 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | Estimated collection efficiency of new LPS at proposed site | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 5703.6 | 15944.4 | 15944.4 | 15944.4 | 15944.4 | 15944.4 | 15944.4 | 15944.4 | 15944.4 | 15944.4
| Min | -0.8825% | 0.1174% | -0.1003% | 0.02207% | 0.3196% | -0.1274% | 0.1197% | 0.2968% | Estimated passage efficiency of new LPS at proposed site | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | 0.4 | 0.6 | 0.8 | Estimated passage efficiency of new LPS at proposed site
| Rank | 5 | 1 | 4 | 3 | 2 | 6 | NR | NR | [56 empty] | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.06 | These collection efficiencies are pretty conservative - you can get some big benefits by bumping these up
[10 empty] | Estimate: Number of lamprey collected by new LPS | 188 | 188 | 188 | 564 | 564 | 564 | 1128 | 1128 | 1128 | 398 | 398 | 398 | 1194 | 1194 | 1194 | 2388 | 2388 | 2388 | 3300 | 3300 | 3300 | 6600 | 6600 | 6600 | 9900 | 9900 | 9900 | 1595 | 1595 | 1595 | 4785 | 4785 | 4785 | 7975 | 7975 | 7975 | 1540 | 1540 | 1540 | 2310 | 2310 | 2310 | 3080 | 3080 | 3080 | 131 | 131 | 131 | 393 | 393 | 393 | 786 | 786 | 786 | Estimate: Number of lamprey collected by new LPS | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9 | 0.8 | 0.85 | 0.9
[10 empty] | Estimate: Number of lamprey not collected by new LPS | 18612 | 18612 | 18612 | 18236 | 18236 | 18236 | 17672 | 17672 | 17672 | 39402 | 39402 | 39402 | 38606 | 38606 | 38606 | 37412 | 37412 | 37412 | 29700 | 29700 | 29700 | 26400 | 26400 | 26400 | 23100 | 23100 | 23100 | 30305 | 30305 | 30305 | 27115 | 27115 | 27115 | 23925 | 23925 | 23925 | 6160 | 6160 | 6160 | 5390 | 5390 | 5390 | 4620 | 4620 | 4620 | 12969 | 12969 | 12969 | 12707 | 12707 | 12707 | 12314 | 12314 | 12314 | Estimate: Number of lamprey not collected by new LPS
[66 empty] | 147 | 147 | 147 | 441 | 441 | 441 | 882 | 882 | 882 | 387 | 387 | 387 | 1161 | 1161 | 1161 | 2322 | 2322 | 2322
[10 empty] | Estimate: Number of lamprey collected by new LPS that pass dam | 75.2 | 112.8 | 150.4 | 225.6 | 338.4 | 451.2 | 451.2 | 676.8 | 902.4 | 159.2 | 238.8 | 318.4 | 477.6 | 716.4 | 955.2 | 955.2 | 1432.8 | 1910.4 | 2640 | 2805 | 2970 | 5280 | 5610 | 5940 | 7920 | 8415 | 8910 | 1276 | 1355.75 | 1435.5 | 3828 | 4067.25 | 4306.5 | 6380 | 6778.75 | 7177.5 | 1232 | 1309 | 1386 | 1848 | 1963.5 | 2079 | 2464 | 2618 | 2772 | 52.4 | 78.6 | 104.8 | 157.2 | 235.8 | 314.4 | 314.4 | 471.6 | 628.8 | Estimate: Number of lamprey collected by new LPS that pass dam | 14553 | 14553 | 14553 | 14259 | 14259 | 14259 | 13818 | 13818 | 13818 | 38313 | 38313 | 38313 | 37539 | 37539 | 37539 | 36378 | 36378 | 36378
[10 empty] | Estimate: Number of lamprey not collected by new LPS that pass dam | 8282.34 | 8282.34 | 8282.34 | 8115.02 | 8115.02 | 8115.02 | 7864.04 | 7864.04 | 7864.04 | 23128.974 | 23128.974 | 23128.974 | 22661.722 | 22661.722 | 22661.722 | 21960.844 | 21960.844 | 21960.844 | 23225.4 | 23225.4 | 23225.4 | 20644.8 | 20644.8 | 20644.8 | 18064.2 | 18064.2 | 18064.2 | 24031.865 | 24031.865 | 24031.865 | 21502.195 | 21502.195 | 21502.195 | 18972.525 | 18972.525 | 18972.525 | 4281.2 | 4281.2 | 4281.2 | 3746.05 | 3746.05 | 3746.05 | 3210.9 | 3210.9 | 3210.9 | 6251.058 | 6251.058 | 6251.058 | 6124.774 | 6124.774 | 6124.774 | 5935.348 | 5935.348 | 5935.348 | Estimate: Number of lamprey not collected by new LPS that pass dam
[10 empty] | Estimate: Combined passage | 8357.54 | 8395.14 | 8432.74 | 8340.62 | 8453.42 | 8566.22 | 8315.24 | 8540.84 | 8766.44 | 23288.174 | 23367.774 | 23447.374 | 23139.322 | 23378.122 | 23616.922 | 22916.044 | 23393.644 | 23871.244 | 25865.4 | 26030.4 | 26195.4 | 25924.8 | 26254.8 | 26584.8 | 25984.2 | 26479.2 | 26974.2 | 25307.865 | 25387.615 | 25467.365 | 25330.195 | 25569.445 | 25808.695 | 25352.525 | 25751.275 | 26150.025 | 5513.2 | 5590.2 | 5667.2 | 5594.05 | 5709.55 | 5825.05 | 5674.9 | 5828.9 | 5982.9 | 6303.458 | 6329.658 | 6355.858 | 6281.974 | 6360.574 | 6439.174 | 6249.748 | 6406.948 | 6564.148 | Estimate: Combined passage | 117.6 | 124.95 | 132.3 | 352.8 | 374.85 | 396.9 | 705.6 | 749.7 | 793.8 | 309.6 | 328.95 | 348.3 | 928.8 | 986.85 | 1044.9 | 1857.6 | 1973.7 | 2089.8
[10 empty] | Estimate: Change in passage as a result of new LPS (n) | -8.46 | 29.14 | 66.74 | -25.38 | 87.42 | 200.22 | -50.76 | 174.84 | 400.44 | -74.426 | 5.174 | 84.774 | -223.278 | 15.522 | 254.322 | -446.556 | 31.044 | 508.644 | 59.4 | 224.4 | 389.4 | 118.8 | 448.8 | 778.8 | 178.2 | 673.2 | 1168.2 | 11.165 | 90.915 | 170.665 | 33.495 | 272.745 | 511.995 | 55.825 | 454.575 | 853.325 | 161.7 | 238.7 | 315.7 | 242.55 | 358.05 | 473.55 | 323.4 | 477.4 | 631.4 | -10.742 | 15.458 | 41.658 | -32.226 | 46.374 | 124.974 | -64.452 | 92.748 | 249.948 | Estimate: Change in passage as a result of new LPS (n) | 5646.564 | 5646.564 | 5646.564 | 5532.492 | 5532.492 | 5532.492 | 5361.384 | 5361.384 | 5361.384 | 15784.956 | 15784.956 | 15784.956 | 15466.068 | 15466.068 | 15466.068 | 14987.736 | 14987.736 | 14987.736
[10 empty] | Estimate: 'New' dam-wide passage (n) | 50591.54 | 50629.14 | 50666.74 | 50574.62 | 50687.42 | 50800.22 | 50549.24 | 50774.84 | 51000.44 | 50525.574 | 50605.174 | 50684.774 | 50376.722 | 50615.522 | 50854.322 | 50153.444 | 50631.044 | 51108.644 | 50659.4 | 50824.4 | 50989.4 | 50718.8 | 51048.8 | 51378.8 | 50778.2 | 51273.2 | 51768.2 | 50611.165 | 50690.915 | 50770.665 | 50633.495 | 50872.745 | 51111.995 | 50655.825 | 51054.575 | 51453.325 | 50761.7 | 50838.7 | 50915.7 | 50842.55 | 50958.05 | 51073.55 | 50923.4 | 51077.4 | 51231.4 | 50589.258 | 50615.458 | 50641.658 | 50567.774 | 50646.374 | 50724.974 | 50535.548 | 50692.748 | 50849.948 | Estimate: 'New' dam-wide passage (n) | 5764.164 | 5771.514 | 5778.864 | 5885.292 | 5907.342 | 5929.392 | 6066.984 | 6111.084 | 6155.184 | 16094.556 | 16113.906 | 16133.256 | 16394.868 | 16452.918 | 16510.968 | 16845.336 | 16961.436 | 17077.536
[10 empty] | Estimate: 'New' dam-wide passage efficiency | 0.50592 | 0.50629 | 0.50667 | 0.50575 | 0.50687 | 0.508 | 0.50549 | 0.50775 | 0.51 | 0.50526 | 0.50605 | 0.50685 | 0.50377 | 0.50616 | 0.50854 | 0.50153 | 0.50631 | 0.51109 | 0.50659 | 0.50824 | 0.50989 | 0.50719 | 0.51049 | 0.51379 | 0.50778 | 0.51273 | 0.51768 | 0.50611 | 0.50691 | 0.50771 | 0.50633 | 0.50873 | 0.51112 | 0.50656 | 0.51055 | 0.51453 | 0.50762 | 0.50839 | 0.50916 | 0.50843 | 0.50958 | 0.51074 | 0.50923 | 0.51077 | 0.51231 | 0.50589 | 0.50615 | 0.50642 | 0.50568 | 0.50646 | 0.50725 | 0.50536 | 0.50693 | 0.5085 | Estimate: 'New' dam-wide passage efficiency | 60.564 | 67.914 | 75.264 | 181.692 | 203.742 | 225.792 | 363.384 | 407.484 | 451.584 | 150.156 | 169.506 | 188.856 | 450.468 | 508.518 | 566.568 | 900.936 | 1017.036 | 1133.136
[66 empty] | 50660.564 | 50667.914 | 50675.264 | 50781.692 | 50803.742 | 50825.792 | 50963.384 | 51007.484 | 51051.584 | 50750.156 | 50769.506 | 50788.856 | 51050.468 | 51108.518 | 51166.568 | 51500.936 | 51617.036 | 51733.136
[10 empty] | Estimate: Change in dam-wide passage efficiency | -8.46e-05 | 0.0002914 | 0.0006674 | -0.0002538 | 0.0008742 | 0.0020022 | -0.0005076 | 0.0017484 | 0.0040044 | -0.00074426 | 5.174e-05 | 0.00084774 | -0.0022328 | 0.00015522 | 0.0025432 | -0.0044656 | 0.00031044 | 0.0050864 | 0.000594 | 0.002244 | 0.003894 | 0.001188 | 0.004488 | 0.007788 | 0.001782 | 0.006732 | 0.011682 | 0.00011165 | 0.00090915 | 0.0017067 | 0.00033495 | 0.0027274 | 0.0051199 | 0.00055825 | 0.0045458 | 0.0085332 | 0.001617 | 0.002387 | 0.003157 | 0.0024255 | 0.0035805 | 0.0047355 | 0.003234 | 0.004774 | 0.006314 | -0.00010742 | 0.00015458 | 0.00041658 | -0.00032226 | 0.00046374 | 0.0012497 | -0.00064452 | 0.00092748 | 0.0024995 | Estimate: Change in dam-wide passage efficiency | 0.50661 | 0.50668 | 0.50675 | 0.50782 | 0.50804 | 0.50826 | 0.50963 | 0.51007 | 0.51052 | 0.5075 | 0.5077 | 0.50789 | 0.5105 | 0.51109 | 0.51167 | 0.51501 | 0.51617 | 0.51733
[10 empty] | Estimate: % Change in efficiency over baseline | -0.01672% | 0.05759% | 0.1319% | -0.05016% | 0.1728% | 0.3957% | -0.1003% | 0.3455% | 0.7914% | -0.1471% | 0.01023% | 0.1675% | -0.4413% | 0.03068% | 0.5026% | -0.8825% | 0.06135% | 1.005% | 0.1174% | 0.4435% | 0.7696% | 0.2348% | 0.887% | 1.539% | 0.3522% | 1.33% | 2.309% | 0.02207% | 0.1797% | 0.3373% | 0.0662% | 0.539% | 1.012% | 0.1103% | 0.8984% | 1.686% | 0.3196% | 0.4717% | 0.6239% | 0.4793% | 0.7076% | 0.9359% | 0.6391% | 0.9435% | 1.248% | -0.02123% | 0.03055% | 0.08233% | -0.06369% | 0.09165% | 0.247% | -0.1274% | 0.1833% | 0.494% | Estimate: % Change in efficiency over baseline
[66 empty] | 0.00060564 | 0.00067914 | 0.00075264 | 0.0018169 | 0.0020374 | 0.0022579 | 0.0036338 | 0.0040748 | 0.0045158 | 0.0015016 | 0.0016951 | 0.0018886 | 0.0045047 | 0.0050852 | 0.0056657 | 0.0090094 | 0.01017 | 0.011331
[10 empty] | 1 Source: Table 1 in Keefer et al. (2013); annual range = 0.46-0.57 | 0.4: * Collection efficiency: based loosely on Casc Island LPS | * Collection efficiency: based loosely on Casc Island LPS | [8 empty] | * Collection efficiency: guess that higher than CI LPS but lower than AWS channels | [8 empty] | * Collection efficiency: guess that lower than AWS channels and lower than channel above UMT | [8 empty] | * Collection efficiency: equivalent to AWS LPS (note: could go higher, potentially) | [8 empty] | * Collection efficiency: based loosely on existing Casc Island LPS (i.e., new south side would collect same proportion as existing north side LPS) | [9 empty] | 0.1197% | 0.1342% | 0.1487% | 0.3591% | 0.4027% | 0.4462% | 0.7182% | 0.8053% | 0.8925% | 0.2968% | 0.335% | 0.3732% | 0.8903% | 1.005% | 1.12% | 1.781% | 2.01% | 2.239%
[10 empty] | 2 Source: 10 years of RT data (annual estimates are possible) | 0.4: * Passage efficiency: based loosely on Casc Island LPS | * Passage efficiency: based loosely on Casc Island LPS | [8 empty] | * Passage efficiency: guess that slightly lower than AWS channels | [8 empty] | * Passage efficiency: guess that slightly lower than AWS channels | [8 empty] | * Passage efficiency: equivalent to AWS LPS | [8 empty] | * Passage efficiency: based loosely on existing Casc Island LPS
[66 empty] | * Collection efficiency: based loosely on Casc Island LPS | [8 empty] | * Collection efficiency: based loosely on Casc Island LPS
[66 empty] | * Passage efficiency: equivalent to AWS LPS | [8 empty] | * Passage efficiency: equivalent to AWS LPS

## JDA North Collection #s
2014 JDA North LPS Collection
DATE | TOTAL # COLLECTED | # OF RECAPS | DART LADDER COUNTS | COMMENTS
2014-06-25 | 0 | 0 | 39 | LPS FIRED UP!!!
2014-06-26 | 18 | 1 | 36 | Recap was MAK flume fish released at 17:20
2014-06-27 | 41 | 0 | 37
2014-06-28 | 82 | 1 | 44 | Recap was MAK flume fish released at 18:00
2014-06-29 | 91 | 1 | 73 | Recap was MAK flume fish releaed at 16:00
2014-06-30 | 67 | 2 | 67 | Both recaps were MAK flume fish released at 16:00
2014-07-01 | 31 | 1 | 83 | Recap was HD-PIT onl yfish released at 15:20
2014-07-02 | 39 | 1 | 93 | Recap was MAK flume fish
2014-07-03 | 59 | 0 | 115
2014-07-04 | 19 | 0 | 81 | All 19 fish were PIT-tagged and released at 12:20
2014-07-05 | 16 | 1 | 91 | 14 fish PIT-tagged, one was lethargic and went untagged. Recap released @11:45
2014-07-06 | 19 | 0 | 139
2014-07-07 | 3 | 0 | 128 | Supply pipe broke sometime in the AM, fish recovered by Corps bios and released in forebay. Pump is off, will repair on Tuesday.
2014-07-08 | 0 | 0 | 109 | Pipe repaired, but everything smelled strongly of glue. Will turn pumps back on Wednesday morning.
2014-07-09 | 0 | 0 | 117 | LPS FIRED BACK UP!!!
2014-07-10 | 27 | 0 | 275
2014-07-11 | 35 | 3 | 211 | TWO RECAPS WERE MAK/FLUME FISH, ONE WAS 2013 TAGGED FISH
2014-07-12 | 31 | 0 | 216
2014-07-13 | 25 | 0 | 204
2014-07-14 | 27 | 0 | 261 | No recaps; All 27 fish were PIT-tagged
2014-07-15 | 20 | 2 | 225 | TWO RECAPS. ONE WAS MAK/FLUME FISH, OTHER ONE WAS 2013 TAGGED FISH RELEASED @ 15:39
2014-07-16 | 9 | 1 | 210 | RELEASE 13:56
2014-07-17 | 32 | 0 | 223 | 32 fish to USFW, unsure how many tagged by them.
2014-07-18 | 9 | 0 | 147 | all 9 to USFWS
2014-07-19 | 20 | 0 | 126 | all released in forebay
2014-07-20 | 29 | 0 | 116 | all released in forebay
2014-07-21 | 32 | 0 | 160 | Tagged 10 PIT-only, 20 to USFWS, 2 released
2014-07-22 | 33 | 0 | 161 | 10 hdx, 20 to usfw, 3 released
2014-07-23 | 7 | 0 | 117 | all released in forebay
2014-07-24 | 17 | 0 | 82 | 14 HDX, 3 USFW
2014-07-25 | 35 | 0 | 90 | 20 TO FWS, 15 TO FBAY RELEASE
2014-07-26 | 27 | 0 | 159 | all released in forebay
2014-07-27 | 11 | 0 | 114 | all released in forebay, 13:05
2014-07-28 | 9 | 0 | 145 | ALL RELEASED TO FOREBAY
2014-07-29 | 29 | 2 | 149 | 25 TO FISH AND WILDLIFE, 4 RELEASED INTO FOREBAY
2014-07-30 | 27 | 0 | 133 | All released to forebay
2014-07-31 | 18 | 0 | 203 | 18 to USFW
2014-08-01 | 22 | 0 | 118 | 20 to USFW, 2 released in forebay
2014-08-02 | 6 | 0 | 162 | all released to forebay
2014-08-03 | 8 | 0 | 120 | all released to forebay
2014-08-04 | 8 | 0 | 90 | all to USFWS
2014-08-05 | 14 | 0 | 76 | All released to forebay (No USFW around to pick up…)
2014-08-06 | 11 | 0 | 112 | all released to forebay
2014-08-07 | 8 | 0 | 138 | all to USFWS
2014-08-08 | 9 | 0 | 106 | all to USFWS
2014-08-09 | 6 | 0 | 65 | RELEASED TO FOREBAY
2014-08-10 | 4 | 1 | 46 | RELEASED TO FOREBAY, 000.000183220904
2014-08-11 | 2 | 0 | 51 | all to USFWS
2014-08-12 | 11 | 0 | 92 | No usfw yesterday so yesterday's fish released in forebay, today's fish released in forebay
2014-08-13 | 9 | 0 | 112 | RELEASED TO FOREBAY
2014-08-14 | 14 | 0 | 115 | all released to forebay
2014-08-15 | 8 | 0 | 74 | all to USFWS
2014-08-16 | 3 | 0 | 40 | RELEASED TO FOREBAY
2014-08-17 | 0 | 0 | 67
2014-08-18 | 7 | 0 | 56 | RELEASED TO FOREBAY
2014-08-19 | 9 | 0 | 47 | RELEASED TO FOREBAY
2014-08-20 | 4 | 0 | 54 | RELEASED TO FOREBAY
2014-08-21 | 2 | 0 | 52 | released to forebay
2014-08-22 | 2 | 0 | 88 | released to forebay
2014-08-23 | 4 | 0 | 60 | released to forebay
2014-08-24 | 4 | 0 | 50 | released to forebay
2014-08-25 | 4 | 0 | 58 | released to forebay
2014-08-26 | 4 | 0 | 64 | given to usfw
2014-08-27 | 1 | 0 | 29 | given to usfw
2014-08-28 | 6 | 0 | 53 | released to forebay
2014-08-29 | 5 | 0 | 36 | all to USFWS
2014-08-30 | 10 | 0 | 62 | released to forebay
2014-08-31 | 11 | 0 | 27 | released to forebay
2014-09-01 | 3 | 0 | 38 | released to forebay
2014-09-02 | 0 | 0 | 61
2014-09-03 | 0 | 0 | 60
2014-09-04 | 2 | 0 | 36 | released to forebay
2014-09-05 | 0 | 0 | 21
2014-09-06 | 1 | 0 | 32 | released to forebay
2014-09-07 | 0 | 0 | 12
1900-09-08 | 0 | 0 | 26
1900-09-09 | 0 | 0 | 26
1900-09-10 | 0 | 0 | 40
1900-09-11 | 2 | 0 | 24 | released to forebay
1900-09-12 | 0 | 0 | 26
1900-09-13 | 0 | 0 | 33
1900-09-14 | 0 | 0 | 12
1900-09-15 | 1 | 0 | 42 | given to USFWS
1900-09-16 | 3 | 0 | 12 | given to USFWS
1900-09-17 | 2 | 0 | 30 | GIVEN TO USFWS
1900-09-18 | 0 | 0 | 18
2014-09-19 | 0 | 0 | 49
2014-09-20 | 2 | 0 | 41 | released to forbay
2014-09-21 | 0 | 0 | 24
2014-09-22 | 0 | 0
2014-09-23 | 0 | 0 | 11
2014-09-24 | 0 | 0 | 23
2014-09-25 | 0 | 0 | 17
2014-09-26 | 0 | 0 | 29
2014-09-27 | 0 | 0 | 14
2014-09-28 | 0 | 0 | 23
2014-09-29 | 2 | 0 | 17 | released to forbay
2014-09-30 | 0 | 0 | 29
2014-10-01 | 0 | 0 | 10 | LPS shutdown
TOTAL | 1228 | 17 | 8135