USACE Portland District (NWP) FFDRWG Update Form
April 6, 2017

PROJECT INFORMATION

| Project Title | Lamprey Passage Structure (LPS) Development and Improvements |
| --- | --- |
| SCT Reference Number |  |
| Project Manager (PM) | Mike Turaski (NWP, 503-808-4704) |
| Technical Lead (TL) | James Schroeder (NWP 503-808-4930) |
| Biologist/Coordination | Ricardo Walker (NWP, 503-808-4709) |

PROJECT DESCRIPTION

This project consists of the design, construction, and modification of LPSs at BON and JDA.

Specific tasks (pending funding availability and prioritization) include the following:

- Design, build, and or modify LPSs that address known problem areas:

  - BON Washington Shore Fish Ladder – Install 2 new ramps in the channel between the UMT junction and count station, as a means of reducing the use of the serpentine weir section. Completed IWW 16/17.

  - BON Bradford Island Fish Ladder –  Upgrade to LPS exit chute (currently in the 90% design process; construction IWW 17/18)

  - BON Cascades Island Fish Ladder – Only minor modifications to the LPS as outlined under bullet 2.

  - JDA North Fish Ladder – Extend entrance LPS to the 2nd 180 degree turning pool (Design late FY17; Construction IWW 18/19).

- Complete minor modifications to existing LPSs to improve O&M functionality:

  - Inspect structures and modify as necessary to minimize risk of structural failures.

  - Modify or replace pumps and pump intakes, as necessary, to meet juvenile salmon fry criteria, accommodate maintenance needs, and provide sufficient water supply for systems.

  - Improve counting systems for existing LPSs.

  - Improve electrical and plumbing systems (as needed) for existing LPSs.

  - Install full duplex systems at the LPS exits.

PROGRESS AND KEY ISSUES (List)

BON WA Shore

- BON Washington shore fish ladder LFS fixes and LPS install have been completed (16/17 winter maintenance period).

- Maintenance of the existing LPS half duplex PIT infrastructure in 16/17 (at BON WA shore fish ladder) for a follow on evaluation of the new LPS structures in FY 18/19.

BON Bradford Island and Cascades Island

- Currently the BCOES package is being developed and will be made available for FFDRWG review mid-April.

CURRENT SCHEDULE

- BCOES review to start ~ 10 April 2017.

- Schedule for installation is 17/18 winter maintenance period.

FFDRWG REVIEW NEEDED AT MEETING?  (If YES, list discussion topics below)

- No