USACE Portland District (NWP) FFDRWG Update Form
7 Sep 2017

PROJECT INFORMATION

| Project Title | JDA Avian Array |
| --- | --- |
| SCT Reference Number |  |
| Project Manager (PM) | George Medina (NWP, 503-808-4753) |
| Technical Leads (TL’s) | Lindsey Roth (503-808-4985) |
| Biologist/Coordination | Jake Macdonald (NWP, 503-808-4844) |

PROJECT DESCRIPTION

This project is for the repair/upgrade of the John Day Avian Array system. The work consist of installing/replacing sixty (60) Vectran synthetic ropes spanning the Columbia River, incorporating a new wire rope sling design such that shackle twisting is minimized, and adding a sheave and winch to nineteen (19) spillway towers so that operations personnel can tension lines. Structural welding of carbon steel and cold galvanizing of affected components is required.  The project requires splicing and rigging high strength synthetic rope for a marine application. There is a requirement that potential contractors possess an AWS D1.1 certification for this project.

The work is required to be carried out between November 24, 2017, and June 30, 2018. The in-water work shall occur between December 1, 2017, and February 28, 2018.

CURRENT SCHEDULE

| Tasks |  | Target Dates |
| --- | --- | --- |
| Complete Market Research |  | 4/10/2017 |
| P&S approved |  | 6/08/2017 |
| Complete Requirements Documents Rec'd by CT |  | 6/29/2017 |
| Issue Pre-Solicitation Notice |  | 7/03/2017 |
| Issue Solicitation |  | 7/19/2017 |
| Bids/Proposals Due |  | 8/21/2017 |
| Source Selection Board Start (if applicable) |  | 9/05/2017 |
| Approved Source Selection Report (if applicable) |  | 10/19/2017 |
| Public Notification (>$7M) |  | N/A |
| Award Date |  | 11/16/2017 |

PROGRESS AND KEY ISSUES (List)

No issues

FFDRWG REVIEW NEEDED AT MEETING?  (If YES, list discussion topics below)