# Lower Columbia River Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# June 2022 DRAFT Meeting Notes

June 2, 2022 09:00-11:00

## FFDRWG meeting Files

http://pweb.crohms.org/tmt/documents/FPOM/2010/FFDRWG/2022%20FFDRWG/

## Introductions

FFDRWG members:

BPA

Scott Bettin

Kim Johnson

Siena Lopez-Johnston

*Christine Petersen

Greg Smith

Leah Sullivan

*Ben Hausmann

NOAA

*Blane Bellerud

*Gabriel Brooks

*Trevor Conder

Kinsey Frick

Claire McGrath

Josie Thompson

Logan Negherbon

Kelsey Swieca

USFWS

*Dave Swank

*Shelby Fowler

States

*Erick Van Dyke (ODFW)

*Charles Morrill (WDFW)

Jonathan Ebel (IDFG)

CRITFC/Tribes

*Tom Lorz (CRITFC)

Blaine Parker (CRITFC)

Tom Skiles (CRITFC)

*Laurie Porter (CRITFC)

*Greg Silver (CRITFC)

Casey Baldwin (CTCR)

Michael Karnosh (CTGR)

Lawrence Schwabe (CTGR)

Torey Wakeland (CTGR)

Aaron Jackson (CTUIR)

Ralph Lampman (YN)

NPCC

Leslie Bach

Kris Homel

FPC

*Erin Cooper

PSMFC

*Alan Brower

Darren Chase

Roger Clark

Mark Leonard

Scott Livingston

Nicole Tancreto

Don Warf

CENWD

*Doug Baus

Tim Dykstra

Dan Feil

Mike Langeslay

Cindy Studebaker

*Lisa Wright

CENWW

Chris Peery

Steve Juhnke

CENWP-OD

Andrew Derugin

Rebecca Cates

Jeanette Wendler

Tucker Gossett

Bob Cordie

Jeffrey Randall

Eric Grosvenor

Michael Lotspeich

Laura Rickets

Tammy Mackey

Robert Wertheimer

Patricia Madson

*Darren Gallion

CENWP-PM

Jim Adams

Ian Chane

Jeff Hicks

Steve Sipe

Jeremiah Woodard

Erin Kovalchuk

Mark Bierman

*Brad Eppard

*Nathan McClain

*Jake Macdonald

*Jon Rerecich

*Ida Royer

David Trachtenbarg

*Scott Fielding

CENWP-ENC

*Adam White

Brandt Bannister

Bridget Bell

*Shari Dunlop

Curtis Lipski

Chris Motti

*Steve Schlenker

*Max Wilson-Fey

Collin Porter

Dan Penn

*Present

## Action items from previous meetings

- Corps will present The Dalles backup AWS debris management alternatives at an upcoming FFDRWG

  - EDR shelved at 50% with no funding in FY 22.  The Corps will walk through alternatives with FFDRWG at 60% (when the project resumes)

## Topics for FFDRWG Discussion/Review/Coordination

BON2 FGE  – Jim Adams (PM), Max Wilson-Fey (TL), Jon Rerecich (FC)

  - Update on hydraulic testing – Wilson-Fey

    - Final week of testing began yesterday 6/1, will finish 6/9

    - Preliminary results toward the end of June will give us an idea but the final go-ahead for construction in additional units will happen in August.  Plenty of time before the next construction window in December.

    - See schedule for additional units in written update below.

    - ACTION: B2 FGE PDT (Max Wilson-Fey) will present preliminary hydraulic testing results at the 7/7 FFDRWG meeting.

JDA adult lamprey passage improvements – Jeremiah Woodard (PM), Adam White (TL), Jake Macdonald (FC)

  - North Fish Ladder LPS 60% Design Documentation Report (DDR) – White

    - 60% DDR available for FFDRWG review on the meeting files website

    - In-house construction, no 90% DDR and no BCOES, straight from 60% to 100%.  Construction in Winter 2022-2023.

    - Plan in hand meeting with John Day staff on May 10th.

    - Beginning to procure materials for construction this Winter.

TDA adult lamprey passage improvements – Jeremiah Woodard (PM), Adam White (TL), Jake Macdonald (FC)

  - Exit weirs 154-157 modifications for lamprey passage – White

    - See attached “TDA Exit Weir Mods Markup_CP Edits.pdf” with 3 options (really 2.5)

    - PDT recommends option #1 (cut lamprey orifices at the bottom corners of the weirs) because we’re certain that option won’t upset the hydraulic conditions of the ladder.

    - FFDRWG recommends option #3 (spacer attached to the bottom of the weirs) because it’s the simplest option and easiest to reverse.

    - PDT agrees the temporary nature of option #3 is appealing.

    - ACTION: TDA lamprey PDT will discuss FFDRWG’s recommended option for exit weirs 154-157 and Adam White will report any significant developments at the 7/7 FFDRWG meeting.

BON1 adult lamprey passage improvements – Jeremiah Woodard (PM), Adam White (TL), Andrew Derugin (FC)

  - B-branch entrance LPS gravity feed water supply update – Derugin/White

    - PDT is refining water supply intake details for 90% DDR, due in August.

Other topics

  - New member

    - Welcome Shelby Fowler, hydraulic engineer for U.S. Fish & Wildlife Service.

  - John Day Ladder Cooling

    - The Corps has a small capability in FY24 tied to this project. This was intended to be for a data analysis. Future efforts may be included in the FY25 budget request. Trevor Conder (NOAA) wants to keep it in the conversation until then.

    - ACTION: Jake Macdonald will add John Day ladder cooling as a standing topic on the FFDRWG agenda

    - ACTION: Scott Fielding will convene a special FFDRWG meeting to discuss the available data for JDA ladder cooling. This discussion will help determine the path forward on design and construction of a ladder cooling structure prior to the FY25 budget request submission in December 2022.

  - Bonneville 1PH ice & trash PIT detection

    - Charles Morrill (WDFW) and others are disappointed the Corps is not able to install PIT detection in the BON 1st powerhouse ice & trash sluiceway intakes at this time.  Would like to see higher priority given to shovel-ready projects to increase juvenile detections.

  - Trevor Conder (NOAA) asked for clarification on CRFM funding priorities.  Can we redirect funding from lower priority projects to higher priority projects in a given year?

    - Yes, usually.  The Corps budget process recognizes that priorities can change in the three years between requesting funding and receiving it.  SCT is the forum where we help the Corps prioritize and reprioritize projects for whatever budget we receive each year.

## Written project updates

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-4-1

# JDA Turbine Rehab

| Project Identifier: | P2 # |
| --- | --- |
| Project Manager (PM): | Steve Sipe (CENWP-PMF-P) Steven.C.Sipe@usace.army.mil |
| Technical Lead (TL): | Curtis Lipski (CENWP-ENC-HD) Curtis.L.Lipski@usace.army.mil |
| FFDRWG Coordination (FL): | Jon Rerecich/Eric Grosvenor (CENWP-PME) Jonathan.G.Rerecich@usace.army.mil/Eric.Grosvenor@usace.army.mil |

## Project Description

The purpose of this project is to address reliability concerns and maximize production of hydroelectric power at JDA, which includes electrical energy production and electrical grid ancillary services while at the same time, improving survival of fish passing through the turbines. Maximum production of hydroelectric power at JDA will be realized through increased reliability and increased efficiency. Reliability improvements will be realized through a combination of replacement and refurbishment of powertrain equipment to include, but not limited to, turbine runners, shafting, generators, isophase bus, breakers, switches, and transformers. Efficiency improvements will be realized through increased turbine efficiencies associated with new turbine runners and other modifications to the turbines.

The purpose of this project is also to increase survival of turbine passed fish. Increased survival of turbine passed fish will be realized through developing state-of-art hydroelectric turbines to obtain improved fish passage survival through the turbines. The design of the state-of-the-art turbines will be an iterative and collaborative process that focuses on fish-friendly design features and criteria. This iterative and collaborative design process will be similar to the ongoing Ice Harbor L&D turbine runner replacement design and upcoming McNary L&D turbine runner replacement in NWW. Phase 1A recommendations include replacing up to 14 units with combination fixed blade & adjustable blade to obtain improved fish passage survival through the turbines.

## Project Schedule

| Phase 1 Short Term Schedule | Start | Finish |
| --- | --- | --- |
| 30% DDR/P&S review | 3/12/2020 | 4/1/2020 |
| 60% DDR/P&S review | 8/28/2020 | 9/18/2020 |
| 90% DDR/P&S review | 9/21/2021 | 2/18/2022 |
| BCOES review | 8/15/2022 | 11/25/2022 |

| Overall Schedule Milestones | Date |
| --- | --- |
| Contract award | August 2024 |
| Collaborative design process model testing | 2024-2029 |
| First unit installation | 2031-2033 |
| Unit installation complete | 2040-2045 |

## Current Status

- The 1:25 scale physical observational turbine model is being used to inform the development of the Phase 1 Plans and Specifications package, to document the hydraulic conditions that affect the biological performance of the existing JDA turbines and will be used to support the collaborative and iterative design process in Phase 2.  Baseline model data collection for Test Series 1 took place from January through June of 2021 with a focus on validating the relocated model and evaluating potential draft tube modifications. The results were used to guide development of the plans and specifications. ERDC prepared a draft data report documenting Test Series 1; this was provided to agency and external partner staff that participate in the PDT in October 2021.  Test Series 2 commenced on March 31, 2022. The focus of Test Series 2 will be data collection to document the baseline hydraulic conditions affecting fish survival within the existing turbine environment (e.g., strike, shear and turbulence).

- The 1:45 JDA general physical model and CFD tailrace model are being used to assess hydraulic conditions affecting juvenile egress and adult approach to the fish ladder entrances. Tailrace flow patterns for both models were validated to a single operating condition in 2020. The physical model was used in 2021 to simulate selected scenarios that had been analyzed using CFD during Phase 1A. The results are currently under review by the PDT.  Model runs will resume after further HAC modeling is complete and preliminary options for the turbine mix are established.

- The PDT is investigating the possibility of going with oil-free hubs for the adjustable-blade units. Working with PNNL to complete bushing and corrosion fatigue testing.

- 90% DQC and NMFS review has been completed.  NMFS had no comment and DQC comments are in review.

## Topics for FFDRWG Review/Coordination

None currently.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-1-28

# TDA Backup AWS Debris Management EDR

| Project Identifier: | P2 # |
| --- | --- |
| Project Manager (PM): | Erin Kovalchuk (CENWP-PMF) Erin.H.Kkovalchuk@usace.army.mil |
| Technical Lead (TL): | Mehdi Roshani (CENWP-ENC) Mehdi.Roshani@usace.army.mil |
| FFDRWG Coordination (FC): | Jon Rerecich (CENWP-PME) Jonathan.G.Rerecich@usace.army.mil |

## Project Description

This project is to evaluate alternatives to remove debris from The Dalles Dam Auxiliary Water Supply (AWS) trash rack. Debris build-up on the rack currently causes high head differential across the rack. Fish Unit Rehab requires the AWS backup system to operate during the rehab to provide adequate flow for fish attraction. Fish Unit Rehab duration is one year per unit for a total of two years. Long term use of the backup AWS system will be part of the alternatives evaluation.

## Project Schedule

| Milestone | Start | End |
| --- | --- | --- |
| Criteria and Constraint Report | 4/19/2021 | 8/6/2021 |
| Value Management | 8/9/2021 | 8/20/2021 |
| Alternative Evaluation Report | 8/23/2021 | ? |
| Draft Final Report | ? | ? |
| ATR | ? | ? |
| Final Report | ? | ? |
| Closeout | ? | ? |

## Current Status

Value Management Study completed.

No Funding in FY 22

Alternative evaluation Engineering Design Report (EDR) shelved at 50%

## Topics for FFDRWG Review/Coordination

PDT will solicit FFDRWG participation at the 60% Engineering Design Report (EDR).

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-4-1

# BON Second Powerhouse FGE

| Project Identifier: | P2 # |
| --- | --- |
| Project Manager (PM): | Jim Adams (CENWP-PMF) James.R.Adams@usace.army.mil |
| Technical Lead (TL): | Max Wilson-Fey (CENWP-ENC) Max.P.Wilson-Fey@usace.army.mil |
| FFDRWG Coordination (FL): | Jon Rerecich (CENWP-PME) Jonathan.G.Rerecich@usace.army.mil |

## Project Description

Steel plates were installed in all units in the A and B gatewells to restrict flow. During routine inspections, however, it became apparent that the anchoring system for the steel plates was inadequate. In effect, the nuts and anchoring bolts holding down the plates had come loose, posing the risk that the plates could detach and potentially take out a unit. All flow restriction plates were removed from the units. A concrete corbel will be installed in the same location as the flow control plates with the design goal to achieve similar gatewell hydraulic conditions as the flow control plates. This new concrete corbel has been designed to meet the flow criteria established and tested for the previous flow restrictor plates to meet the hydraulic and biological goals.

## Project Schedule

| CLIN | Status | Description | Award/Exercise Date | Construction Execution Window |
| --- | --- | --- | --- | --- |
| 1 | Mandatory | Mobilization/Demobilization | Awarded December 2020 | Complete |
| 2 | Mandatory | Unit 15 Construction | Awarded December 2020 | Complete |
| 3 | Optional | Second Mob/Demob and Unit 11 Construction | Awarded August 2021 | Dec 2022-Feb 2023 |
| 4 | Optional | 2 Additional Units | Awarded August 2021 | Extend through May 2023 |
| 5 | Optional | 2 Additional Units | Awarded August 2021 | Extend through August 2023 |
| 6 | Optional | 2 Additional Units (Unit 18 + 1 more Unit) | Awarded August 2021 | Extend through February 2024 |

## Current Status

- Construction in unit 15 is complete.  The contractor did great work, and we had very few RFIs and only one modification.

- Optional construction CLINs were awarded August 2021.  We will modify the dates of execution extending them out a year to allow us to test in the spring of 2022 prior to installing the remaining corbels.

- AE contract for hydraulic testing in Spring 2022 was awarded in September 2021.  Hydraulic tests will be needed in the spring to meet the upper 1% test range of 18.0-18.5 kcfs.

- Original contract schedule said we would continue with units, 12, 13, 14, 16, and 17 and then end with either 11 or 18 the following IWW. However, the contractor thinks they can do both 11 and 18 in the 2022-2023 IWW and then finish with the remaining units throughout the spring/summer. The PDT is confident they can achieve that after how well unit 15 went. We will confirm their schedule after we get the modification in place.

## Topics for FFDRWG Review/Coordination

- FPOM MOC sent on 3/28.  Comments are due by April 11.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# JDA adult lamprey passage improvements

| Project Identifier: | P2 # 492402 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Scott Fielding (CENWP-PME) Scott.D.Fielding@usace.army.mil |

## Project Description

### Modify NFL LPS to increase the capacity and reliability of the system

This is a fish safety/health issue, and the upgrade needs to happen. Current water supply is insufficient so tank cannot be installed without upgraded water supply.  See January 2020 CRS BA § 2.5, pg. 2-85.

- gravity-fed water supply or alternative, more reliable pump configuration.

- larger collection box

### SFL entrance improvements (rounded crest, slot cover/filler)

Caps may not be able to be added to South Ladder entrance weir due to FPP submergence criteria, so the weir may need to be modified more extensively to provide rounded weir crests and guide slot covers.

### SFL count station collection and counting structure (trap) improvements

Increase capacity and efficiency of system by preventing sediment buildup, providing a larger opening into a larger collection box, modified guide, and removal of gate and counting-related structure.

## Project Schedule

Design: FY 2021 – FY 2022

30% DDR – July 2021

60% DDR – November 2021

100% DDR – May 2022

Construction: December 2022 - March 2023

Evaluation/Closeout: FY 2023

## Current Status

100% DDR is underway.  PDT is moving forward with a gravity feed water supply from behind existing picketed leads near the count station via an existing diffuser drain line.  A surplus holding tank at JDA will be modified and relocated to serve as the larger collection box.  All work will be performed by Corps staff, no contracts.

## Topics for FFDRWG Review/Coordination

60% JDA DDR is available on the FFDRWG meeting files website. Because it’s an in-house construction project, there will be no 90% DDR and no BCOES, PDT is advancing straight from 60% to 100%.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# TDA adult lamprey passage improvements

| Project Identifier: | P2 # 492403 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Jacob Macdonald (CENWP-PME) Jacob.Macdonald@usace.army.mil |

## Project Description

### Lamprey collection system (LPS) at the east fish ladder junction pool

Provide a ramp (or multiple) for lamprey to swim out of the junction pool and into a collection box located below the upper segment of the fish ladder for upstream transport. See January 2020 CRS BA § 2.5, pg. 2-85.

### Modify elevated orifices in EFL exit weirs 154-157

Provide better lamprey passage options through the 4 control weirs at the upstream end of the east fish ladder.

### Bulkhead slot covers

Design and install bulkhead slot covers at all four fishway entrances.

## Project Schedule

Design: FY 2021 – FY 2023

30% DDR – August 2021

60% DDR – February 2021

90% DDR – September 2022

BCOES – November 2022

Construction: December 2023 - March 2024

Evaluation/Closeout: FY 2024

## Current Status

90% DDR is underway.  Preferred LPS design includes gravity-fed water supplied from an existing auxiliary penstock in the dam, a large collection box on the deck near the junction pool, and 1-3 climbing ramps reaching down to the fishway floor.

## Topics for FFDRWG Review/Coordination

Lead paint on exit weirs 154-157

- Cannot cut or drill into existing weirs without lead paint remediation

- estimated cost of new weirs = $1 Million, estimated cost to modify existing weirs = $750,000 - $1 Million

- PDT is exploring an option using the existing weirs without modification

60% TDA DDR is available on the FFDRWG meeting files website.  90% will be available in September.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# BON1 adult lamprey passage improvements

| Project Identifier: | P2 # 492400 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Jacob Macdonald (CENWP-PME) Jacob.Macdonald@usace.army.mil |

## Project Description

The project scope is divided into three parts:

### Entrance Modifications

Modify the B-branch fish ladder entrance to improve lamprey passage. This includes a variable-width entrance weir with rounded edges, guide slot fillers or covers to aid lamprey passage along the walls, and bollards on the channel floor for hydraulic refuge.

### Lamprey Collection

Provide an alternate route for lamprey entering the B-branch of the Bradford Island fish ladder. Fish would climb up a flume structure to a holding tank on the deck of the dam and be transported upstream by Tribal fisheries personnel. This will be designed so that in the future we could extend the system to provide volitional passage to the Bonneville forebay.

### Serpentine Section Extensive Minor Mods

Upgrade the serpentine section of the Bradford Island fish ladder to improve lamprey passage by rounding corners, providing refuge boxes, and lamprey orifices.

## Project Schedule

Design: FY 2021 – FY 2022

30% DDR – July 2021

60% DDR – November 2021

90% DDR – August 2022

BCOES – October 2022

Construction:

Advertise Contract – January 2023

Award Contract – April 2023

Installation - December 2023 - March 2024

Evaluation/Closeout: FY 2024 - FY 2025

## Current Status

90% DDR is underway.  PDT is refining the LPS climbing flume alignment.

## Topics for FFDRWG Review/Coordination

60% BON1 DDR is available on the FFDRWG meeting files website.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# BON2 adult lamprey passage improvements

| Project Identifier: | P2 # 492401 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Shari Dunlop (CENWP-ENC) Shari.L.Dunlop@usace.army.mil |
| FFDRWG Coordination (FC): | Nathan McClain (CENWP-PME) nathan.a.mcclain@usace.army.mil |

## Project Description

Full redesign of control section (EDR/DDR, P&S, Construction).

2020 CRS BA Chapter 2: Proposed Action (pg.2-85): “This measure would modify the serpentine-style flow control sections of Bonneville Dam’s Washington Shore and Bradford Island fish ladders, converting them to Ice Harbor-style vertical slot with submerged orifices configurations. This would improve passage conditions for adult lamprey and likely reduce stress and delay for adult salmon, steelhead, and bull trout. All full-duplex passive integrated transponder (PIT) arrays currently located in the control sections of these ladders would be replaced in kind or improved to maintain or enhance current levels of detection of PIT-tagged anadromous fish.

## Project Schedule

Design: FY2021-FY2024

Construction: Winter 2024/2025

Evaluation/Follow-on: FY2025-FY2026

Closeout: FY 2027

Preliminary Milestones:

- Project Kick-Off: ~ August 2021

- 30% DDR: ~ January 2021

- 60% DDR: ~ June 2022  *FFDRWG review ~August 2022

- 90% DDR: ~ November 2022 *FFDRWG review ~December 2022

- Draft-Final: ~ January 2023  *FFDRWG review ~January 2023

- [Start P&S after 90% DDR DQC is complete, ~December 2023]

## Current Status

Screening-level hydraulic analysis was completed for four variations to achieve the CRS BA proposed action of replacing the serpentine control section with a vertical slot and orifice configuration. A site-specific cost estimate determined that the total project cost (not including evaluation/follow-on) would be in the $5M to $7M range. The PDT is now setting up 3D CAD and computational fluid dynamics (CFD) models to support the DDR design development work and advancing the structural design of the proposed modifications. PSMFC is additionally working on designs for the new PIT antenna arrays. The 30% DDR DQC is complete, and comments are being addressed by the PDT.

## Topics for FFDRWG Review/Coordination

30% BON2 DDR is available on the FFDRWG meeting files website