# Lower Columbia River Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

September 2022 Written Updates

## FFDRWG meeting Files

http://pweb.crohms.org/tmt/documents/FPOM/2010/FFDRWG/2022%20FFDRWG/

## Action items from previous meetings

- Jon and Max will perform a “red flag” review of the preliminary B2 FGE hydraulic test data and report back to FFDRWG via email in 2 weeks (18-Aug)

  - See written update below

- Nathan McClain and Jake Macdonald will summarize the available information supporting our expectation of a substantial boost to lamprey passage success combined with a benefit to salmonid passage at an upcoming FFDRWG meeting.

- TDA AWS backup debris management PDT will send the current draft as a read-ahead for September 1st FFDRWG.

  - Discussion postponed until 6-Oct.

  - The 50% EDR and alternatives ranking matrix are available on the FFDRWG website: http://pweb.crohms.org/tmt/documents/FPOM/2010/FFDRWG/2022%20FFDRWG/

- FFDRWG will review 2022 temperature data and shad mode test results in September and October, then provide a recommendation to the CRFM Program Manager for the initial FY 2025 budget capability submission due on 18-November.

  - Discussion postponed until 3-Nov.

  - See written update below.

- USACE (Jake, Jon, Max, Erin, or ??) will provide an update on the rock *prevention* PDT at the 1-September FFDRWG meeting.

  - From Max Wilson-Fey: “The BON Spillway Rock Mitigation project completed a Phase 1A report (similar to an EDR) back in January 2022.  The project has been shelved as we await funding for Phase 1, which last I heard may be provided at the beginning of FY23.”

  - “BON Spillway Rock Mitigation Phase 1A Final Report” is available on the FFDRWG website to refresh memories. http://pweb.crohms.org/tmt/documents/FPOM/2010/FFDRWG/2022%20FFDRWG/

Written Updates

BON Second Powerhouse FGE	2

TDA Backup AWS Debris Management EDR	3

BON2 adult lamprey passage improvements	5

JDA adult lamprey passage improvements	7

TDA adult lamprey passage improvements	8

BON1 adult lamprey passage improvements	9

JDA Ladder Cooling	10

Fish Facility Design Review Work Group (FFDRWG)

USACE, Portland District

Project Update

Date Prepared/Updated: 2022-08-31

# BON Second Powerhouse FGE

| Project Identifier: | P2 # |
| --- | --- |
| Project Manager (PM): | Jim Adams (CENWP-PMF) James.R.Adams@usace.army.mil |
| Technical Lead (TL): | Max Wilson-Fey (CENWP-ENC) Max.P.Wilson-Fey@usace.army.mil |
| FFDRWG Coordination (FL): | Jon Rerecich (CENWP-PME) Jonathan.G.Rerecich@usace.army.mil |

## Project Description

Steel plates were installed in all units in the A and B headgate slot to restrict flow in the gatewells to improve passage conditions for juvenile fish. During routine inspections, however, it became apparent that the anchoring system for the steel plates was inadequate. In effect, the nuts and anchoring bolts holding down the plates had come loose, posing the risk that the plates could detach and potentially take out a unit. All steel plates were removed from the units. A concrete corbel has been installed in Unit 15 where the steel plates once were. The design goal is to achieve similar gatewell hydraulic conditions as the steel plates. This new concrete corbel has been designed to meet the flow criteria established and tested for the previous steel plates to meet the hydraulic and biological goals.

## Project Schedule

| CLIN | Status | Description | Award/Exercise Date | Construction Execution Window |
| --- | --- | --- | --- | --- |
| 1 | Mandatory | Mobilization/Demobilization | Awarded DEC 2020 | Complete |
| 2 | Mandatory | Unit 15 Construction | Awarded DEC 2020 | Complete |
| 3 | Optional | Second Mob/Demob, Unit 11 and 18 Construction | Awarded AUG 2021 | DEC 2022 - FEB 2023 |
| 4 | Optional | 2 Additional Units | Awarded AUG 2021 | Extend through MAY 2023 |
| 5 | Optional | 2 Additional Units | Awarded AUG 2021 | Extend through AUG 2023 |
| 6 | Optional | 1 Additional Units | Awarded AUG 2021 | Extend through FEB 2024 |

## Current Status

- 2022 hydraulic testing is complete. Velocity measurements were taken in unit 15 upstream of the VBS to verify performance of corbels. Pressure transducer measurements were taken in units 14 and 15 to determine effects of pressure wave on corbels.

- Preliminary data is under review by the Corps. Internal discussions continue to occur to discuss results and get alignment on recommended path forward. A final report is due 28-OCT-2022.

- Preliminary data suggests the 2022 data (corbels) displays slightly higher through-screen velocities compared to the 2015 data (steel plates). Average turbulence values were comparable between years. Pressure results show no appreciable impact of pressure wave on corbel.

- PDT moving forward at present time with outfitting the remaining units. Construction of corbels in units 11 and 18 is scheduled for the DEC 2022 – FEB 2023 IWW, followed by the remaining PH2 units throughout the remainder of 2023.

## Topics for FFDRWG Review/Coordination

Discuss preliminary results prior to or at the 6-OCT-2022 FFDRWG.

Fish Facility Design Review Work Group (FFDRWG)

USACE, Portland District

Project Update

Date Prepared/Updated: 2022-08-31

# TDA Backup AWS Debris Management EDR

| Project Identifier: | P2 # |
| --- | --- |
| Project Manager (PM): | Erin Kovalchuk (CENWP-PMF) Erin.H.Kkovalchuk@usace.army.mil |
| Technical Lead (TL): | Mehdi Roshani (CENWP-ENC) Mehdi.Roshani@usace.army.mil |
| FFDRWG Coordination (FC): | Jon Rerecich (CENWP-PME) Jonathan.G.Rerecich@usace.army.mil |

## Project Description

This project is to evaluate alternatives to remove debris from The Dalles Dam Auxiliary Water Supply (AWS) trash rack. Debris build-up on the rack currently causes high head differential across the rack. Fish Unit Rehab requires the AWS backup system to operate during the rehab to provide adequate flow for fish attraction. Fish Unit Rehab duration is one year per unit for a total of two years. Long term use of the backup AWS system will be part of the alternatives evaluation.

## Project Schedule

| Milestone | Start | End |
| --- | --- | --- |
| Criteria and Constraint Report (30%) | 4/19/2021 | 8/6/2021 |
| Value Management | 8/9/2021 | 8/20/2021 |
| Alternative Evaluation Report (60%) | 8/23/2021 | 1/27/2023 |
| Draft Final Report (90%) | 1/30/2023 | 7/14/2023 |
| ATR | 7/7/2023 | 7/21/2023 |
| Final Report | 7/17/2023 | 10/23/2023 |
| Closeout | 10/24/2023 | 10/30/2023 |

## Current Status

- Working toward 60% EDR.  The PDT has developed alternatives, evaluation criteria and scoring.

- The 50% EDR and alternatives ranking matrix are available on the FFDRWG website: http://pweb.crohms.org/tmt/documents/FPOM/2010/FFDRWG/2022%20FFDRWG/

- The PDT is planning to present the alternatives at the Oct. 6 FFDRWG for discussion.

## Topics for FFDRWG Review/Coordination

- Discussion of alternatives and other ideas to incorporate into the evaluation matrix for the 60% Engineering Design Report (EDR) milestone.

- PDT will send the 60% EDR for FFDRWG review.

## Summary

PDT stopped working on this project during alternative evaluation at the end of FY21, due to lack of funding. The Value Engineering (VE) study was performed in August 2021 and a draft report was provided. During the VE study, various tools were used to help the project team identify existing alternatives and develop new proposals to best meet project criteria. Weighted paired comparisons were used to develop performance criteria for ranking existing alternatives and new proposals. All proposals, as well as the team’s assessment of the top five existing potential alternatives, were evaluated against the performance criteria developed using the weighted paired comparisons.

After receiving the Draft VE Study Report, PDT further evaluated the weighted paired comparisons, prepared by the VE team, and updated the values and the evaluation criteria list. The PDT modified the alternative ranking of all the potential alternatives and the selected new potential alternatives proposed by the VE team. The EDR includes Evaluation Criteria, Paired Comparisons, and Alterative Rankings developed by both VE team and PDT members.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# BON2 adult lamprey passage improvements

| Project Identifier: | P2 # 492401 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Shari Dunlop (CENWP-ENC) Shari.L.Dunlop@usace.army.mil |
| FFDRWG Coordination (FC): | Nathan McClain (CENWP-PME) nathan.a.mcclain@usace.army.mil |

## Project Description

Full redesign of control section (EDR/DDR, P&S, Construction).

2020 CRS BA Chapter 2: Proposed Action (pg.2-85): “This measure would modify the serpentine-style flow control sections of Bonneville Dam’s Washington Shore and Bradford Island fish ladders, converting them to Ice Harbor-style vertical slot with submerged orifices configurations. This would improve passage conditions for adult lamprey and likely reduce stress and delay for adult salmon, steelhead, and bull trout. All full-duplex passive integrated transponder (PIT) arrays currently located in the control sections of these ladders would be replaced in kind or improved to maintain or enhance current levels of detection of PIT-tagged anadromous fish.

## Project Schedule

Design: FY2021-FY2024

Construction: Winter 2024/2025

Evaluation/Follow-on: FY2025-FY2026

Closeout: FY 2027

Preliminary Milestones:

- Project Kick-Off: ~ August 2021

- 30% DDR: ~ January 2021

- 60% DDR: ~ June 2022  *FFDRWG review ~August 2022

- 90% DDR: ~ November 2022 *FFDRWG review ~December 2022

- Draft-Final: ~ January 2023  *FFDRWG review ~January 2023

- [Start P&S after 90% DDR DQC is complete, ~December 2023]

## Current Status

Screening-level hydraulic analysis was completed for four variations to achieve the CRS BA proposed action of replacing the serpentine control section with a vertical slot and orifice configuration. A site-specific cost estimate determined that the total project cost (not including evaluation/follow-on) would be in the $5M to $7M range. The PDT is now setting up 3D CAD and computational fluid dynamics (CFD) models to support the DDR design development work and advancing the structural design of the proposed modifications. PSMFC is additionally working on designs for the new PIT antenna arrays. The 30% DDR DQC is complete, and comments are being addressed by the PDT.

## Topics for FFDRWG Review/Coordination

30% BON2 DDR is available on the FFDRWG meeting files website

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# JDA adult lamprey passage improvements

| Project Identifier: | P2 # 492402 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Scott Fielding (CENWP-PME) Scott.D.Fielding@usace.army.mil |

## Project Description

### Modify NFL LPS to increase the capacity and reliability of the system

This is a fish safety/health issue, and the upgrade needs to happen. Current water supply is insufficient so tank cannot be installed without upgraded water supply.  See January 2020 CRS BA § 2.5, pg. 2-85.

- gravity-fed water supply or alternative, more reliable pump configuration.

- larger collection box

### SFL entrance improvements (rounded crest, slot cover/filler)

Caps may not be able to be added to South Ladder entrance weir due to FPP submergence criteria, so the weir may need to be modified more extensively to provide rounded weir crests and guide slot covers.

### SFL count station collection and counting structure (trap) improvements

Increase capacity and efficiency of system by preventing sediment buildup, providing a larger opening into a larger collection box, modified guide, and removal of gate and counting-related structure.

## Project Schedule

Design: FY 2021 – FY 2022

30% DDR – July 2021

60% DDR – November 2021

100% DDR – May 2022

Construction: December 2022 - March 2023

Evaluation/Closeout: FY 2023

## Current Status

100% DDR is complete.  PDT is moving forward with a gravity feed water supply from behind existing picketed leads near the count station via an existing diffuser drain line.  A surplus holding tank at JDA will be modified and relocated to serve as the larger collection box.  All work will be performed by Corps staff, no contracts.

## Topics for FFDRWG Review/Coordination

100% JDA DDR is available on the FFDRWG meeting files website. Because it’s an in-house construction project, there will be no 90% DDR and no BCOES, PDT is advancing straight from 60% to 100%.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# TDA adult lamprey passage improvements

| Project Identifier: | P2 # 492403 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Jacob Macdonald (CENWP-PME) Jacob.Macdonald@usace.army.mil |

## Project Description

### Lamprey collection system (LPS) at the east fish ladder junction pool

Provide two ramps for lamprey to swim out of the junction pool and into a collection box located below the upper segment of the fish ladder for upstream transport. See January 2020 CRS BA § 2.5, pg. 2-85.

### Modify elevated orifices in EFL exit weirs 154-157

Provide better lamprey passage options through the 4 control weirs at the upstream end of the east fish ladder.

### Bulkhead slot covers

Design and install bulkhead slot covers at all four fishway entrances.

## Project Schedule

Design: FY 2021 – FY 2023

30% DDR – August 2021

60% DDR – February 2021

90% DDR – September 2022

BCOES – November 2022

Construction: December 2023 - March 2024

Evaluation/Closeout: FY 2024

## Current Status

90% DDR is underway.  Preferred LPS design includes gravity-fed water supplied from an existing auxiliary penstock in the dam, a large collection box on the deck near the junction pool, and two climbing ramps reaching down to the fishway floor.

## Topics for FFDRWG Review/Coordination

- Exit weirs 154-157 will be notched in the corners to improve lamprey passage. Because the weirs have lead paint, they will be removed from the ladder to perform this work. Project will perform the necessary lead paint mitigation away from the fish ladder.

60% TDA DDR is available on the FFDRWG meeting files website.  90% will be available in September.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-5-3

# BON1 adult lamprey passage improvements

| Project Identifier: | P2 # 492400 |
| --- | --- |
| Project Manager (PM): | Jeremiah Woodard (CENWP-PMF) jeremiah.j.woodard@usace.army.mil |
| Technical Lead (TL): | Adam White (CENWP-ENC) Adam.J.White@usace.army.mil |
| FFDRWG Coordination (FC): | Jacob Macdonald (CENWP-PME) Jacob.Macdonald@usace.army.mil |

## Project Description

The project scope is divided into three parts:

### Entrance Modifications

Modify the B-branch fish ladder entrance to improve lamprey passage. This includes a variable-width entrance weir with rounded edges, guide slot fillers or covers to aid lamprey passage along the walls, and bollards on the channel floor for hydraulic refuge.

### Lamprey Collection

Provide an alternate route for lamprey entering the B-branch of the Bradford Island fish ladder. Fish would climb up a flume structure to a holding tank on the deck of the dam and be transported upstream by Tribal fisheries personnel. This will be designed so that in the future we could extend the system to provide volitional passage to the Bonneville forebay.

### Serpentine Section Extensive Minor Mods

Upgrade the serpentine section of the Bradford Island fish ladder to improve lamprey passage by rounding corners, providing refuge boxes, and lamprey orifices.

## Project Schedule

Design: FY 2021 – FY 2022

30% DDR – July 2021

60% DDR – November 2021

90% DDR – August 2022

BCOES – October 2022

Construction:

Advertise Contract – January 2023

Award Contract – April 2023

Installation - December 2023 - March 2024

Evaluation/Closeout: FY 2024 - FY 2025

## Current Status

90% DDR is underway.  PDT is refining the LPS climbing flume alignment.

## Topics for FFDRWG Review/Coordination

60% BON1 DDR is available on the FFDRWG meeting files website.

# Fish Facility Design Review Work Group (FFDRWG)

# USACE, Portland District

# Project Update

Date Prepared/Updated: 2022-9-1

# JDA Ladder Cooling

| Project Identifier: | P2 # N/A |
| --- | --- |
| Project Manager (PM): | N/A |
| Technical Lead (TL): | N/A |
| FFDRWG Coordination (FC): | Scott Fielding (CENWP-PME) Scott.D.Fielding@usace.army.mil |

## Project Description

Future project to reduce entrance-exit temperature differentials and maximum temperatures in the John Day South fish ladder.  Ladder cooling structures at the Snake River dams are effective, a similar design may be effective at JDA as well.

## Project Schedule (optimistic rough estimate)

| YEAR | MAJOR ACTIVITIES |
| --- | --- |
| FY24 | EDR/DDR |
| FY25 | P&S (as needed; funding dependent) |
| FY26 | Construction (as needed; funding dependent) |

## Current Status

## In 2022, John Day Fisheries Staff is collecting temperature data related to differentials between the John Day South fish ladder exit and entrance.  A temperature string has been deployed in the forebay to gather profile temperatures.  In 2022, an extended shad operation to test the effects of the operation on ladder temperatures. The shad operation, temperature profile string, ladder temperatures, and fish passage information will be compiled in a memo for review by regional fish managers.  This memo will be sent to FFDRWG in late fall/early winter of 2022.

## Topics for FFDRWG Review/Coordination

FFDRWG will review the above-mentioned memo at our 3-Nov meeting and determine if a structural solution is the best path forward to reduce the temperature differentials between the entrance and exit of the South Fish Ladder.  If so, FFDRWG may recommend the Corps express capability for design and construction in an out-year’s budget.