
Updated 28 August 2019

CENWP-OD-B

MEMORANDUM FOR THE RECORD 
SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2019/20.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.  
KEY TO COLORS:
Red - Painters

Blue – Mechanics

Pink – Riggers

Green – Garage

Orange – Electricians

Aqua- Fisheries
Yellow- Contractors or Researchers
1. OREGON SIDE
1.1. Bradford Island Ladder – (30 Nov 19 – 27 Feb 20)  
Orifice flow on Saturday, Nov 30th 
Dewater A-branch and B-branch to tailwater on Monday, Dec 2nd & Tuesday, Dec 3rd
Dewater PH1CC past tailwater on Wednesday, Dec 4th and Thursday, Dec 5th 
1.1.1. FG3-3 through FG3-9 (A-branch):
1.1.1.1. FG3-5 OOS since 28-Mar-19.
1.1.2. FG3-18 through FG3-33 (B-branch):

1.1.2.1. FG3-27 Caution Card.
1.1.3. FV1-1 / FV1-2:

1.1.4. FV3-7: 
1.1.5. FV3-9:

1.1.6. FV4-3:

1.1.7. FV4-4:

1.1.8. FG2-4 through FG2-22B (PH1CC): 

1.1.9. WG1/2:

1.1.10. WG64/65: 

1.1.11. PH1 ITS:

1.1.12. SG4-N / SG4-S (B-branch): 
1.1.13. Pressure wash fishways, remove vegetation on top of weirs, A-Branch!!! (GAR or PNT)
1.1.14. Remove BI Wetted Wall? (MPH1)

1.1.15. Pressure wash BI LPS and exit chute (GAR or PNT)
1.1.16. Repair or replace FV 1-1 AWS level sensor
2. WASHINGTON SIDE - Not dewatering 2019/20.
2.1. Cascades Island – (Dewater on 10 Dec 19)
PSMFC inspection 11 Dec


ROV inspection during winter 15-16 Jan?
2.2. Washington Shore Ladder – Not dewatering

ROV inspection during winter 15-16 Jan?
2.3. PH2CC, North and South entrances – Not dewatering
ROV inspection during winter 15-16 Jan?
2.4. B2 Corner Collector  (01 Sept 2019 – Mar 2020)
2.4.1. Check/repair PIT antenna joints (FISH/PNT) 09 Sept
2.5. DSM 2 (15 Dec – 28 Feb 2020)
2.5.1. Turn off orifice lights on Saturday, Dec 14th?
2.5.2. Dewater DSM on Sunday, Dec 15th?
2.5.3. Pull STSs week of Dec 16th – 19th?
2.5.4. STS repairs / maintenance.
2.5.5. 2-mile pipe inspection Wednesday, Jan 22nd?
2.5.6. Install STSs starting week of Feb 17th 2020?

3. RESEARCH FACILITIES 

3.1. Adult Fish Facility (Nov – late Mar / early Apr) 
Go to orifice flow on Monday, Nov 18th?
Dewater on Tuesday, Nov 19th?
3.1.1. Replace seals in fill station.
3.2. Smolt Monitoring Facility (31 Oct – 28 Feb)

Switch to bypass, drain and inspect sample flume on 31 Oct (PSMFC)
3.2.1. Will update once Dean sends up his annual list for maintenance. 
3.3. Lamprey Passage Systems (01 Nov – 01 Apr)

3.3.1. Turn off systems, check rest boxes, and dewater 31 Oct

3.3.2. Pull pumps week of 04 Nov
3.3.3. Power wash accessible surfaces
3.3.4. WA Shore LPS cabinet repairs?

3.3.5. LFS hatch repairs
[image: image1.png]


