# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2021/2022.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.

KEY TO COLORS:

Red - Painters

Blue – Mechanics/Riggers

Green – Garage

Orange – Electricians

Aqua- Fisheries

Yellow- Contractors or Researchers

Purple - Engineers

- OREGON SIDE

  - Bradford Island Ladder – (Wednesday, 01 Dec 21 – Monday, 28 Feb 22 (or Thursday 24 February if possible))

Orifice flow on Monday, Nov 29th

Dewater A-branch and B-branch to tailwater on Wednesday, Dec 1st & Thursday, Dec 2nd

    - PH1CC - Dewater PH1CC past tailwater on Monday, Dec 6th and Tuesday, Dec 7th

      - FG 2-22 gear box issue

      - Check spalling

      - Suck truck

    - FG3-3 through FG3-9 (A-branch):

      - FG3-3: Unsure if it is fixed?

      - FG3-4 OOS since Dec 2020

      - FG3-5 OOS since 07 June 2021. Broken gate possibly

      - FG3-6 OOS since 07 June 2021. Mechanically bound

    - FG3-18 through FG3-33 (B-branch):

      - FG3-27 Caution Card.

      - Entrance Bay grating has shifted (holes around edges)

      - Replace juvenile bypass bulkheads at B-Branch

    - FV1-1 / FV1-2: Clean pit?

    - FV3-7: Has been in manual since June 2021 due to diffusers not operating

    - FV3-9:

    - FV4-3: Clean pit?

    - FV4-4: Clean pit?

    - FG2-4 through FG2-22B (PH1CC): Lots of concrete spalling found on floor of Collection Channel, check where that is coming from

    - WG1/2: WG1 Transponder not working/Mattias in the process of fixing

    - WG64/65:

    - A Branch AWS: Check leak

    - SG4-N / SG4-S (B-branch):

    - Pressure wash fishways, remove vegetation on top of weirs. A-Branch/B-Branch/Junction Pool/Serpentine (GAR or PNT)

    - Polish windows at BIVC/Count Window

    - Pressure wash BI LPS and exit chute (GAR or PNT)

    - Repair/Replace Tailwater gauges at PH1 N and S, PH2 Downstream TW’s, Spillway N and S TW

    - Repair spillway avian line (or lines) that have broken/Also B2CC avian lines

    - New Temp monitoring system. Stillwells at B-Branch Ent and CI Ent Bay need to be fixed

    - Swap out ALL PVC LPS drain valves with metal (Both PH1 and PH2/CI sides)

- WASHINGTON SIDE - Not dewatering 2021/22.

  - Cascades Island

  - Washington Shore Ladder – Not dewatering

  - PH2CC, North and South entrances – Not dewatering

  - B2 Corner Collector (01 Sept 2021 – Mar 2022)

    - Check/repair PIT antenna joints (FISH/PNT) Tuesday, 19 October

  - DSM 2 (15 Dec – 28 Feb 2020)

    - Turn off orifice lights on Tuesday, Dec 14th?

    - Dewater DSM on Wednesday, Dec 15th?

    - Pull STSs week of Dec 13th – 17th?

    - STS repairs / maintenance.

    - 2-mile pipe inspection Tues Jan 18th

    - Install STSs starting week of Feb 14th 2020?

- OTHER FACILITIES

  - Adult Fish Facility (Nov – late Mar / early Apr)

Go to orifice flow on Monday, Nov 1st?

Dewater on Tuesday, Nov 2nd?

    - Replace seals in fill station.

    - Replace grating that was planned to be replaced last year

    - Add screen at Valve 15 to float dead shad, etc…

    - Pressure wash accessible surfaces

  - Lamprey Passage Systems (01 Nov – 01 Apr)

    - Turn off systems, check rest boxes, and dewater Monday 01 Nov 2021

    - Pull pumps week of 01 Nov

    - Power wash accessible surfaces

    - Replace all PVC drain valves with metal, esp CI LPS

  - Smolt Monitoring Facility (01 Nov – 28 Feb)

Switch to bypass, drain and inspect sample flume on Monday 01 Nov (PSMFC)

- LAMPREY ACCORDS $$$$

  - Rounding off corners, orifice ramps, diffuser plating, serpentine section lamprey orifices – lamprey $$$ (all fishways)

  - Add lamprey orifices in BI serpentine

- NAVLOCK

  - Navlock 2 dewatered 2/13-3/19 (possibly only 3 weeks instead of all 5)

    - Fish on Monday 14 February?