JOHN DAY DAM FISHWAYS’ ANNUAL MAINTENANCE SCHEDULE WINTER 2021/2022

North Fish Ladder (NFL)

[December 6th, 2021 – January 7th, 2022]

North Entrance

- Modify NFL Entrance weir plating – JDM

- SCADA – add sluice gate screen for AWS pumps to office - JDE

North Upper

- PM count station and exit weirs - JDM & E

- Update light fixtures and install emergency lights at the Counting Station – JDE

- Set window brush to run 1-cycle instead of 3-cycles - JDE

- Adjust window/crowder brush to get closer to the CS window in Auto – JDM or JDE

- New hobo probe locations and ensure all piping is 3” diameter - JDF

LPS

- Modification installation – JDM JD Eng

- LPS – pull and inspect water supply piping and pumps – Repair water supply line - JDM

- Inspect pumps if necessary (may be modified) – JDM/JDF

- Install valve at CS drain for future LPS gravity feed – JDM/JD Eng

North Exit

- AWS pumps inspection & annual maintenance (year-round) JDM & E

- Entrance Computer System & sensors PM – JDE

- Fix and reinstall pump 4 - JDM

- Leaking Butterfly Valves (AWS Pumps) repair (3 @ $ 10K) – JDM

- Inspect and service two AWS pumps (has this been done)– JDM

- PMs of entrance sluice gates 1-8 – JDM

- Variable width weir front plating replacement - JD Eng and JDM

SMF and JBS

[December 1st, 2021 – February 21st,2022]

(Dewater earlier in case of an inclement/winter weather forecast)

Lab									Dec. 01, ‘21

- Order and Replace V-14 (Aux water valve near head tank) -JDM

- Complete the multi-year SCADA PLC updates to have all alarms and functions working properly - JDE and JD Eng

- Replace valves - JDM

Crest Gate Raised							January 3- February 21 ‘22

- Ensure new extendable ladder is at JBS

- Design a better bottom seal/ boot on the Switch Gate (last winter’s work didn’t succeed): to minimize water leaks and potential for small fish getting stuck underneath – ENG/JDM

- Switch gate porosity plate rehab (smaller porosity, or plate over) – ENG/JDM

- Seal leaking expansion joints inside of the Elevated Chute – optional since don’t leak a lot - JDM

- PMs and cleanup including Screen Cleaner and calibrate weirs– JDM/JDE

- High-capacity drain opens in the off position – Should only open when prompted to - JDE

- Replace screen cleaner limit switches – JDE

- Clean PDS staff gauge, and clear coat - JDF

- Replace blown plug under grating on W end of PDS – JDF

- Remove debris from PDS - JDF

- Replace plug chains with rope – JDF

- Joint in flume below switch gate (collection side)-JDM

JBS Collection Channel Dewater						Jan. 3 – Feb.21, ‘22

- Install STSs at MUs 1-4 by February28 and the remaining ones by March 30. - JDM

- First joint downstream of the TG needs the redesigned cover plates and recessed concrete to fit them properly within the wall – JDM

- Inspect CC conduit’s spalling & structural integrity – JD Eng. & JDM

- Inspect all orifices/ hardware – JDM

- Search for all metal strips/brackets to assure their structural integrity- JDF

- PM JBS Tainter gate –JDM & JDE

South Fish Ladder (SFL)

[January 10th, 2022 – February 10th, 2022]

(The early water up coincides with the early Navlock outage on February 13th)

South Turbine Bulkhead Install - ROV if necessary				Jan. 12, ‘22

- AWS turbines 2/3 inspections -JDM

- Inspect inside of AWS Turbines’ penstock – JDM and JD Eng

South Fish Ladder Exit Dewater							Jan 10 - Feb. 21, ‘22

- PM counting station equipment and exit sills (JDM/JDE)

- Fix leaking expansion joints – JDM or contract by JD Eng – resources

- Count station Lamprey trap modifications (tentative) – JDM/ JD Eng

- Clean clams and sand accumulation from LPS area – JDF

- Clean out triangular area where CS sensor is located JDF if NOT able to lift porosity plating– JDM, JDF?

- Check to ensure floor at CS is still white – clean all CS windows – JDF

- Modify exit boom to omit otter predation and better secure – JDM

- New hobo probe locations and ensure all piping is 3” diameter - JDF

South Ladder Lamprey Trap							TBD

- Rotate Grating 90° near the ramp entrance, and replace ramp area with grating to help push sediment out - JDM

South Entrance Collection channel - Dewater					Jan. 11, ‘22

- Inspect all gratings and fix deficiencies if found. A few grating segments on the south end of CC showed some wear from the man lifts used there in 2013; JD Structural inspected/scoped in 2014- JDM

- New staff gauge tracks SE1/CC - JDF

- 90 degrees bend wall erosion – needs to be fixed before we have a landslide into Fishway’s channel – repair contract by JD Engineering!

- Inspect new SE1 weir; check guides for wear from the stainless-steel wheels (TD had bad/costly experience with theirs!)  – JDM

- Floating orifices, remove entrance plating - JDM

- If dewatered below tailwater replace Bay 1 and Bay 19 staff gauges - JDF

- PM SE1, NE1/2 entrance weirs –JDM&E

- Relocate SE1 tailrace sensor (TW) – JDM/JDE

- Inspect diffuser valves/sluice gates on open diffusers only (ask Fisheries for details)- JDM

- Demob and remove Wing Gates hardware from Collection Channel MU 9 (Optional) - JDM

South AWS conduit – Dewater or NOT?						Jan. 12, ’22

- Inspect and remove accumulated mussel shells if necessary

South fish turbine intake trashrack install and water up				Feb. 22, ‘22

- Install trashracks and picketed leads at count stations - JDM

- Reinstall avian line from spill bay 7 – lower priority – JDM or Contracting

Guidelines

- Adult winter maintenance (outage) season is Dec 1 through Feb 28.

- Juvenile winter maintenance (outage) season is Dec 1 through February 28.

- STS pulled after 15 December

- One adult ladder in regular service at all times when the second one is OOS for winter maintenance.  Any overlapping outages (two ladders OOS at the same time are required to be coordinated in advance with FPOM.