THE DALLES FISHWAY DEWATER SCHEDULE

2021-22

Fish Unit 1 and 2 				OOS				Dec 1, 2021

East Fishladder 				Dewater			Dec 2, 2021

- 158 seal

- Inspect weir brackets

- Inspect lower ladder grating

- Scan for PITs (TDF)

- Pull exit trashrack inspect

- Install exit oil boom

East Fishway below tailwater			Dewater			Dec 6, 2021

- Inspect grating

- Inspect diffuser valves JP AWS chamber

- Install SCADA west entrance

North Fishladder				Dewater			Jan 17, 2022

- Inspect diffuser valve at count station

- Pull Exit trashrack inspect

- Pull PUD intake trashrack inspect

North Fishway below tailwater		Dewater			Jan 18, 2022

- Inspect grating

- Install SCADA north entrance

- Inspect weir N1 wheel wear

Ice Trash Sluiceway 				OOS				Dec 16, 2021

- Endgate inspect

- Lower channel check for spalling