# CENWP-OD-B

MEMORANDUM FOR THE RECORD

SUBJECT:  BONNEVILLE DAM WINTER NON-ROUTINE FISHWAY MAINTENANCE 2023/2024.

This is a working document; reviewers can expect changes as we approach the winter maintenance season.

KEY TO COLORS:

Blue – Mechanics/Riggers

Green – Garage/Paint

Orange – Electricians

Aqua – Fisheries

Red – Contractors or Researchers

Purple – Engineers/Tech

Prospected Dates

- Bradford Island Ladder:

  - Orifice Flow: Friday 01 Dec (Derugin)

  - Mech Prep/Staging Day: Monday 04 Dec

  - Dewater to tailwater: Tuesday 05 Dec

  - Dewater past TW:

    - B-Branch: 06 – 07 Dec

    - A-Branch: Week of 11 Dec?

  - Water Up: By 28 Feb

  - Project Winter Maint work in B-Branch to Occur: 22-26 Jan

- B2CC:

  - Spalling fixes: 09-15 Sept 2023 Work occurred, but requires further work.  Coordination still to come.

- DSM2:  _____________ to _______________

  - Turn off orifice lights: __per Ops___________

  - Dewater DSM: _____per Ops________

  - Pull STS’s: Week of 11 Dec

  - 2-Mile pipe inspection: 10 Jan

- AFF: (Late Nov to Early April)

  - Go to orifice flow: 24 Nov

  - Dewater on: 27 Nov

  - Water up: By early April

- LPS’s:

  - Take down LPS’s: 01 Nov complete!

  - Pull pumps: week of 01 Nov

- SMF:

  - Switch to bypass: 01 Nov complete!

- Navlock 2: Dewatering to upper sill: 1st two weeks of March

- B-Branch LPS Construction:

  - Expected arrival of premade lamprey flume: 05 Jan

  - Contractors onsite: 30 Oct to start mobilize

  - Trench work at B-Branch: 06 Nov – 24/25 Nov

  - Project-related winter maintenance work (WORs/PMs) in B-Branch to occur: 22-26 Jan

Work Priority:

- Final Fishway Inspection with Fisheries and Maintenance Supervisors

  - 21 February

- Avian Line Re-Install (If required) ***not required this year, unless wires break***

  - 1st or 2nd week of March (prior to kelt trigger starting B2CC)

- BI Exit Dredging (Possibly in Feb - TBD)

  - Project support needed for at least pulling boom from area

  - Corps District Dive team NOT involved (but there is a Contract dive team) in veg removal

  - MPH1 may want to install bulkheads to prevent excess debris movement

  - MPH1 possibly need to remove raking skiff (Derugin to find out)

- Bradford Island

  - B-Branch (Week of 22-26 January set aside for Project work)

    - B-Branch South Entrance Gate stuck in the closed position

    - FV 4-4 Brakes Hanging Up

    - Investigate Controls for FV 4-3 and FV 4-4 Not Responding

  - A-Branch

    - FG 3-4 In manual control until lower limits set

  - PH1 Collection Channel

    - FG 2-19 Stuck in the closed position

    - AWS Sensor Relocation

- B-Branch LPS Construction

  - Inspect B-Branch Entrance Bay thoroughly.

  - Expected arrival of pre-made flume: 05 January

  - Electrical preps

- Rehab Flow Control Louvre in BI Flow Control Section

  - “Evaluation” with this WOR to determine if we can make it work/what it needs

- Pressure wash fishways, remove vegetation on top of weirs (Normal PM)

  - Cut brush away at A-Branch Staff Gauge

- SMF Outdoor Water Supply Drain

- FV 4-3/4-4:

  - Clean pit (Normal PM)

- FV 1-1/FV 1-2

  - Clean pit (Normal PM)

  - Check structural integrity of valve pits

  - TECH to inspect possible concrete spalling at FV 1-1 Valve (Leakage)

  - Derugin asked MPH1 to look into doing a ROV inspection of forebay sill of FV 1-1 bulkhead during outage (spalling suspected due to heavy leakage).

- A-Branch Leak

  - Check structural integrity

  - Utilize Dock Blocks to inspect conduit?

- Staff Gauges (WOR created)

  - CAD Design

  - Make Gauges and Install

  - Next on list to install are:

    - PH2 TW gauges (bottom sections need to be finished)

    - Spillway N and S TW gauges

    - PH1 S TW

- DSM Tunnel Ride

  - Who’s getting the honor of riding: Tucker and TECH

- Inspect old wooden gate bulkheads in slots at juvenile bypass section at B-Branch/Main Dam South Tower

  - Get eyes on slots and check to see if still usable (MPH1)

- LPS

  - Pressure wash all LPS’s (including ramps from water level to rest boxes

  - Install shroud over pump control panels (BI LPS, CI LPS)

  - Pressure wash all lamprey traps

- AFF

  - Pressure wash accessible surfaces (Normal PM)

  - Valve PMs

- Lamprey Minor Mods: (Expect about 2 days of work?)

  - Orifice ramps

    - Only needed anywhere there is a step (even a 1” step should be ramped)

    - Size depends on the height of step. End goal is “continuous planar surface” through the high velocity zone of influence from the orifice

  - Finish lamprey orifices in flow control section

    - 5 more volutes on hand in Blue (FISH) Connex behind BISB

  - Lamprey rest box rehab (BI Control Section)

    - Create PM for this?

    - Properly blow out/clean bolt holes in floor

    - Fasten boxes back on prior to water up

      - Possibly use bigger, thicker gaskets to create better connection (less rattling ability)

    - Address broken box

      - Possibly attach with eye bolts instead of current fasteners

- Polish Windows at VC/Count Window

  - Normal PM

- SMF

  - Priority New Work Requests:

    - Address/repair the section of the adult bypass flume that has subsided.

    - Replace the degraded rubber join on subsided flume (above) and other adult flume sections, as required.

    - Replace the burned-out Infrared heaters at the PDS.

    - Re-caulk PDS wedge wire, perf plate, and separator bar areas.

    - Add bleed valve to compressed air system on 2-way and 3-way rotating gates for safety.

    - Remove overgrown foliage that is impacting fish flume and grating.

    - Activate or repair digital video camera to enable high-definition feed to monitors.

  - Annual Maintenance Items:

    - Inspect and repair (where needed) all joints in the fish distribution flumes paying particular attention to those upstream of the 3-way rotating gate and downstream of River Exit PIT detector.

    - Winterize the 2 and 3-way rotating gates, including:

      - Inspect and repair any cracks in the movable sections of the rotating gates.

      - Insure free rotation of the movable sections.

      - Adjust or replace drive belts, if needed.

      - Replace shock absorbers, if needed.

    - Replace the charcoal filters on the water treatment system. Please ensure lids have center-cut inflow to match existing plumbing.

    - Inspect all fish lift cables with special attention to the most use used lift, #2.

    - Winterize compressed air system in facility.

    - Inspect entire air system for leaks, especially at the regulators and oil/water traps.

    - Arrange to have sludge pumped/removed from 1000-gallon wastewater tank.