## Ranking Sheet
CRFM FY19 RANKING SPREADSHEET
|  | FY2019 PBUD TOTAL $46M - $28.975M FCRPS, $17.025M Willamette, and $0 Lamprey |  |  | Version: 4/18/2018 (Version 1.0)
|  | PBud- $46M |  |  | Updated By: I. Chane
House - ?
Senate - ?
Line # | Project Location | Project Title | PM | Project P2 ID | Description (FY18 Scope) | FY19 Pbud | FY19 Current Capability | FY19 Preliminary Cumulative | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2019 Average Score | CURRENT REMARKS | Agency Remarks During Ranking
| Willamette | [22 empty] | District
1 | Willamette |  |  |  | Total - Willamette (NWP) | 17025 | 18020 | 18020 | Y | [11 empty] | M |  |  | P
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP) | 0 | 0 | 18020 | Y | [11 empty] | M |  |  | P/W
FCRPS
3 | ESTU | Estuary Habitat Studies | Turaski | 123452 | Oversight of FY17/FY18 studies - preparation for AEMR report and synthesis in FY19 | 0 | 625 | 18645 | [13 empty] | Deferred to FY19 pending FY18 funding availability |  | P
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - depredation, monitoring and terrain modifications | 750 | 750 | 19395 | [15 empty] | P
5 | JDA | John Day Avian Wires | Medina | 463071 | SA/EDC for Phase 2 construction; including contract mod contingency | 0 | 0 | 19395
6 | JDA | John Day Adult PIT Detection | Richards | 454951 | SA/EDC for remaining construction; project closeout | 0 | 0 | 19395 | [13 empty] | This task/budget was not included in FY18 PBUD
11 | JDA | John Day Mitigation | Gibbons | 122434 | Analysis for JDA - TAP | 0 | 436 | 19831 | [13 empty] | Not initially in FY18 budget - coordination with TAC and further analysis
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Turaski | 142630 | SA/EDC and mod contingency; oversight | 500 | 500 | 20331
8 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight | 1600 | 1600 | 21931 | [15 empty] | P
9 | SYS | Avian Island PIT Detection | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 200 | 200 | 22131 | [15 empty] | W
10 | SYS | Turbine Survival Program | Medina | 157101 | Project closeout; final reporting | 0 | 0 | 22131 | [15 empty] | W
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | Adams | 465995 | Monitoring of forebay temperatures for assessing stratification/profile (July-August). Preparation for deployment in 2018. | 0 | 50 | 22181 | [13 empty] | Not in FY18 Pbud
13 | SYS | FCRPS CRFM Program Management (NWP) | Chane | 123591 | Internal and external program coordination; oversight; project and budget support | 600 | 500 | 22681
14 | MCN | McNary Avian Water Cannon Deficiency Correction and Avian Wire Design Feasibility Report | Wik | 464428 | Design and contract award to address water cannon/sprinkler deficiencies. Additionally a limited evaluation on avian wire arrays will occur that focuses on placement of wires if water cannon/sprinkler system is not satisfactory. | 100 | 100 | 22781 | [15 empty] | P
15 | MCN | McNary Top Spill Weir (TSW) Permanence | Wik | 398029 | Design effort in FY18. Design includes: TSW 1a leaf closure leaf seal, hoist stilts and deck mods, and replace two upper leaves. | 300 | 2500 | 25281 | [13 empty] | Added 10-18-2017 |  | P
16 | IHR | Turbine Passage Survival Program - Ice Harbor Test Turbine | Crum | 334588 | Oversight in FY18. Trolley pipe contract has been delayed. work will shift into FY19. Characterize the pressure, sheer, and strike environment; and estimate direct injury rates and direct survival rates of juvenile salmon through the new fixed blade turbine in Unit 2 using balloon tagged salmon and sensor fish. | 250 | 100 | 25381
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | Wik | 469977 | Design and construction contract award to correct joint deficiency on outfall pipe | 75 | 575 | 25956 | [13 empty] | Deferred to FY19 pending FY18 funding availability |  | W
18 | LGO | Little Goose Spillway Weir Boat Barrier | Sands | 453700 | EDC and S&A effort in FY18. Close out will also occur. | 0 | 0 | 25956 | [15 empty] | W
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | Wik | 456609 | Complete fabrication and installation of permanent cooling system at fish ladder exit. Complete design and contract award on power supply. | 125 | 100 | 26056 | [13 empty] | Budget reduction on 10-18-17; determined M at 9/7/17 SCT meeting. |  | W
20 | LGO | Little Goose Spillway Weir | Aston | 370855 | EDC and S&A effort in FY18. Close out will also occur. | 0 | 0 | 26056
21 | LGR | Lower Granite Spillway PIT Detection | Heller | 368299 | Award design build contract for spillway pit tag detection system at Lower Granite. | 650 | 500 | 26556 | [15 empty] | W
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Wik | TBD | Balloon tag and PIT study; oversight | 100 | 15 | 26571 | [13 empty] | Deferred to FY19 pending FY18 funding availability |  | W
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) and Follow-On | Alturk | 372857 | EDC, S&A and contract modifications for system so we can pass fish by April 16 2018. Automation of orifices will occur in FY19. Design effort for follow on contract for site and safety requirements. | 3000 | 3000 | 29571 | [13 empty] | SA/EDC & commissioning
26 | LGR | Lower Granite Surface Passage Modifications | Heller | 404508 | Design 30% plans and specification to support a design build contract | 250 | 500 | 30071 | [15 empty] | W
27 | LGR | Lower Granite Spillway Weir Boat Barrier | Aston | 459700 | Purchase signs. Project close out. | 200 | 0 | 30071 | [15 empty] | W
28 | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | Wik | 334888 | Repair of trolley pipe system and oversight of studies. | 150 | 75 | 30146
28b | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | Wik | 334888 | Passage and survival study at Lower Granite. Purchase acoustic transmitters for the Lower Granite survival study that will also be used for the spill evaluation studies. | 100 | 100 | 30246
29 | SYS | LMO and LWG SOG vs PROG (SR 10-min intake gate closure) | Wik | 453111 | Lower Monumental deferred until more units are online. Alternatives for Lower Granite were evaluated and proposed solution is being routed for consideration. | 0 | 0 | 30246 | [15 empty] | W
30 | SYS | Snake River Intake Gate Closure | Heller | 149683 | Reinstate 10 Minute Criteria Alternatives Evaluation - Review alternatives and complete a fish passage plan (FPP) that addresses how to meet 10-minute closure | 25 | 10 | 30256 | [13 empty] | Mandatory for safety. |  | W
31 | SYS | Snake River Adult Sockeye Passage Initiatives | Wik | 461410 | FY18 activities include follow-up for the contract and MIPR, adding a forebay temperature string to Lower Monumental and Ice Harbor dams, maintenance of existing temperature arrays, adding temperature monitoring at McNary, looking at possibilities for improving temperature regimes at Lower Monumental and Ice Harbor ladders and assessing possibilities for trap and haul locations/facilities on Lower Snake River projects. | 0 | 275 | 30531 | [13 empty] | Temperature modeling / Scope refinement
32 | SYS | Inland Avian Predation | Colter | 328188 | Project oversight and closeout | 150 | 150 | 30681
33 | SYS | Columbia River System Operations (CRSO) EIS | Gibbons | NA | Prepare alternative impact statement | 6350 | 7800 | 38481
34 | SYS | Snake River Fall Chinook System Survival Study | Wik | 149671 | Study completion; final report | 0 | 35 | 38516 | [13 empty] | Study completion / report
35 | SYS | FCRPS CRFM Program Management and COP Updates (NWW) | McGill | 139435 | Coordination; project and budget support; COP updates | 370 | 400 | 38916 | [15 empty] | P
36 | SYS | FCRPS Spill to the Gas Cap - Spill Pattern Development | Ament | 466539 | Develop spill patterns; John Day physical model design and construction; oversight | 0 | 0 | 38916 | [13 empty] | Model construction / Modeling |  | P
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 38916
38 | SYS | Insert title (Placeholder) | Insert | Insert | Evaluate Feasibility of Alternatives for More Acceptable Turbine Blade Blocking | 0 | 0 | 38916
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 38916
40 | SYS | Sheepy Lake Caspian Tern Island | Turaski | 466191 | Sheepy Island Reconstruction (CATES / EIS) SA/EDC - work to be completed in FY18 | 0 | 0 | 38916 | [13 empty] | Initiated in late FY17 - requires SA/EDC in FY18 - NOT in FY18 Pbud
41 | SYS | Insert title (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | 0 | 0 | 38916
42 | SYS | FCRPS Spill to Gas Cap - Adult and Juvenile Studies | Ament | TBD | Juvenile and adult passage and survival studies; oversight and coordination | 12300 | 11300 | 50216 | [13 empty] | Funding included under FCRPS Court Ordered Spill Evaluation (Scope TBD) / cost to be broken out once studies are scoped
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Medina | 122645 | Project oversight and closeout; locking nut/welding modification prior to closeout | 0 | 150 | 50366
44 | BON | Bonneville Powerhouse 2 Floating Orifice Gates/Bulkheads | Ball | 466128 | Fabrication and installation of bulkheads on the Bonn Floating Orifice Gates (contract ready to advertise) | 0 | 10 | 50376 | [13 empty] | Deferred to FY19 pending FY18 funding availability
[8 empty] | 50376 | [14 empty] | P | #REF!
[8 empty] | 50376 | [14 empty] | W | #REF!
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Regular monitoring, hazing and dissuasion on East Sand Island and Corps constructed islands; oversight and closeout | 630 | 0 | 50376
46 | LGO | Little Goose Adult Ladder Temperature Mitigation: Post-Construction Monitoring | Wik | TBD | scope to be determined. May be covered by other studies. | 0 | 0 | 50376
47 | LWG | Lower Granite Adult Ladder Temperature Mitigation: Post-Construction Monitoring | Wik | 448130 | oversight of biostat contract | 0 | 0 | 50376
48 | SYS | AMIP Spill Test | Wik | 134706 | provide oversight and support to system wide efforts | 0 | 0 | 50376
49 | BON | Bonneville PIT Detection | TBD | TBD | Assess feasibility of prototype PIT detection located at juvenile outfall piers below Bonneville Dam | 0 | 160 | 50536 | [13 empty] | Feasibility in FY18 with possible installation in FY19
50 | LGR | Lower Granite JBS Upgrade Post Construction Evaluation | Wik | 470252 | Post construction evaluation on JBS upgrade | 0 | 0 | 50536

## Ranked Order
CRFM FY18 RANKING SPREADSHEET
| Version: 4/18/2018 (Version 1.0) | FY2019 PBUD TOTAL $46M - $28.975M FCRPS, $17.025M Willamette, and $0 Lamprey
Updated By: I. Chane
PBud- $46M
Line # | Project Location | Measure | FY19 Current Capability | FY19 Preliminary Cumulative | SCT 2019 Average Score
Willamette
1 | Willamette | Total - Willamette | 17025 | 17025 | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 0 | 17025 | M
FCRPS
3 | ESTU | Estuary Habitat Studies | 625 | 17650 | 0
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | 750 | 750 | 0
5 | JDA | John Day Avian Wires | 0 | 0 | 0
6 | JDA | John Day Adult PIT Detection | 0 | 17650 | 0
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 500 | 1250 | 0
8 | SYS | Lower Columbia River Juvenile Survival Studies | 1600 | 1600 | 0
13 | SYS | FCRPS CRFM Program Management (NWP) | 500 | 18150 | 0
16 | IHR | Turbine Passage Survival Program - Ice Harbor Test Turbine | 100 | 1350 | 0
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | 575 | 2175 | 0
18 | LGO | Little Goose Spillway Weir Boat Barrier | 0 | 18150 | 0
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | 100 | 1450 | 0
20 | LGO | Little Goose Spillway Weir | 0 | 2175 | 0
21 | LGR | Lower Granite Spillway PIT Detection | 500 | 18650 | 0
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | 15 | 1465 | 0
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) and Follow-On | 3000 | 5175 | 0
27 | LGR | Lower Granite Spillway Weir Boat Barrier | 0 | 18650 | 0
28 | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | 75 | 1540 | 0
29 | SYS | LMO and LWG SOG vs PROG (SR 10-min intake gate closure) | 0 | 5175 | 0
30 | SYS | Snake River Intake Gate Closure | 10 | 18660 | 0
33 | SYS | Columbia River System Operations (CRSO) EIS | 7800 | 9340 | 0
34 | SYS | Snake River Fall Chinook System Survival Study | 35 | 5210 | 0
35 | SYS | FCRPS CRFM Program Management and COP Updates (NWW) | 400 | 19060 | 0
40 | SYS | Sheepy Lake Caspian Tern Island | 0 | 9340 | 0
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 150 | 5360 | 0
44 | BON | Bonneville Powerhouse 2 Floating Orifice Gates/Bulkheads | 10 | 19070 | 0
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | 0 | 9340 | 0
47 | LWG | Lower Granite Adult Ladder Temperature Mitigation: Post-Construction Monitoring | 0 | 5360 | 0
48 | SYS | AMIP Spill Test | 0 | 19070 | 0
28b | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | 100 | 9440 | 0
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | 0 | 5360 | 0
42 | SYS | FCRPS Spill to Gas Cap - Adult and Juvenile Studies | 11300 | 30370 | 0
36 | SYS | FCRPS Spill to the Gas Cap - Spill Pattern Development | 0 | 9440 | 0
49 | BON | Bonneville PIT Detection | 160 | 5520 | 0
31 | SYS | Snake River Adult Sockeye Passage Initiatives | 275 | 30645 | 0
32 | SYS | Inland Avian Predation | 150 | 9590 | 0
38 | SYS | Insert title (Placeholder) | 0 | 5520 | 0
9 | SYS | Avian Island PIT Detection | 200 | 30845 | 0
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | 50 | 9640 | 0
46 | LGO | Little Goose Adult Ladder Temperature Mitigation: Post-Construction Monitoring | 0 | 5520 | 0
10 | SYS | Turbine Survival Program | 0 | 30845 | 0
14 | MCN | McNary Avian Water Cannon Deficiency Correction and Avian Wire Design Feasibility Report | 100 | 9740 | 0
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | 0 | 5520 | 0
41 | SYS | Insert title (Placeholder) | 0 | 30845 | 0
26 | LGR | Lower Granite Surface Passage Modifications | 500 | 10240 | 0
15 | MCN | McNary Top Spill Weir (TSW) Permanence | 2500 | 8020 | 0
11 | JDA | John Day Mitigation | 436 | 31281 | 0
50 | LGR | Lower Granite JBS Upgrade Post Construction Evaluation | 0 | 10240 | 0